## Summary
Invoices Process Report - Design Projects
Consultant | Framework status | Framework ID | Frame Work Contract | Value | Duration | Start Date | Finsih Date | Committed | Remaining from framework | Invoices w/out VAT | Earned value | Remaining to Invoice
Dorsch food | Closed | MLTX-01-085 | 2547 | 19993600 | 24M | 2023-06-08 | 2025-06-08 | 19558881 | 434719 | 18891265.58 | 19558881 | 667615.42
SYSTRA | Closed | MLTX-01-102 | 2672 | 15054089 | 24M | 2024-02-20 | 2026-02-20 | 15054089 | 0 | 15054089 | 15054089 | 0
EGEC - NIS2 | Ongoing | MLTX-01-099 | 2709 | 19979840 | 48M | 2024-05-09 | 2028-05-09 | 18497269 | 1482571 | 18147017.55 | 18467769 | 320751.45
ENGICON | Closed | RDH4-00-001 | 2666 | 27837620 | 10M | 2024-06-01 | 2025-04-01 | 27837620 | 0 | 25053857.995 | 27837620 | 2783762.005
EGEC - WAS | Ongoing | WAS1-01-039 | TBA | 9799000 | 24M | 2024-11-12 | 2026-11-12 | 7075670 | 2723330 | 7075670.9 | 7075670 | -0.9
ENGICON - Package1 | Ongoing | MLTX-01-098 | 2891 | 19856000 | 60M | 2025-02-12 | 2030-02-12 | 16551382 | 3304618 | 14962620.51 | 15549822.66 | 587202.15 |  | a | b | c
ENGICON - RDH4 | Closed | RDH4-01-002 | TBA | 7025000 | 24M | 2024-11-21 | 2026-11-21 | 7025000 | 0 | 7024999.85 | 14050000 | 7025000.15 | a | 15 | 13 | 15
Dar AlRiyadh 2 | Ongoing | MLTX-01-100 | 2814 | 59999685.82 | 60M | 2024-10-02 | 2029-10-02 | 0 | 59999685.82 | 22554552.33 | 0 | -22554552.33
Meinhardt (KHJ - FOOD) | Ongoing | KHJ1-01-020 | 2966 | 14990000 | 24M | 2025-06-24 | 2027-06-24 | 11685630 | 3304370 | 3939904.93 | 4469255 | 529350.07
Meinhardt (RDH1-01-006) | Ongoing | RDH1-01-006 | 3172 | 25298852.17 |  | 2026-02-04 | 2027-08-03 | 25298852 | 0.17 | 7469770.12 | 12009586.72 | 4539816.6
ENGICON - RDH4 PH2 | Ongoing | RDH4-01-003 | 3026 | 59500000 | 36M | 2025-07-20 | 2028-07-20 | 39471610 | 20028390 | 27536518 | 28199914.91 | 663396.91 |  | 1
AlDar International (KHJ - FOOD2) | Ongoing | KHJ-01-027 | 3041 | 11637180 | 24M | 2025-08-10 | 2027-08-10 | 7146100 | 4491080 | 6043100.3344 | 7146100 | 1102999.6656
ENGICON - Logistics | Ongoing | MLTX-01-117 | 3042 | 27800000 | 24M | 2025-07-30 | 2027-07-30 | 23907174 | 3892826 | 19924324.7 | 22967071.6 | 3042746.9
EGEC - NIS3 | Ongoing |  | 3020 | 19955000 | 48M | 2025-07-10 | 2029-07-10 | 0 | 19955000 | 0 | 0 | 0
TYPSA- (KHJ-AMIC) | Ongoing | KHJ2-01-001 |  | 57332139 |  |  |  | 51542408.52 | 5789730.48 | 7579488.41 | 5647031.8799 | -1932456.5301
Total |  |  |  | 326147696.99 |  |  |  | 201176095.52 | 124971601.47 | 135232967.7844 | 121532221.7699
Formulas:
Start Date = EDATE(Wrapup31[[#This Row],[Finsih Date]], - 24)

## Invoices (2)
CASH FLOW OVERVIEW OF RUNNING PROJECTS
Consultant | Framework ID | S/No. | Projects | Project ID | Task Value | Invoice # 1 date | Invoice # 1 amount | Invoice # 1 vat | Invoice # 1 total | Invoice # 2 date | Invoice # 2 amount | Invoice # 2 vat | Invoice # 2 total | Invoice # 3 date | Invoice # 3 amount | Invoice # 3 vat | Invoice # 3 total | Invoice # 4 date | Invoice # 4 amount | Invoice # 4 vat | Invoice # 4 total | Invoice # 5 date | Invoice # 5 amount | Invoice # 5 vat | Invoice # 5 total | Invoice # 6 date | Invoice # 6 amount | Invoice # 6 vat | Invoice # 6 total | Invoice # 7 date | Invoice # 7 amount | Invoice # 7 vat | Invoice # 7 total | Invoice # 8 date | Invoice # 8 amount | Invoice # 8 vat | Invoice # 8 total | Invoice # 9 date | Invoice # 9 amount | Invoice # 9 vat | Invoice # 9 total | Invoice # 10 date | Invoice # 10 amount | Invoice # 10 vat | Invoice # 10 total | Invoice # 11 date | Invoice # 11 amount | Invoice # 11 vat | Invoice # 11 total | Invoice # 12 date | Invoice # 12 amount | Invoice # 12 vat | Invoice # 12 total | Invoice # 13 date | Invoice # 13 amount | Invoice # 13 vat | Invoice # 13 total | Invoice # 14 date | Invoice # 14 amount | Invoice # 14 vat | Invoice # 14 total | Invoice # 15 date | Invoice # 15 amount | Invoice # 15 vat | Invoice # 15 total | Invoice # 16 date | Invoice # 16 amount | Invoice # 16 vat | Invoice # 16 total | Invoice # 17 date | Invoice # 17 amount | Invoice # 17 vat | Invoice # 17 total | Invoice # 18 date | Invoice # 18 amount | Invoice # 18 vat | Invoice # 18 total | Invoice # 19 date | Invoice # 19 amount | Invoice # 19 vat | Invoice # 19 total | Invoice # 20 date | Invoice # 20 amount | Invoice # 20 vat | Invoice # 20 total | Invoice # 21 date | Invoice # 21 amount | Invoice # 21 vat | Invoice # 21 total | Invoice # 22 date | Invoice # 22 amount | Invoice # 22 vat | Invoice # 22 total | Invoice # 23 date | Invoice # 23 amount | Invoice # 23 vat | Invoice # 23 total | Invoice # 24 date | Invoice # 24 amount | Invoice # 24 vat | Invoice # 24 total | Invoice # 25 date | Invoice # 25 amount | Invoice # 25 vat | Invoice # 25 total | Remarks | Task Value2 | VAT | Total | Invoices Submitted Without VAT | Invoices Submitted With VAT | % Completion | Earned Value | Remaining Value
Dorsch food | MLTX-01-085 | 1 | Jeddah 2 - Food Cluster - RBF 450 & 900 m2 | JDH2-01-016 | 877779 | 2023-10-26 | 416905 | 62535.75 | 479440.75 |  |  |  |  | 2024-04-16 | 368699 | 55304.85 | 424003.85 | [89 empty] | 877779 | 131666.85 | 1009445.85 | 785604 | 903444.6 | 100% | 877779 | 92175
Dorsch food | MLTX-01-085 | 2 | Jeddah Food Cluster - Masterplan Update & Lands Selection at Jeddah 2nd & 3rd Ind. Cities | MLTX-01-093 | 1403611 | 2023-10-26 | 1403611 | 210541.65 | 1614152.65 | [97 empty] | 1403611 | 210541.65 | 1614152.65 | 1403611 | 1614152.65 | 100% | 1403611 | 0
Dorsch food | MLTX-01-085 | 3 | Jeddah 3 - Design of Shared Dry & Cold Storage Warehouses in Jeddah 3 Ind. City | JDH3-01-021 | 2999654 | 2023-10-26 | 1377997 | 206699.55 | 1584696.55 |  |  |  |  | 2024-04-16 | 1297326 | 194598.9 | 1491924.9 | [89 empty] | 2999654 | 449948.1 | 3449602.1 | 2675323 | 3076621.45 | 100% | 2999654 | 324331
Dorsch food | MLTX-01-085 | 4 | Master planning a logistic area in Dammam 2 | DAM2-01-026 | 4125000 |  |  |  |  | 2024-03-19 | 682683 | 102402.45 | 785085.45 |  |  |  |  | 2024-05-23 | 1379810.1 | 206971.515 | 1586781.615 |  |  |  |  | 2024-06-28 | 2062506.53 | 309375.9795 | 2371882.5095 | [77 empty] | 4125000 | 618750 | 4743750 | 4124999.63 | 4743749.5745 | 100% | 4125000 | 0.37
Dorsch food | MLTX-01-085 | 5 | Hydrology Study for preventing Jeddah 4th Industrial City from floods and stormwater | JDH4-01-040 | 404258 | [12 empty] | 2024-05-23 | 125226 | 18783.9 | 144009.9 | [8 empty] | 2024-09-02 | 279032 | 41854.8 | 320886.8 | [73 empty] | 404258 | 60638.7 | 464896.7 | 404258 | 464896.7 | 100% | 404258 | 0
Dorsch food | MLTX-01-085 | 6 | Completing the infrastructure networks and residential neighborhood in the 2nd industrial city in Dammam | DAM2-02-027 | 6968306 | [16 empty] | 2024-06-08 | 2539503 | 380925.45 | 2920428.45 | [8 empty] | 2024-09-05 | 1602086 | 240312.9 | 1842398.9 | [16 empty] | 2025-03-12 | 2826717.95 | 424007.6925 | 3250725.6425 | [49 empty] | 6968306 | 1045245.9 | 8013551.9 | 6968306.95 | 8013552.9925 | 100% | 6968306 | -0.95
Dorsch food | MLTX-01-085 | 7 | Reviewing the masterplan for alkhrj nd. City |  | 174000 | [16 empty] | 2024-06-08 | 58000.11 | 8700.0165 | 66700.1265 | 2024-06-28 | 115999.89 | 17399.9835 | 133399.8735 | [77 empty] | 174000 | 26100 | 200100 | 174000 | 200100 | 100% | 174000 | 0
Dorsch food | MLTX-01-085 | 8 | Detail MPL and infra Design for the multi-use area in Dammam2 | DAM2-01-029 | 836000 | [32 empty] | 2024-10-07 | 302500.8 | 45375.12 | 347875.92 | 2024-12-24 | 533499.2 | 80024.88 | 613524.08 | [61 empty] | 836000 | 125400 | 961400 | 836000 | 961400 | 100% | 836000 | 0
Dorsch food | MLTX-01-085 | 9 | Design shared services center - Food cluster | JDH2-01-023 | 1505768 | [32 empty] | 2024-10-07 | 499280 | 74892 | 574172 |  |  |  |  | 2025-02-05 | 500302 | 75045.3 | 575347.3 | 2025-03-04 | 255076 | 38261.4 | 293337.4 | [53 empty] | 1505768 | 225865.2 | 1731633.2 | 1254658 | 1442856.7 | 100% | 1505768 | 251110
Dorsch food | MLTX-01-085 | 10 | الدراسه القيميه لمشاريع المصانع الجاهزة |  | 264505 | [36 empty] | 2024-12-24 | 264505 | 39675.75 | 304180.75 | [61 empty] | 264505 | 39675.75 | 304180.75 | 264505 | 304180.75 | 100% | 264505 | 0
SYSTRA | MLTX-01-102 | 1 | Masterplan & Infrstructure Detailed Design For Technology Zones (Jenadryah) | JNDT-01-001 | 6726972 | 2024-07-31 | 672697.82 | 100904.673 | 773602.493 | 2024-08-07 | 1681772 | 252265.8 | 1934037.8 | 2024-12-15 | 1345449 | 201817.35 | 1547266.35 | 2025-03-11 | 1681658.78 | 252248.817 | 1933907.597 |  |  |  |  | 2025-07-01 | 1345394.4 | 201809.16 | 1547203.56 | [77 empty] | 6726972 | 1009045.8 | 7736017.8 | 6726972 | 7736017.8 | 100% | 6726972 | 0
SYSTRA | MLTX-01-102 | 2 | Masterplan & Infrstructure Detailed Design For Technology Zones (Dammam) | DAMT-01-001 | 3300435 | [12 empty] | 2025-03-11 | 330043.5 | 49506.525 | 379550.025 | 2025-05-11 | 1072641.37 | 160896.2055 | 1233537.5755 | 2025-07-01 | 577576.13 | 86636.4195 | 664212.5495 | 2026-05-10 | 1320174 | 198026.1 | 1518200.1 | [73 empty] | 3300435 | 495065.25 | 3795500.25 | 3300435 | 3795500.25 | 100% | 3300435 | 0
SYSTRA | MLTX-01-102 | 3 | Masterplan & Infrstructure Detailed Design For Technology Zones (Dhahran) | DHRT-01-001 | 3300435 | [12 empty] | 2025-03-11 | 330043.5 | 49506.525 | 379550.025 | 2025-05-11 | 1072641.38 | 160896.207 | 1233537.587 | 2025-07-01 | 577576.12 | 86636.418 | 664212.538 | 2026-05-10 | 1320174 | 198026.1 | 1518200.1 | [73 empty] | 3300435 | 495065.25 | 3795500.25 | 3300435 | 3795500.25 | 100% | 3300435 | 0
SYSTRA | MLTX-01-102 | 4 | Technical review and transport planning expertise support for Riyadh Industrial cities 1 & 4 | MLTX-01-111 | 1726247 | [16 empty] | 2025-05-11 | 1208357.98 | 181253.697 | 1389611.677 | 2025-07-01 | 517889.02 | 77683.353 | 595572.373 | [77 empty] | 1726247 | 258937.05 | 1985184.05 | 1726247 | 1985184.05 | 100% | 1726247 | 0
EGEC - NIS2 | MLTX-01-099 | 1 | Updated concept masterplan & Infrastructure designs for Tabouk ind. City | TAB-01-009 | 4360270 | 2024-07-23 | 1395290.5 | 209293.575 | 1604584.075 | 2024-08-28 | 1874916.39 | 281237.4585 | 2156153.8485 | [8 empty] | 2024-11-30 | 872049.61 | 130807.4415 | 1002857.0515 | 2024-12-25 | 218013.5 | 32702.025 | 250715.525 | [77 empty] | 4360270 | 654040.5 | 5014310.5 | 4360270 | 5014310.5 | 100% | 4360270 | 5.0003e-06
EGEC - NIS2 | MLTX-01-099 | 2 | Project support services (6 months) (Masterplan) |  | 744150 |  |  |  |  | 2024-08-28 | 372075 | 55811.25 | 427886.25 |  |  |  |  | 2024-10-31 | 372075 | 55811.25 | 427886.25 | [85 empty] | 744150 | 111622.5 | 855772.5 | 744150 | 855772.5 | 100% | 744150 | 0
EGEC - NIS2 | MLTX-01-099 | 3 | Project support services (6 months) (VRO) |  | 744150 | [24 empty] | 2025-01-31 | 372075 | 55811.25 | 427886.25 | [12 empty] | 2025-05-30 | 372075 | 55811.25 | 427886.25 | [57 empty] | 744150 | 111622.5 | 855772.5 | 744150 | 855772.5 | 100% | 744150 | 0
EGEC - NIS2 | MLTX-01-099 | 4 | Testing and evaluating concrete structure |  | 153002 |  |  |  |  | 2024-08-28 | 107101.54 | 16065.231 | 123166.771 | 2024-10-21 | 45900.66 | 6885.099 | 52785.759 | [89 empty] | 153002 | 22950.3 | 175952.3 | 153002.2 | 175952.53 | 100% | 153002 | -0.2
EGEC - NIS2 | MLTX-01-099 | 5 | Preliminary designs for the expansion of the industrial city in riyadh |  | 156177 | [8 empty] | 2024-10-21 | 109323.9 | 16398.585 | 125722.485 |  |  |  |  | 2024-11-30 | 46853.1 | 7027.965 | 53881.065 | [81 empty] | 156177 | 23426.55 | 179603.55 | 156177 | 179603.55 | 100% | 156177 | 0
EGEC - NIS2 | MLTX-01-099 | 6 | Incubators in Al-Qassim Oasis | QSM3-01-014 | 1656100 | [16 empty] | 2024-11-30 | 248415 | 37262.25 | 285677.25 | 2024-12-25 | 828050 | 124207.5 | 952257.5 | 2025-01-31 | 579635 | 86945.25 | 666580.25 | [73 empty] | 1656100 | 248415 | 1904515 | 1656100 | 1904515 | 100% | 1656100 | 0
EGEC - NIS2 | MLTX-01-099 | 7 | Site development and infrastructure design works for expansion in Jeddah 1 | JDH1-01-021 | 2560090 | [24 empty] | 2025-01-31 | 384013.5 | 57602.025 | 441615.525 |  |  |  |  | 2025-04-13 | 384013.5 | 57602.025 | 441615.525 | 2025-04-30 | 640022.5 | 96003.375 | 736025.875 | 2025-05-30 | 896032 | 134404.8 | 1030436.8 | 2025-07-27 | 256008.5 | 38401.275 | 294409.775 | [53 empty] | 2560090 | 384013.5 | 2944103.5 | 2560090 | 2944103.5 | 100% | 2560090 | 0
EGEC - NIS2 | MLTX-01-099 | 8 | Detailed design of connection road (Fly Over) in Dammam 2 | DAM2-01-033 | 2310000 | [32 empty] | 2025-04-13 | 693000 | 103950 | 796950 | [36 empty] | 2026-04-28 | 577500 | 86625 | 664125 | 2026-06-17 | 808500 | 121275 | 929775 | [21 empty] | 2310000 | 346500 | 2656500 | 2079000 | 2390850 | 100% | 2310000 | 231000
EGEC - NIS2 | MLTX-01-099 | 9 | Labour camp masterplan and infrastructure development in AlKharj | KHJ-01-025 | 350000 | [28 empty] | 2025-03-02 | 175000 | 26250 | 201250 | 2025-04-13 | 175000 | 26250 | 201250 | [65 empty] | 350000 | 52500 | 402500 | 350000 | 402500 | 100% | 350000 | 0
EGEC - NIS2 | MLTX-01-099 | 10 | Potable water pipeline supply and connection to alkharj 1st ind. City | KHJ-01-026 | 534490 | [32 empty] | 2025-04-13 | 210000 | 31500 | 241500 | [12 empty] | 2025-09-07 | 175000.64 | 26250.096 | 201250.736 | [8 empty] | 2025-12-03 | 140000 | 21000 | 161000 | 2025-12-23 | 9490 | 1423.5 | 10913.5 | [33 empty] | 534490 | 80173.5 | 614663.5 | 534490.64 | 614664.236 | 100% | 534490 | -0.64
EGEC - NIS2 | MLTX-01-099 | 11 | Study design RBFs 900 & 450m2 SFDA requirements |  | 170000 | [32 empty] | 2025-04-13 | 85000 | 12750 | 97750 | [16 empty] | 2025-09-29 | 85000 | 12750 | 97750 | [45 empty] | 170000 | 25500 | 195500 | 170000 | 195500 | 100% | 170000 | 0
EGEC - NIS2 | MLTX-01-099 | 12 | Improving the entrances and exit points for Jeddah 1 | JDH1-01-028 | 1590000 | [56 empty] | 2025-10-26 | 794999.1 | 119249.865 | 914248.965 |  |  |  |  | 2025-12-23 | 556500 | 83475 | 639975 | [8 empty] | 2026-06-17 | 119250 | 17887.5 | 137137.5 | [21 empty] | 1590000 | 238500 | 1828500 | 1470749.1 | 1691361.465 | 100% | 1590000 | 119250.9
EGEC - NIS2 | MLTX-01-099 | 13 | Hydrology study for Jeddah 2 | JDH2-01-028 | 110500 | [56 empty] | 2025-10-26 | 44199.17 | 6629.8755 | 50829.0455 | [8 empty] | 2026-02-03 | 66300 | 9945 | 76245 | [29 empty] | 110500 | 16575 | 127075 | 110499.17 | 127074.0455 | 100% | 110500 | 0.83
EGEC - NIS2 | MLTX-01-099 | 14 | Jenadriyadh Business Incubators | JNDT-01-002 | 500000 | [60 empty] | 2025-12-03 | 100000 | 15000 | 115000 | 2025-12-23 | 225000 | 33750 | 258750 | 2026-02-03 | 100000 | 15000 | 115000 | 2026-04-28 | 75000 | 11250 | 86250 | [25 empty] | 500000 | 75000 | 575000 | 500000 | 575000 | 100% | 500000 | 0
EGEC - NIS2 | MLTX-01-099 | 15 | Project support services 3 |  | 1798340 | [48 empty] | 2025-09-07 | 449585 | 67437.75 | 517022.75 | 2025-09-29 | 449585 | 67437.75 | 517022.75 | [8 empty] | 2025-12-23 | 449585 | 67437.75 | 517022.75 | 2026-02-03 | 449585 | 67437.75 | 517022.75 | [29 empty] | 1798340 | 269751 | 2068091 | 1798340 | 2068091 | 100% | 1798340 | 0
EGEC - NIS2 | MLTX-01-099 | 16 | Adaptation and Design of an Administrative Building Humanization in Riyadh 2 | RDH2-01-031 | 590000 | [52 empty] | 2025-09-29 | 471999.23 | 70799.8845 | 542799.1145 |  |  |  |  | 2025-12-03 | 59000 | 8850 | 67850 |  |  |  |  | 2026-02-03 | 59000 | 8850 | 67850 | [29 empty] | 590000 | 88500 | 678500 | 589999.23 | 678499.1145 | 95% | 560500 | -29499.23
EGEC - NIS2 | MLTX-01-099 | 17 | Ddevelopment The walkway In residential area Jeddah1 |  | 170000 | [72 empty] | 2026-04-28 | 119000 | 17850 | 136850 | 2026-06-17 | 51000.21 | 7650.0315 | 58650.2415 | [21 empty] | 170000 | 25500 | 195500 | 170000.21 | 195500.2415 | 100% | 170000 | -0.21
ENGICON | RDH4-00-001 | 1 | Riyadh 4 Masterplan and Infrastructure concept design |  | 27837620 | 2024-07-07 | 2361050.1 | 354157.515 | 2715207.615 | 2024-08-07 | 3157746.651 | 473661.9976 | 3631408.6486 | 2024-08-31 | 3983985.909 | 597597.8863 | 4581583.7954 | 2024-10-02 | 3449998.296 | 517499.7444 | 3967498.0404 | 2024-12-10 | 1820099.709 | 273014.9563 | 2093114.6653 | 2025-01-28 | 999999.999 | 149999.9998 | 1149999.9989 | 2025-03-04 | 2695839.615 | 404375.9423 | 3100215.5573 | 2025-04-20 | 2223402.876 | 333510.4314 | 2556913.3074 | 2025-05-12 | 1742432.4 | 261364.86 | 2003797.26 | 2025-06-01 | 2619302.44 | 392895.366 | 3012197.806 | [61 empty] | 27837620 | 4175643 | 32013263 | 25053857.995 | 28811936.6943 | 100% | 27837620 | 2783762.005
ENGICON | RDH4-00-001 | [108 empty] | 0 | 0
EGEC - WAS | WAS1-01-039 | 1 | Site development and buildings design for labour community area in WAS industrial city | WAS1-01-035 | 4421850 | 2024-03-03 | 1726555 | 258983.25 | 1985538.25 |  |  |  |  | 2025-04-30 | 1641704.68 | 246255.702 | 1887960.382 | 2025-05-30 | 611379 | 91706.85 | 703085.85 | 2025-07-27 | 221091 | 33163.65 | 254254.65 | 2025-09-01 | 221120.33 | 33168.0495 | 254288.3795 | [77 empty] | 4421850 | 663277.5 | 5085127.5 | 4421850.01 | 5085127.5115 | 100% | 4421850 | -0.01
EGEC - WAS | WAS1-01-039 | 2 | Design commercial area with fuel station in Waad AlShamal | WAS-01-034 | 650000 |  |  |  |  | 2024-04-13 | 195000 | 29250 | 224250 | 2025-04-30 | 227500 | 34125 | 261625 | 2025-05-30 | 227500 | 34125 | 261625 | [85 empty] | 650000 | 97500 | 747500 | 650000 | 747500 | 100% | 650000 | 0
EGEC - WAS | WAS1-01-039 | 4 | Development of labour camps in: DAM03, NJR, MKH2, JDH2, SUD, ASR1 | MLTX-01-119 | 1150000 | [16 empty] | 2025-07-27 | 115000 | 17250 | 132250 |  |  |  |  | 2025-09-17 | 460000 | 69000 | 529000 | 2025-10-26 | 575000 | 86250 | 661250 | [69 empty] | 1150000 | 172500 | 1322500 | 1150000 | 1322500 | 100% | 1150000 | 0
EGEC - WAS | WAS1-01-039 | 4 | Project support services 4 |  | 853820 | [32 empty] | 2025-12-03 | 284606.76 | 42691.014 | 327297.774 | 2026-02-03 | 355759.13 | 53363.8695 | 409122.9995 | 2026-07-02 | 213455 | 32018.25 | 245473.25 | [57 empty] | 853820 | 128073 | 981893 | 853820.89 | 981894.0235 | 100% | 853820 | -0.89
ENGICON - RDH4 | RDH4-01-002 | 1 | Design work for entrance and facilities for Riyadh 4 |  | 7025000 | 2025-01-27 | 1999999.85 | 299999.9775 | 2299999.8275 | 2025-07-01 | 2350000 | 352500 | 2702500 | 2025-07-10 | 2675000 | 401250 | 3076250 | [89 empty] | 7025000 | 1053750 | 8078750 | 7024999.85 | 8078749.8275 | 100% | 7025000 | 0.15
ENGICON - RDH4 | RDH4-01-002 | [105 empty] | 7025000 | 1053750 | 8078750 | 0 | 0 |  | 7025000 | 0.15
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 1 | 2024-12-19 | 40768 | 6115.2 | 46883.2 | [100 empty] | 40768 | 46883.2 | 100% | 0 | -40768
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 2 | 2024-12-19 | 866679.33 | 130001.8995 | 996681.2295 | [100 empty] | 866679.33 | 996681.2295 | 100% | 0 | -866679.33
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 3 | 2025-01-01 | 1114782.01 | 167217.3015 | 1281999.3115 | [100 empty] | 1114782.01 | 1281999.3115 | 100% | 0 | -1114782.01
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 4 | 2025-02-04 | 1206719.08 | 181007.862 | 1387726.942 | [100 empty] | 1206719.08 | 1387726.942 | 100% | 0 | -1206719.08
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 5 | 2025-03-03 | 1200633.93 | 180095.0895 | 1380729.0195 | [100 empty] | 1200633.93 | 1380729.0195 | 100% | 0 | -1200633.93
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 6 | 2025-04-08 | 1118030.39 | 167704.5585 | 1285734.9485 | [100 empty] | 1118030.39 | 1285734.9485 | 100% | 0 | -1118030.39
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 7 | 2025-05-04 | 1216426.3 | 182463.945 | 1398890.245 | [100 empty] | 1216426.3 | 1398890.245 | 100% | 0 | -1216426.3
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 8 | 2025-06-01 | 1310618.68 | 196592.802 | 1507211.482 | [100 empty] | 1310618.68 | 1507211.482 | 100% | 0 | -1310618.68
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 9 | 2025-07-02 | 1147200.41 | 172080.0615 | 1319280.4715 | [100 empty] | 1147200.41 | 1319280.4715 | 100% | 0 | -1147200.41
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 10 | 2025-08-04 | 1122204.53 | 168330.6795 | 1290535.2095 | [100 empty] | 1122204.53 | 1290535.2095 | 100% | 0 | -1122204.53
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 11 | 2025-09-01 | 1165613.3 | 174841.995 | 1340455.295 | [100 empty] | 1165613.3 | 1340455.295 | 100% | 0 | -1165613.3
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 12 | 2025-10-01 | 1069979.68 | 160496.952 | 1230476.632 | [100 empty] | 1069979.68 | 1230476.632 | 100% | 0 | -1069979.68
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 13 | 2025-11-02 | 1203549.11 | 180532.3665 | 1384081.4765 | [100 empty] | 1203549.11 | 1384081.4765 | 100% | 0 | -1203549.11
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 14 | 2025-12-03 | 1075450.04 | 161317.506 | 1236767.546 | [100 empty] | 1075450.04 | 1236767.546 | 100% | 0 | -1075450.04
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 15 | 2026-01-04 | 1147266.4 | 172089.96 | 1319356.36 | [100 empty] | 1147266.4 | 1319356.36 | 100% | 0 | -1147266.4
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 16 | 2026-02-01 | 1116684.52 | 167502.678 | 1284187.198 | [100 empty] | 1116684.52 | 1284187.198 | 100% | 0 | -1116684.52
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 17 | 2026-03-01 | 1127991.11 | 169198.6665 | 1297189.7765 | [100 empty] | 1127991.11 | 1297189.7765 | 100% | 0 | -1127991.11
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 18 | 2026-04-01 | 1083424.63 | 162513.6945 | 1245938.3245 | [100 empty] | 1083424.63 | 1245938.3245 | 100% | 0 | -1083424.63
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 19 | 2026-05-01 | 1062629.68 | 159394.452 | 1222024.132 | [100 empty] | 1062629.68 | 1222024.132 | 100% | 0 | -1062629.68
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 20 | 2026-06-01 | 1059489.76 | 158923.464 | 1218413.224 | [100 empty] | 1059489.76 | 1218413.224 | 100% | 0 | -1059489.76
Dar AlRiyadh 2 | MLTX-01-100 |  |  |  | 21 | 2026-07-01 | 1098411.44 | 164761.716 | 1263173.156 | [100 empty] | 1098411.44 | 1263173.156 | 100% | 0 | -1098411.44
Dar AlRiyadh 2 | MLTX-01-100 | [108 empty] | 0 | 0
Dar AlRiyadh 2 | MLTX-01-100 | [108 empty] | 0 | 0
ENGICON - Package1 | MLTX-01-098 | 1 | NIS Design adaptation of RBF 450 , 900 m2 |  | 7940002 | 2025-01-28 | 3062572.2 | 459385.83 | 3521958.03 | 2025-07-10 | 1814857.6 | 272228.64 | 2087086.24 | [12 empty] | 2025-10-08 | 2296929.16 | 344539.374 | 2641468.534 |  |  |  |  | 2025-11-30 | 765643.05 | 114846.4575 | 880489.5075 | [69 empty] | 7940002 | 1191000.3 | 9131002.3 | 7940002.01 | 9131002.3115 | 100% | 7940002 | -0.01
ENGICON - Package1 | MLTX-01-098 | 2 | Detailed design of lake park and supply connection for Sudair Industrial City | SUD1-01-033 | 1658659 | 2025-01-28 | 746396.55 | 111959.4825 | 858356.0325 | 2025-07-10 | 912262.45 | 136839.3675 | 1049101.8175 | [93 empty] | 1658659 | 248798.85 | 1907457.85 | 1658659 | 1907457.85 | 100% | 1658659 | 0
ENGICON - Package1 | MLTX-01-098 | 3 | Technology Zone- Asfan | ASFT-01-001 | 1192999 | [8 empty] | 2025-07-21 | 119240 | 17886 | 137126 | 2025-08-24 | 417907 | 62686.05 | 480593.05 | 2025-09-29 | 268306 | 40245.9 | 308551.9 |  |  |  |  | 2025-10-29 | 387546 | 58131.9 | 445677.9 | [73 empty] | 1192999 | 178949.85 | 1371948.85 | 1192999 | 1371948.85 | 100% | 1192999 | 0
ENGICON - Package1 | MLTX-01-098 | 4 | Technology Zone- Khumra | KUMT-01-001 | 1318399 | [8 empty] | 2025-07-21 | 131844 | 19776.6 | 151620.6 | 2025-08-24 | 461503 | 69225.45 | 530728.45 | 2025-09-29 | 296604 | 44490.6 | 341094.6 |  |  |  |  | 2025-10-29 | 428448 | 64267.2 | 492715.2 | [73 empty] | 1318399 | 197759.85 | 1516158.85 | 1318399 | 1516158.85 | 100% | 1318399 | 0
ENGICON - Package1 | MLTX-01-098 | 5 | Riyadh 3 Business incubators | RDH3-01-012 | 1230000 | [24 empty] | 2025-10-29 | 123052 | 18457.8 | 141509.8 | 2025-11-30 | 122987 | 18448.05 | 141435.05 | 2025-12-14 | 122987 | 18448.05 | 141435.05 | 2026-02-04 | 676477 | 101471.55 | 777948.55 | 2026-04-13 | 184497 | 27674.55 | 212171.55 | [57 empty] | 1230000 | 184500 | 1414500 | 1230000 | 1414500 | 100% | 1230000 | 0
ENGICON - Package1 | MLTX-01-098 | 6 | Bonded Zone in Jeddah 3rd Industrial City-MSC |  | 2210695 | [40 empty] | 2026-04-13 | 331568 | 49735.2 | 381303.2 | 2026-05-12 | 773781 | 116067.15 | 889848.15 |  |  |  |  | 2026-07-15 | 442105 | 66315.75 | 508420.75 | [45 empty] | 2210695 | 331604.25 | 2542299.25 | 1547454 | 1779572.1 | 90% | 1989625.5 | 442171.5
ENGICON - Package1 | MLTX-01-098 | 7 | Adimn Building In Riyadh 4 |  | 1000628 | [48 empty] | 2026-06-23 | 75107.5 | 11266.125 | 86373.625 | [49 empty] | 1000628 | 150094.2 | 1150722.2 | 75107.5 | 86373.625 | 22% | 220138.16 | 145030.66
Meinhardt (KHJ- FOOD) | KHJ1-01-020 | 1 | Development of Design guidelines, production strategy, and prototype packages for mid-sized RBFs |  | 2997130 | 2025-10-09 | 299713 | 44956.95 | 344669.95 | 2025-10-21 | 299713 | 44956.95 | 344669.95 | 2025-10-29 | 599426.07 | 89913.9105 | 689339.9805 | 2025-12-08 | 157349.33 | 23602.3995 | 180951.7295 | 2025-12-08 | 157349.33 | 23602.3995 | 180951.7295 | 2026-01-06 | 134870.85 | 20230.6275 | 155101.4775 | 2026-03-03 | 569454.69 | 85418.2035 | 654872.8935 | 2026-04-19 | 779253.66 | 116888.049 | 896141.709 | [69 empty] | 2997130 | 449569.5 | 3446699.5 | 2997129.93 | 3446699.4195 | 100% | 2997130 | 0.07
Meinhardt (KHJ- FOOD) | KHJ1-01-020 | 2 | Development of full Design for Multi - Story Building for foure Sities |  | 5188500 | [32 empty] | 2026-06-18 | 255925 | 38388.75 | 294313.75 | [8 empty] | 2026-08-19 | 511850 | 76777.5 | 588627.5 | [53 empty] | 5188500 | 778275 | 5966775 | 767775 | 882941.25 | 25% | 1297125 | 529350
Meinhardt (KHJ- FOOD) | KHJ1-01-020 | 3 | Development of full Design Of Mid RBFs for Food , Machinery & Equipment and Pharmceutical Cluster |  | 3500000 | [32 empty] | 2026-06-18 | 175000 | 26250 | 201250 | [65 empty] | 3500000 | 525000 | 4025000 | 175000 | 201250 | 5% | 175000 | 0
ENGICON - RDH4 PH2 | RDH4-01-003 | 1 | 70 RBF's in Riyadh 04 | RDH4-01-003 | 2490457 | 2025-11-05 | 747154 | 112073.1 | 859227.1 |  | 622572 | 93385.8 | 715957.8 | 2025-12-22 | 622572 | 93385.8 | 715957.8 |  |  |  |  | 2026-04-13 | 498159 | 74723.85 | 572882.85 | [81 empty] | 2490457 | 373568.55 | 2864025.55 | 2490457 | 2864025.55 | 100% | 2490457 | 0
ENGICON - RDH4 PH2 | RDH4-01-003 | 2 | Development for the Masterplan and Concept Infrastructure for the expansion of Riyadh 4 industrial city | RDH4-01-005 | 24501677 | 2025-11-05 | 7963335 | 1194500.25 | 9157835.25 |  |  |  |  | 2025-12-22 | 3062800.5 | 459420.075 | 3522220.575 | 2026-04-02 | 2450222.5 | 367533.375 | 2817755.875 |  |  |  |  | 2026-04-15 | 5512659.5 | 826898.925 | 6339558.425 |  |  |  |  | 2026-07-06 | 5512659.5 | 826898.925 | 6339558.425 | [69 empty] | 24501677 | 3675251.55 | 28176928.55 | 24501677 | 28176928.55 | 100% | 24501677 | 0
ENGICON - RDH4 PH2 | RDH4-01-003 | 3 | Design Bridge 3rd HIGHWAY RiyaDH 4 |  | 1124289 | [16 empty] | 2026-04-13 | 168701 | 25305.15 | 194006.15 | [81 empty] | 1124289 | 168643.35 | 1292932.35 | 168701 | 194006.15 | 25% | 281072.25 | 112371.25
ENGICON - RDH4 PH2 | RDH4-01-003 | 4 | Oasis Lab Riyadh 4 |  | 2504618 | [24 empty] | 2026-06-23 | 187841.5 | 28176.225 | 216017.725 |  |  |  |  | 2026-07-15 | 187841.5 | 28176.225 | 216017.725 | [65 empty] | 2504618 | 375692.7 | 2880310.7 | 375683 | 432035.45 | 37% | 926708.66 | 551025.66
ENGICON - RDH4 PH2 | RDH4-01-003 | 5 | Riyadh4 Industrial City expansion 1&2 |  | 8850569 | [104 empty] | 0 | 0
AlDar International (KHJ - FOOD2) | KHJ-01-027 | 1 | AlKharj Food cluster | KHJ1-01-030 | 7146100 | 2025-10-30 | 659049.98 | 98857.497 | 757907.477 | 2025-11-20 | 776250 | 116437.5 | 892687.5 | 2026-04-01 | 1090800.0001 | 163620 | 327240 |  | 3517000.3543 | 527550.0531 | 4044550.4075 | [85 empty] | 7146100 | 1071915 | 8218015 | 6043100.3344 | 6022385.3845 | 100% | 7146100 | 1102999.6656
AlDar International (KHJ - FOOD2) | KHJ-01-027 | [108 empty] | 0 | 0
AlDar International (KHJ - FOOD2) | KHJ-01-027 | [108 empty] | 0 | 0
ENGICON - Logistics | MLTX-01-117 | 1 | Logistic Zones (JDH3,DAM3,MAD,MKH2) | MLTX-01-123 | 19206662 | 2025-09-29 | 960349 | 144052.35 | 1104401.35 | 2025-10-08 | 960349 | 144052.35 | 1104401.35 | 2025-10-29 | 288080.85 | 43212.1275 | 331292.9775 | 45992 | 2784853.1 | 417727.965 | 3202581.065 | 2025-12-21 | 2496772.25 | 374515.8375 | 2871288.0875 | 2026-02-04 | 4897779.9 | 734666.985 | 5632446.885 | 2026-04-13 | 5185884.6 | 777882.69 | 5963767.29 | [73 empty] | 19206662 | 2880999.3 | 22087661.3 | 17574068.7 | 20210179.005 | 100% | 19206662 | 1632593.3
ENGICON - Logistics | MLTX-01-117 | 2 | SIDF-RBF SITE ADAPTATION 450 &900M2 IN 5 CITIES |  | 4700512 | [28 empty] | 2026-07-02 | 940240 | 141036 | 1081276 | 2026-07-15 | 1410016 | 211502.4 | 1621518.4 | [65 empty] | 4700512 | 705076.8 | 5405588.8 | 2350256 | 2702794.4 | 80% | 3760409.6 | 1410153.6
ENGICON - Logistics | MLTX-01-117 | 3 | [107 empty] | 0 | 0
EGEC - NIS3 | [109 empty] | 0 | 0
EGEC - NIS3 | [109 empty] | 0 | 0
EGEC - NIS3 | [109 empty] | 0 | 0
TYPSA- (KHJ2-01-001) | KHJ2-01-001 | 1 | Design and Engineering Support Works for the Master Plan and Infrastructure Project for the Military Industries City in Al Kharj | KHJ2-01-002 | 42715823.6 | 2025-11-30 | 857830 | 128674.5 | 986504.5 | 2025-12-23 | 1510048.5 | 226507.275 | 1736555.775 | 2026-02-02 | 1681963.09 | 252294.4635 | 1934257.5535 | 2026-04-05 | 290932.38 | 43639.857 | 334572.237 | 2026-04-22 | 514671 | 77200.65 | 591871.65 | 2026-06-08 | 1362021.71 | 204303.2565 | 1566324.9665 | 2026-07-06 | 1362021.73 | 204303.2595 | 1566324.9895 | [73 empty] | 42715823.6 | 6407373.54 | 49123197.14 | 7579488.41 | 8716411.6715 | 13.22% | 5647031.8799 | -1932456.5301
TYPSA- (KHJ2-01-001) | KHJ2-01-001 | 2 | Strategic Advisory and Military Industrial Planning Support Services | KHJ2-01-007 | 2142000 | [104 empty] | 0 | 0
TYPSA- (KHJ2-01-001) | KHJ2-01-000 | 3 | Comprehensive Facility Survey & Update of As-Builts, Al Kharj MIC | KHJ2-01-006 | 6684584.92 | [104 empty] | 0 | 0
Meinhardt (RDH1-01-006) | RDH1-01-006 | 1 | Riyadh 1 Industrial City Masterplan | RDH1-01-007 | 16898852 | 2026-04-26 | 844942.61 | 126741.3915 | 971684.0015 | 2026-05-13 | 422471 | 63370.65 | 485841.65 | 2026-06-11 | 422471.3 | 63370.695 | 485841.995 | 2026-07-06 | 844942.61 | 126741.3915 | 971684.0015 | 2026-07-27 | 422471.3 | 63370.695 | 485841.995 |  |  |  |  | 2026-08-16 | 422471.3 | 63370.695 | 485841.995 | [73 empty] | 16898852 | 2534827.8 | 19433679.8 | 3379770.12 | 3886735.638 | 36% | 6083586.72 | 2703816.6
Meinhardt (RDH1-01-006) | RDH1-01-006 | 2 | Riyadh 1-Codes and Guidelines | RDH1-01-008 | 6200000 | 2026-04-26 | 310000 | 46500 | 356500 | 2026-05-13 | 1240000 | 186000 | 1426000 | 2026-06-11 | 620000 | 93000 | 713000 |  |  |  |  | 2026-07-27 | 434000 | 65100 | 499100 |  |  |  |  | 2026-08-16 | 186000 | 27900 | 213900 | [73 empty] | 6200000 | 930000 | 7130000 | 2790000 | 3208500 | 63% | 3906000 | 1116000
Meinhardt (RDH1-01-006) | RDH1-01-006 | 3 | Riyadh 1-RBF-Value Engineering | RDH1-01-009 | 1200000 | 2026-04-26 | 60000 | 9000 | 69000 | 2026-05-13 | 240000 | 36000 | 276000 | [93 empty] | 1200000 | 180000 | 1380000 | 300000 | 345000 | 85% | 1020000 | 720000
Meinhardt (RDH1-01-006) | RDH1-01-006 | 4 | Multi-Story Building | RDH1-01-000 | 1000000 | 2026-04-26 | 50000 | 7500 | 57500 | 2026-05-13 | 400000 | 60000 | 460000 | 2026-06-11 | 200000 | 30000 | 230000 | 2026-07-06 | 150000 | 22500 | 172500 | 2026-07-27 | 100000 | 15000 | 115000 |  |  |  |  | 2026-08-16 | 100000 | 15000 | 115000 | [73 empty] | 1000000 | 150000 | 1150000 | 1000000 | 1150000 | 100% | 1000000 | 0
0
0

## Sheet4
Framework name | Framework ID | Framework Total amount | Framework Status | Project Name | Project status | Project ID | Project Total amount
Dorsch food | MLTX-01-085 | 19993600 | Closed | Jeddah 2 - Food Cluster - RBF 450 & 900 m2 | Closed | JDH2-01-016 | 877779
Dorsch food | MLTX-01-085 | 19993600 | Closed | Jeddah Food Cluster - Masterplan Update & Lands Selection at Jeddah 2nd & 3rd Ind. Cities | Closed | MLTX-01-093 | 1403611
Dorsch food | MLTX-01-085 | 19993600 | Closed | Jeddah 3 - Design of Shared Dry & Cold Storage Warehouses in Jeddah 3 Ind. City | Closed | JDH3-01-021 | 2999654
Dorsch food | MLTX-01-085 | 19993600 | Closed | Master planning a logistic area in Dammam 2 | Closed | DAM2-01-026 | 4125000
Dorsch food | MLTX-01-085 | 19993600 | Closed | Hydrology Study for preventing Jeddah 4th Industrial City from floods and stormwater | Closed | JDH4-01-040 | 404258
Dorsch food | MLTX-01-085 | 19993600 | Closed | Completing the infrastructure networks and residential neighborhood in the 2nd industrial city in Dammam | Closed | DAM2-02-027 | 6968306
Dorsch food | MLTX-01-085 | 19993600 | Closed | Reviewing the masterplan for alkhrj nd. City | Closed |  | 174000
Dorsch food | MLTX-01-085 | 19993600 | Closed | Detail MPL and infra Design for the multi-use area in Dammam2 | Closed | DAM2-01-029 | 836000
Dorsch food | MLTX-01-085 | 19993600 | Closed | Design shared services center - Food cluster | Closed | JDH2-01-023 | 1505768
Dorsch food | MLTX-01-085 | 19993600 | Closed | الدراسه القيميه لمشاريع المصانع الجاهزة | Closed |  | 264505
SYSTRA | MLTX-01-102 | 15054089 | ongoing | Masterplan & Infrstructure Detailed Design For Technology Zones (Jenadryah) | Closed | JNDT-01-001 | 6726972
SYSTRA | MLTX-01-102 | 15054089 | ongoing | Masterplan & Infrstructure Detailed Design For Technology Zones (Dammam) | ongoing | DAMT-01-001 | 3300435
SYSTRA | MLTX-01-102 | 15054089 | ongoing | Masterplan & Infrstructure Detailed Design For Technology Zones (Dhahran) | ongoing | DHRT-01-001 | 3300435
SYSTRA | MLTX-01-102 | 15054089 | ongoing | Technical review and transport planning expertise support for Riyadh Industrial cities 1 & 4 | Closed | MLTX-01-111 | 1726247
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Updated concept masterplan & Infrastructure designs for Tabouk ind. City | Closed | TAB-01-009 | 4360270
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Project support services (6 months) (Masterplan) | Closed |  | 744150
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Project support services (6 months) (VRO) | Closed |  | 744150
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Testing and evaluating concrete structure | Closed |  | 153002
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Preliminary designs for the expansion of the industrial city in riyadh |  |  | 156177
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Incubators in Al-Qassim Oasis | Closed | QSM3-01-014 | 1656100
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Site development and infrastructure design works for expansion in Jeddah 1 | Closed | JDH1-01-021 | 2560090
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Detailed design of connection road (Fly Over) in Dammam 2 | ongoing | DAM2-01-033 | 2310000
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Labour camp masterplan and infrastructure development in AlKharj | Closed | KHJ-01-025 | 350000
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Potable water pipeline supply and connection to alkharj 1st ind. City | ongoing | KHJ-01-026 | 534490
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Study design RBFs 900 & 450m2 SFDA requirements |  |  | 170000
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Improving the entrances and exit points for Jeddah 1 | ongoing | JDH1-01-028 | 1590000
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Hydrology study for Jeddah 2 | ongoing |  | 110500
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Jenadriyadh Business Incubators | ongoing | JNDT-01-002 | 500000
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Project support services 3 |  |  | 1798340
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Adaptation and Design of an Administrative Building Humanization in Riyadh 2 | ongoing |  | 590000
ENGICON | RDH4-00-001 | 27837620 | Closed | Riyadh 4 Masterplan and Infrastructure concept design | Closed | RDH4-00-001 | 27837620
EGEC - WAS | WAS1-01-039 | 9799000 | ongoing | Site development and buildings design for labour community area in WAS industrial city | ongoing | WAS-01-035 | 4421850
EGEC - WAS | WAS1-01-039 | 9799000 | ongoing | Design commercial area with fuel station in Waad AlShamal | ongoing | WAS-01-034 | 650000
EGEC - WAS | WAS1-01-039 | 9799000 | ongoing | Development of labour camps in: DAM03, NJR, MKH2, JDH2, SUD, ASR1 | ongoing | MLTX-01-119 | 1150000
EGEC - WAS | WAS1-01-039 | 9799000 | ongoing | Project support services 4 | ongoing |  | 853820
ENGICON - RDH4 | RDH4-01-002 | 7025000 | Closed | Design work for entrance and facilities for Riyadh 4 | Closed | RDH4-01-002 | 7025000
Dar AlRiyadh 2 | MLTX-01-100 | 59999685.82 | ongoing |  | ongoing | MLTX-01-100
ENGICON - Package1 | MLTX-01-098 | 19856000 | ongoing | NIS Design adaptation of RBF 450 , 900 m2 | Closed |  | 7940002
ENGICON - Package1 | MLTX-01-098 | 19856000 | ongoing | Detailed design of lake park and supply connection for Sudair Industrial City | Closed | SUD1-01-033 | 1658659
ENGICON - Package1 | MLTX-01-098 | 19856000 | ongoing | Technology Zone- Asfan | ongoing | ASFT-01-001 | 1192999
ENGICON - Package1 | MLTX-01-098 | 19856000 | ongoing | Technology Zone- Khumra | ongoing | KUMT-01-001 | 1318399
ENGICON - Package1 | MLTX-01-098 | 19856000 | ongoing | Riyadh 3 Business incubators | ongoing | RDH3-01-012 | 1230000
ENGICON - Package1 | MLTX-01-098 | 19856000 | ongoing | Bonded Zone in Jeddah 3rd Industrial City-MSC | ongoing |  | 2210695
ENGICON - Package1 | MLTX-01-098 | 19856000 | ongoing | Adimn Building In Riyadh 4 | ongoing |  | 1000628
Meinhardt (KHJ- FOOD) | KHJ1-01-020 | 14990000 | ongoing | Development of Design guidelines, production strategy, and prototype packages for mid-sized RBFs | ongoing |  | 2997130
Meinhardt (KHJ- FOOD) | KHJ1-01-020 | 14990001 | ongoing | Development of full Design for Multi - Story Building for foure Sities | ongoing |  | 5188500
Meinhardt (KHJ- FOOD) | KHJ1-01-020 | 14990002 | ongoing | Development of full Design Of Mid RBFs for Food , Machinery & Equipment and Pharmceutical Cluster | ongoing |  | 3500000
ENGICON - RDH4 PH2 | RDH4-01-003 | 59500000 | ongoing | 70 RBF's in Riyadh 04 | ongoing |  | 2490457
ENGICON - RDH4 PH2 | RDH4-01-003 | 59500000 | ongoing | Development for the Masterplan and Concept Infrastructure for the expansion of Riyadh 4 industrial city | ongoing | RDH4-01-005 | 24501677
ENGICON - RDH4 PH2 | RDH4-01-003 | 59500000 | ongoing | Design Bridge 3rd HIGHWAY RiyaDH 4 | ongoing |  | 1124289
ENGICON - RDH4 PH2 | RDH4-01-003 | 59500000 | ongoing | Oasis Lab Riyadh 4 | ongoing |  | 2504618
ENGICON - RDH4 PH2 | RDH4-01-003 | 59500000 | ongoing | Riyadh4 Industrial City expansion 1&2 | ongoing |  | 8850569
AlDar International (KHJ - FOOD2) | KHJ-01-027 | 11637180 | ongoing | AlKharj Food cluster | ongoing | KHJ1-01-030 | 7146100
ENGICON - Logistics | MLTX-01-117 | 27800000 | ongoing | Logistic Zones (JDH3,DAM3,MAD,MKH2) | ongoing | MLTX-01-123 | 19206662
ENGICON - Logistics | MLTX-01-117 | 27800000 | ongoing | SIDF-RBF SITE ADAPTATION 450 &900M2 IN 5 CITIES | ongoing |  | 4700512
TYPSA- (KHJ-AMIC) | KHJ2-01-001 | 57332139 | ongoing | Design and Engineering Support Works for the Master Plan and Infrastructure Project for the Military Industries City in Al Kharj | ongoing | KHJ2-01-002 | 42715823.6
TYPSA- (KHJ-AMIC) | KHJ2-01-001 | 57332139 | ongoing | Strategic Advisory and Military Industrial Planning Support Services |  | KHJ2-01-007 | 2142000
TYPSA- (KHJ-AMIC) | KHJ2-01-001 | 57332139 | ongoing | Comprehensive Facility Survey & Update of As-Builts, Al Kharj MIC |  | KHJ2-01-006 | 6684584.92
EGEC - NIS2 | MLTX-01-099 | 19979840 | ongoing | Ddevelopment The walkway In residential area Jeddah1 | ongoing |  | 170000
Meinhardt (RDH1-01-006) | RDH1-01-006 | 25298852 | ongoing | Riyadh 1 Industrial City Masterplan | ongoing | RDH1-01-007 | 16898852
Meinhardt (RDH1-01-006) | RDH1-01-006 | 25298852 | ongoing | Riyadh 1-Codes and Guidelines | ongoing | RDH1-01-008 | 6200000
Meinhardt (RDH1-01-006) | RDH1-01-006 | 25298852 | ongoing | Riyadh 1-RBF-Value Engineering | ongoing | RDH1-01-009 | 1200000
Meinhardt (RDH1-01-006) | RDH1-01-006 | 25298852 | ongoing | Multi-Story Building | ongoing | RDH1-01-000 | 1000000

## EGEC - NIS2
|  |  |  | Tabouk |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 5 |  | Invoice 6
Description |  | Total quantity | Remaining quantity | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity3 | Amount4 | Quantity25 | Amount36
Lead Engineer/ Discipline Engineer | A1 | 670 |  | Lead Engineer/ Discipline Engineer | A1 |  | 0 | 465 |  | 0 |  | 0 |  | 0 |  | 0
Sr. Engineer/ Senior discipline specialist | B1 | 1050 |  | Sr. Engineer/ Senior discipline specialist | B1 |  | 0 | 390 |  | 0 |  | 0 |  | 0 |  | 0
Engineer/ Discipline Specialist | C1 | 1810 |  | Engineer/ Discipline Specialist | C1 |  | 0 | 200 |  | 0 |  | 0 |  | 0 |  | 0
Draftsman | D1 | 2380 |  | Draftsman | D1 |  | 0 | 90 |  | 0 |  | 0 |  | 0 |  | 0
Lead engineer/ discipline expert | A2 | 9040 | -1690.27 | Lead engineer/ discipline expert | A2 | 1800 | 561.5182 | 275 | 253.5 | 69712.5 | 984.9818 | 270869.99 | 471.5182 | 129667.51 | 90 | 24750
Sr. Engineer/ Senior discipline specialist | B2 | 19600 | 10753.11 | Sr. Engineer/ Senior discipline specialist | B2 | 3200 | 952.45 | 180 | 775.55 | 139599 | 1472 | 264960 | 792.45 | 142641 | 160 | 28800
Engineer/ Discipline Specialist | C2 | 33970 | -3702.03 | Engineer/ Discipline Specialist | C2 | 15200 | 4511 | 145 | 3849 | 558105 | 6840 | 991800 | 3751 | 543895 | 760 | 110200
Draftsman | D2 | 36820 | -10720.06 | Draftsman | D2 | 13235 | 1342.8 | 82 | 7657 | 627874 | 4235.2 | 347286.4 | 681.05 | 55846.1 | 661.75 | 54263.5
E2/ Project Manager | E2 | 7140 | 7140 | E2/ Project Manager | E2 |  | 0 | 275 |  | 0 |  | 0 |  | 0 |  | 0
F2/ Project Manager | F2 | 7140 | 7140 | F2/ Project Manager | F2 |  | 0 | 180 |  | 0 |  | 0 |  | 0 |  | 0
[8 empty] | Total | 12535.05 | 1395290.5 | 13532.1818 | 1874916.39 | 5696.0182 | 872049.61 | 1671.75 | 218013.5
VO
|  |  |  | Project support services |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 4 |  |  |  | Invoice 7 |  | Invoice 11
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity22 | Amount33 | Column1 | Column2 | Quantity2222 | Amount3333 | Quantity22222 | Amount33333
|  |  | 0.033204 | Lead Engineer/ Discipline Engineer | A1 |  | 0 | 465 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  | 0 | 390 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  | 1488300 | 8268.3333 | Engineer/ Discipline Specialist | C1 |  | 0 | 200 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | Draftsman | D1 |  | 0 | 90 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | Lead engineer/ discipline expert | A2 | 5412 | 0 | 275 |  |  | 1353 | 372075 | 1353 | 372075 |  |  | 1353 | 372075 | 1353 | 372075
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 |  | 0 | 180
|  |  |  | Engineer/ Discipline Specialist | C2 |  | 0 | 145
|  |  |  | Draftsman | D2 |  |  | 82
|  |  |  | E2/ Project Manager | E2 |  |  | 275 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | F2/ Project Manager | F2 |  |  | 180 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
[8 empty] | Total | 0 | 0 | 1353 | 372075 | 1353 | 372075 |  |  | 1353 | 372075 | 1353 | 372075
|  |  |  | Testing and evaluating concrete structure |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity22 | Amount33
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  |  | 465 |  | 0 |  | 0
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  |  | 390 |  | 0 |  | 0 |  |  |  | 744150
|  |  |  | Engineer/ Discipline Specialist | C1 |  |  | 200 |  | 0 |  | 0 |  |  |  | 744150
|  |  |  | Draftsman | D1 |  |  | 90 |  | 0 |  | 0
|  |  |  | Lead engineer/ discipline expert | A2 | 28 | 8.4 | 275 |  |  | 19.6 | 5390 | 8.4 | 2310
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 84 | 25.2 | 180 |  |  | 58.8 | 10584 | 25.2 | 4536
|  |  |  | Engineer/ Discipline Specialist | C2 | 423 | 126.9 | 145 |  |  | 296.1 | 42934.5 | 126.9 | 18400.5
|  |  |  | Draftsman | D2 | 839.6 | 251.88 | 82 |  |  | 587.72 | 48193.04 | 251.88 | 20654.16
|  |  |  | E2/ Project Manager | E2 |  |  | 275 |  | 0 |  | 0
|  |  |  | F2/ Project Manager | F2 |  |  | 180 |  | 0 |  | 0
[8 empty] | Total | 0 | 0 | 962.22 | 107101.54 | 412.38 | 45900.66
|  |  |  | Preliminary designs for the expansion of the industrial city in riyadh |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity22 | Amount33
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  |  | 465 |  | 0 |  | 0
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  |  | 390 |  | 0 |  | 0
|  |  |  | Engineer/ Discipline Specialist | C1 |  |  | 200 |  | 0 |  | 0
|  |  |  | Draftsman | D1 |  |  | 90 |  | 0
|  |  |  | Lead engineer/ discipline expert | A2 | 29 | 29 | 275 |  |  |  |  | 20.3 | 5582.5
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 87 | 87 | 180 |  |  |  |  | 60.9 | 10962
|  |  |  | Engineer/ Discipline Specialist | C2 | 430 | 430 | 145 |  |  |  |  | 301 | 43645
|  |  |  | Draftsman | D2 | 856 | 856 | 82 |  |  |  |  | 599.2 | 49134.4
|  |  |  | E2/ Project Manager | E2 |  |  | 275 |  | 0 |  | 0
|  |  |  | F2/ Project Manager | F2 |  |  | 180 |  | 0 |  | 0
[8 empty] | Total | 0 | 0 | 0 | 0 | 981.4 | 109323.9
|  |  |  | Incubators in AlQassim oasis |  |  |  |  | Invoice 6 |  | Invoice 7 |  | Invoice 8
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity22 | Amount33
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  | 0 | 465 |  | 0 |  | 0
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  | 0 | 390 |  | 0 |  | 0
|  |  |  | Engineer/ Discipline Specialist | C1 |  | 0 | 200 |  | 0 |  | 0
|  |  |  | Draftsman | D1 |  | 0 | 90 |  | 0 |  | 0
|  |  |  | Lead engineer/ discipline expert | A2 | 700 | 105 | 275 | 350 | 96250 | 245 | 67375
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 1300 | 195 | 180 | 650 | 117000 | 455 | 81900
|  |  |  | Engineer/ Discipline Specialist | C2 | 5200 | 780 | 145 | 2600 | 377000 | 1820 | 263900
|  |  |  | Draftsman | D2 | 5800 | 870 | 82 | 2900 | 237800 | 2030 | 166460
|  |  |  | E2/ Project Manager | E2 |  |  | 275 |  | 0 |  | 0
|  |  |  | F2/ Project Manager | F2 |  |  | 180 |  | 0 |  | 0
[8 empty] | Total |  | 828050 |  | 579635
|  |  |  | Jeddah 1 Expansion |  |  |  |  | Invoice 6 |  | Invoice 7 |  | Invoice 8 |  | Invoice 9 |  | Invoice 10 |  | Invoice 11 |  | Invoice 12
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity22 | Amount33 | Quantity222 | Amount333 | Quantity222 | Amount333 | Quantity222 | Amount333 | Quantity222 | Amount333
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  | 0 | 465 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  | 0 | 390 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | Engineer/ Discipline Specialist | C1 |  | 0 | 200 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0
|  |  |  | Draftsman | D1 |  | 0 | 90 |  | 0 |  | 0 |  |  |  | 0
|  |  |  | Lead engineer/ discipline expert | A2 | 1800 | 1260 | 275 |  |  | 270 | 74250 |  |  | 270 | 74250 | 450 | 123750 | 630.0004 | 173250.1 | 179.9996 | 49499.9 | 173250.1 | 630.0004
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 1900 | 1330 | 180 |  |  | 285 | 51300 |  |  | 285 | 51300 | 475 | 85500 | 665.0004 | 119700.07 | 189.9996 | 34199.93 | 119700.07 | 665.0004
|  |  |  | Engineer/ Discipline Specialist | C2 | 7150 | 5005 | 145 |  |  | 1072.5 | 155512.5 |  |  | 1072.5 | 155512.5 | 1787.5 | 259187.5 | 2502.5014 | 362862.7 | 714.9986 | 103674.8 | 362862.7 | 2502.5014
|  |  |  | Draftsman | D2 | 8370 | 5859 | 82 |  |  | 1255.5 | 102951 |  |  | 1255.5 | 102951 | 2092.5 | 171585 | 2929.5016 | 240219.13 | 836.9984 | 68633.87 | 240219.13 | 2929.5016
|  |  |  | E2/ Project Manager | E2 |  |  | 275 |  |  |  | 0 |  |  |  | 0
|  |  |  | F2/ Project Manager | F2 |  |  | 180 |  |  |  | 0 |  |  |  | 0
[8 empty] | Total |  |  |  | 384013.5 |  |  |  | 384013.5 | 4805 | 640022.5 | 6727.0037 | 896032 | 1921.9963 | 256008.5
|  |  |  | Labour camp in AlKharj |  |  |  |  | Invoice 6 |  | Invoice 7 |  | Invoice 8 |  | Invoice 9
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity22 | Amount33 | Quantity222 | Amount333 | Column1 | Column2
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  | 0 | 465 |  | 0 |  | 0 |  |  |  | 0
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  | 0 | 390 |  | 0 |  | 0 |  |  |  | 0
|  |  |  | Engineer/ Discipline Specialist | C1 |  | 0 | 200 |  | 0 |  | 0 |  |  |  | 0
|  |  |  | Draftsman | D1 |  | 0 | 90 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | Lead engineer/ discipline expert | A2 | 64 | 0.36364 | 275 |  |  |  |  | 31.8182 | 8750 | 31.8182 | 8750
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 194 | -0.44444 | 180 |  |  |  |  | 97.2222 | 17500 | 97.2222 | 17500
|  |  |  | Engineer/ Discipline Specialist | C2 | 966 | 0.48276 | 145 |  |  |  |  | 482.7586 | 70000 | 482.7586 | 70000
|  |  |  | Draftsman | D2 | 1921 | 0.26829 | 82 |  |  |  |  | 960.3659 | 78750 | 960.3659 | 78750
|  |  |  | E2/ Project Manager | E2 |  |  | 275 | [5 empty] | 0 |  | 0
|  |  |  | F2/ Project Manager | F2 |  |  | 180 | [5 empty] | 0 |  | 0 |  |  |  | 210000
[8 empty] | Total | [5 empty] | 175000 |  | 175000 |  |  |  | 693000
85000
384013.5
175000
|  |  |  | Potable water pipeline supply and connection to kharj 1 |  |  |  |  | Invoice 6 |  | Invoice 7 |  | Invoice 8 |  | Invoice 9 |  | Invoice13 |  | Invoice16
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Column1 | Column2 | Quantity222 | Amount333 | Column3 | Column4 | Column5 | Column6
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  | 0 | 465 |  | 0 |  | 0 | [5 empty] | 0 |  | 0
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  | 0 | 390 |  | 0 |  | 0 | [5 empty] | 0 |  | 0
|  |  |  | Engineer/ Discipline Specialist | C1 |  | 0 | 200 |  | 0 |  | 0 | [5 empty] | 0 |  | 0
|  |  |  | Draftsman | D1 |  | 0 | 90 |  | 0 | [5 empty] | 0 |  | 0 |  | 0
|  |  |  | Lead engineer/ discipline expert | A2 | 127.27 | 89.0882 | 275 | [6 empty] | 38.1818 | 10500 | 31.82 | 8750.5 | 25.25 | 6943.75
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 388.89 | 272.2233 | 180 | [6 empty] | 116.6667 | 21000 | 97.22 | 17499.6 | 77.78 | 14000.4
|  |  |  | Engineer/ Discipline Specialist | C2 | 1931.03 | 1351.7197 | 145 | [6 empty] | 579.3103 | 84000 | 482.76 | 70000.2 | 386.21 | 56000.45
|  |  |  | Draftsman | D2 | 3841.46 | 2689.021 | 82 | [6 empty] | 1152.439 | 94500 | 960.37 | 78750.34 | 768.29 | 62999.78
|  |  |  | E2/ Project Manager | E2 |  |  | 275 | [7 empty] | 0 |  |  |  | 0
|  |  |  | F2/ Project Manager | F2 |  |  | 180 | [7 empty] | 0 |  |  |  | 0
[8 empty] | Total | [7 empty] | 210000 |  | 175000.64 |  | 140000
|  |  |  | Flyover |  |  |  |  | Invoice 6 |  | Invoice 7 |  | Invoice 8 |  | Invoice 9 |  | Invoice 19 |  | Invoice 20
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Column1 | Column2 | Quantity222 | Amount333 | Column3 | Column4 | Column5
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  | 0 | 465 |  | 0 |  | 0 | [5 empty] | 0
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  | 0 | 390 |  | 0 |  | 0 | [5 empty] | 0
|  |  |  | Engineer/ Discipline Specialist | C1 |  | 0 | 200 |  | 0 |  | 0 | [5 empty] | 0
|  |  |  | Draftsman | D1 |  | 0 | 90 |  | 0 | [5 empty] | 0 |  | 0
|  |  |  | Lead engineer/ discipline expert | A2 | 420 | 294 | 275 | [6 empty] | 126 | 34650 | 105 | 28875
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 1283 | 898 | 180 | [6 empty] | 385 | 69300 | 320.83 | 57749.4
|  |  |  | Engineer/ Discipline Specialist | C2 | 6372 | 4460.2759 | 145 | [6 empty] | 1911.7241 | 277200 | 1593.1 | 230999.5
|  |  |  | Draftsman | D2 | 12677 | 8873.9512 | 82 | [6 empty] | 3803.0488 | 311850 | 3169.21 | 259875.22
|  |  |  | E2/ Project Manager | E2 |  |  | 275 | [7 empty] | 0
|  |  |  | F2/ Project Manager | F2 |  |  | 180 | [7 empty] | 0
[8 empty] | Total | [7 empty] | 693000 |  | #VALUE!
577499.12
|  |  |  | RBF's |  |  |  |  | Invoice 6 |  | Invoice 7 |  | Invoice 8 |  | Invoice 9 |  | Invoice 10 |  | Invoice 14
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Column1 | Column2 | Quantity222 | Amount333 | Column3 | Column4 | Quantity223 | Amount334
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  | 0 | 465 |  | 0 |  | 0 | [7 empty] | 0
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  | 0 | 390 |  | 0 |  | 0 | [7 empty] | 0
|  |  |  | Engineer/ Discipline Specialist | C1 |  | 0 | 200 |  | 0 |  | 0 | [7 empty] | 0
|  |  |  | Draftsman | D1 |  | 0 | 90 |  | 0 | [5 empty] | 0 |  |  |  | 0
|  |  |  | Lead engineer/ discipline expert | A2 | 350 | 175 | 275 | [6 empty] | 175 | 48125 |  |  | 175 | 48125
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 410 | 205.1389 | 180 | [6 empty] | 204.8611 | 36875 | 36875 |  | 204.8611 | 36875
|  |  |  | Engineer/ Discipline Specialist | C2 |  |  | 145 | [11 empty] | 0
|  |  |  | Draftsman | D2 |  |  | 82 | [11 empty] | 0
|  |  |  | E2/ Project Manager | E2 |  |  | 275 | [7 empty] | 0 |  |  |  | 0
|  |  |  | F2/ Project Manager | F2 |  |  | 180 | [7 empty] | 0 |  |  |  | 0
[8 empty] | Total | [7 empty] | 85000 |  |  |  | 85000
|  |  |  | Project support services 3 |  |  |  |  | Invoice12 |  | Invoice13
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Column1 | Column2 | Quantity222 | Amount333
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  |  | 465
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  |  | 390
|  |  |  | Engineer/ Discipline Specialist | C1 |  |  | 200
|  |  |  | Draftsman | D1 |  |  | 90
|  |  |  | Lead engineer/ discipline expert | A2 |  |  | 275
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 2400 |  | 180 | 600 | 108000 | 600 | 108000
|  |  |  | Engineer/ Discipline Specialist | C2 | 1892 |  | 145 | 473 | 68585 | 473 | 68585
|  |  |  | Draftsman | D2 |  |  | 82 |  | 0 |  | 0
|  |  |  | E2/ Project Manager | E2 | 2400 |  | 275 | 600 | 165000 | 600 | 165000
|  |  |  | F2/ Project Manager | F2 | 2400 |  | 180 | 600 | 108000 | 600 | 108000
[8 empty] | Total |  | 449585 |  | 449585 |  |  |  | 0
|  |  |  | Adaptation and Design of an Administrative Building Humanization in Riyadh 2 |  |  |  |  | Invoice 14 |  | Invoice16
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount | Quantity | Amount
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  |  | 465
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  |  | 390
|  |  |  | Engineer/ Discipline Specialist | C1 |  |  | 200
|  |  |  | Draftsman | D1 |  |  | 90
|  |  |  | Lead engineer/ discipline expert | A2 |  |  | 275
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 492 |  | 180 | 393.33 | 70799.4 | 49.92 | 8985.6
|  |  |  | Engineer/ Discipline Specialist | C2 | 1628 |  | 145 | 1302.07 | 188800.15 | 162.76 | 23600.2
|  |  |  | Draftsman | D2 | 3238 |  | 82 | 2590.24 | 212399.68 | 323.78 | 26549.96
|  |  |  | E2/ Project Manager | E2 |  |  | 275
|  |  |  | F2/ Project Manager | F2 |  |  | 180
[8 empty] | Total |  | 471999.23 |  | 59000
|  |  |  | Hydrology study for Jeddah 2 |  |  |  |  | Invoice 15
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  |  | 465
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  |  | 390
|  |  |  | Engineer/ Discipline Specialist | C1 |  |  | 200
|  |  |  | Draftsman | D1 |  |  | 90
|  |  |  | Lead engineer/ discipline expert | A2 |  |  | 275
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 92 |  | 180 | 36.83 | 6629.4
|  |  |  | Engineer/ Discipline Specialist | C2 | 305 |  | 145 | 121.93 | 17679.85
|  |  |  | Draftsman | D2 | 606 |  | 82 | 242.56 | 19889.92
|  |  |  | E2/ Project Manager | E2 |  |  | 275
|  |  |  | F2/ Project Manager | F2 |  |  | 180
[8 empty] | Total |  | 44199.17
|  |  |  | Improving the entrances and exit points for Jeddah 1 |  |  |  |  | Invoice 15 |  | Invoice17 |  | Invoice
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount | Quantity | Amount
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  |  | 465
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  |  | 390
|  |  |  | Engineer/ Discipline Specialist | C1 |  |  | 200
|  |  |  | Draftsman | D1 |  |  | 90
|  |  |  | Lead engineer/ discipline expert | A2 |  |  | 275
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 1325 |  | 180 | 662.5 | 119250 | 463.75 | 83475
|  |  |  | Engineer/ Discipline Specialist | C2 | 4386 |  | 145 | 2193.1 | 317999.5 | 1535.17 | 222599.65
|  |  |  | Draftsman | D2 | 8726 |  | 82 | 4362.8 | 357749.6 | 3053.96 | 250424.72
|  |  |  | E2/ Project Manager | E2 |  |  | 275
|  |  |  | F2/ Project Manager | F2 |  |  | 180
[8 empty] | Total |  | 794999.1 |  | 556499.37
|  |  |  | Incubators Riyadh Janariyah |  |  |  |  | Invoice 16 |  | Invoice 17 |  | Invoice 18 |  | Invoice 19
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  |  | 465
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  |  | 390
|  |  |  | Engineer/ Discipline Specialist | C1 |  |  | 200
|  |  |  | Draftsman | D1 |  |  | 90
|  |  |  | Lead engineer/ discipline expert | A2 |  |  | 275
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 417 |  | 180 | 83.33 | 14999.4 | 187.5 | 33750 | 83.33 | 14999.4 | 62.5 | 11250
|  |  |  | Engineer/ Discipline Specialist | C2 | 1379 |  | 145 | 275.86 | 39999.7 | 620.69 | 90000.05 | 275.86 | 39999.7 | 206.9 | 30000.5
|  |  |  | Draftsman | D2 | 2744 |  | 82 | 548.78 | 44999.96 | 1234.76 | 101250.32 | 548.78 | 44999.96 | 411.59 | 33750.38
|  |  |  | E2/ Project Manager | E2 |  |  | 275 | [7 empty] | 0
|  |  |  | F2/ Project Manager | F2 |  |  | 180 | [7 empty] | 0
[8 empty] | Total |  | 100000 |  | 225000.37 |  | 99999.06 |  | 75000.88
|  |  |  | Project support services |  |  |  |  | Invoice 7 |  | Invoice 11
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  |  | 465
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  |  | 390
|  |  |  | Engineer/ Discipline Specialist | C1 |  |  | 200
|  |  |  | Draftsman | D1 |  |  | 90
|  |  |  | Lead engineer/ discipline expert | A2 | 2706 |  | 275 | 1353 | 372075 | 1353 | 372075
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 |  |  | 180
|  |  |  | Engineer/ Discipline Specialist | C2 |  |  | 145
|  |  |  | Draftsman | D2 |  |  | 82
|  |  |  | E2/ Project Manager | E2 |  |  | 275
|  |  |  | F2/ Project Manager | F2 |  |  | 180
Total
|  |  |  | The walkway In residential area Jeddah1 | [6 empty] | Invoice20
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount
|  |  |  | Lead Engineer/ Discipline Engineer | A1 |  |  | 465
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 |  |  | 390
|  |  |  | Engineer/ Discipline Specialist | C1 |  |  | 200
|  |  |  | Draftsman | D1 |  |  | 90
|  |  |  | Lead engineer/ discipline expert | A2 |  |  | 275
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | 142 |  | 180 | 99.17 | 17850.6 | 42.5 | 7650
|  |  |  | Engineer/ Discipline Specialist | C2 | 496 |  | 145 | 328.28 | 47600.6 | 140.69 | 20400.05
|  |  |  | Draftsman | D2 | 933 |  | 82 | 653.05 | 53550.1 | 279.88 | 22950.16
|  |  |  | E2/ Project Manager | E2 |  |  | 275
|  |  |  | F2/ Project Manager | F2 |  |  | 180
[8 empty] | Total |  | 119001.3 |  | 51000.21

## Meinhardt (RDH1-01-006)
Description | Category | Quanty | Rate | total
Lead Engineer/ Discipline Engineer | A1 | 13900.9401 | 504.35 | 7010939.1272
Sr. Engineer/ Senior discipline specialist | B1 | 13100.1456 | 391.3 | 5126086.958
Engineer/ Discipline Specialist | C1 | 16309.8023 | 286.96 | 4680260.8682 | Riyadh 1 Industrial City Masterplan
Draftsman | D1 | 17999.315 | 173.91 | 3130260.8688 | Description | Category | Rate | Quanty | Total
Project Manager | E1 | 5000.0368 | 591.3 | 2956521.7388 | Lead Engineer/ Discipline Engineer | A1 | 504.35 | 9285.399 | 4683091
Project Manager | F1 | 7650.085 | 313.04 | 2394782.6091 | Sr. Engineer/ Senior discipline specialist | B1 | 391.3 | 8750.4932 | 3424068
|  |  |  | 25298852.17 | Engineer/ Discipline Specialist | C1 | 286.96 | 10894.4452 | 3126270
[5 empty] | Draftsman | D1 | 173.91 | 12022.9889 | 2090918
[5 empty] | Project Manager | E1 | 591.3 | 3339.8698 | 1974865
[5 empty] | Project Manager | F1 | 313.04 | 5110.0211 | 1599641
[5 empty] | TOTAL |  |  |  | 16898853
Riyadh 1-Codes and Guidelines
[5 empty] | Description | Category | Rate | Quanty | Total
[5 empty] | Lead Engineer/ Discipline Engineer | A1 | 504.35 | 3406.7096 | 1718174
[5 empty] | Sr. Engineer/ Senior discipline specialist | B1 | 391.3 | 3210.4574 | 1256252
[5 empty] | Engineer/ Discipline Specialist | C1 | 286.96 | 3997.0484 | 1146993
[5 empty] | Draftsman | D1 | 173.91 | 4411.0977 | 767134
[5 empty] | Project Manager | E1 | 591.3 | 1225.3611 | 724556
[5 empty] | Project Manager | F1 | 313.04 | 1874.8083 | 586890
[5 empty] | TOTAL |  |  |  | 6199999
Riyadh 1-RBF-Value Engineering
[5 empty] | Description | Category | Rate | Quanty | Total
[5 empty] | Lead Engineer/ Discipline Engineer | A1 | 504.35 | 659.3635 | 332550
[5 empty] | Sr. Engineer/ Senior discipline specialist | B1 | 391.3 | 621.38 | 243146
[5 empty] | Engineer/ Discipline Specialist | C1 | 286.96 | 773.6235 | 221999
[5 empty] | Draftsman | D1 | 173.91 | 853.7634 | 148478
[5 empty] | Project Manager | E1 | 591.3 | 237.1673 | 140237
[5 empty] | Project Manager | F1 | 313.04 | 362.8674 | 113592
[5 empty] | TOTAL |  |  |  | 1200002
Multi-Story Building
[5 empty] | Description | Category | Rate | Quanty | Total
[5 empty] | Lead Engineer/ Discipline Engineer | A1 | 504.35 | 549.4696 | 277125
[5 empty] | Sr. Engineer/ Senior discipline specialist | B1 | 391.3 | 517.815 | 202621
[5 empty] | Engineer/ Discipline Specialist | C1 | 286.96 | 644.6857 | 184999
[5 empty] | Draftsman | D1 | 173.91 | 711.4657 | 123731
[5 empty] | Project Manager | E1 | 591.3 | 197.6391 | 116864
[5 empty] | Project Manager | F1 | 313.04 | 302.3895 | 94660
[5 empty] | TOTAL |  |  |  | 1000000

## Logistic
|  |  |  | Logistics |  |  | Logistic Zones (JDH3,DAM3,MAD,MKH2) |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4 |  | Invoice 5 |  | Invoice 6 |  | Invoice 7
Description |  | Total quantity | Remaining quantity | Description | Category | Total Quantity | Remaining quantity | Rate | Amount | Quantity2 | Amount3 | Amount36 | Quantity25 | Amount363 | Quantity26 | Amount364 | Quantity27 | Amount365 | Quantity28 | Amount366 | Quantity29 | Amount367
Lead Engineer/ Discipline Engineer | A1 | 6000 |  | Lead Engineer/ Discipline Engineer | A1 |  | #REF! | 478 | 110 | 52580 | 110 | 52580 | 97.5 | 46605 | 747.88 | 357486.64 | 650.38 | 310881.64 | 554.63 | 265113.14 | 587.63 | 280887.14
Sr. Engineer/ Senior discipline specialist | B1 | 378 |  | Sr. Engineer/ Senior discipline specialist | B1 |  | #REF! | 378 | 600 | 226800 | 600 | 226800 | 172.5 | 65205 | 1690 | 638820 | 1517.5 | 573615 | 3060 | 1156680 | 3240 | 1224720
Engineer/ Discipline Specialist | C1 | 302 |  | Engineer/ Discipline Specialist | C1 |  | #REF! | 302 | 850 | 256700 | 850 | 256700 | 210 | 63420 | 2165 | 653830 | 1955 | 590410 | 4335 | 1309170 | 4591.5 | 1386633
Draftsman | D1 | 220 |  | Draftsman | D1 |  | #REF! | 220 | 700 | 154000 | 700 | 154000 | 210 | 46200 | 2030 | 446600 | 1820 | 400400 | 3570 | 785400 | 3795 | 834900
Project Manager | E1 | 478 | 478 | Project Manager | E1 | 0 | #REF! | 478 | 500 | 239000 | 500 | 239000 | 112.5 | 53775 | 1200 | 573600 | 1087.5 | 519825 | 2550 | 1218900 | 2700 | 1290600
Project Manager | F1 | 172 | 172 | Project Manager | F1 | 0 | #REF! | 172 | 181.7965 | 31269 | 181.7965 | 31269 | 74.86 | 12875.92 | 665.81 | 114519.32 | 590.95 | 101643.4 | 944.88 | 162519.36 | 977.6 | 168147.2
|  |  |  | TOTAL |  |  | #REF! |  |  | 960349 |  | 960349 |  | 288080.85 |  | 2784853.1 |  | 2496775.04 |  | 4897782.5 |  | 5185887.34
2208778.85

## ENGICON RIYADH 4 P2
| Total quantity | Remaining quantity
A1 | 30000
B1 | 45000
C1 | 40000
D1 | 440000
E1 | 16000
F1 | 14000
|  |  | 70 RBF's in Riyadh 04 |  |  |  |  | Invoice1 |  | Invoice2 |  | Invoice3 |  | Invoice5
|  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
|  |  | Lead Engineer/ Discipline Engineer | A1 | 2000 |  | 463 | 600 | 277800 | 500 | 231500 | 500 | 231500 | 400 | 185200
|  |  | Sr. Engineer/ Senior discipline specialist | B1 | 2000 |  | 349 | 600 | 209400 | 500 | 174500 | 500 | 174500 | 400 | 139600
|  |  | Engineer/ Discipline Specialist | C1 | 2000 |  | 302 | 600 | 181200 | 500 | 151000 | 500 | 151000 | 400 | 120800
|  |  | Draftsman | D1 | 1553 |  | 169 | 466 | 78754 | 388 | 65572 | 388 | 65572 | 311 | 52559
|  |  | Project Manager | E1 | 0 |  |  |  | 0
|  |  | Project Manager | F1 | 0
|  |  | TOTAL | [5 empty] | 747154 |  | 622572 |  | 622572 |  | 498159
|  |  | Development for the Masterplan and Concept Infrastructure for the expansion of Riyadh 4 industrial city |  |  |  |  | Invoice1 |  | Invoice3 |  | Invoice4 |  | Invoice6
|  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
|  |  | Lead Engineer/ Discipline Engineer | A1 | 8000 |  | 463 | 2600 | 1203800 | 1000 | 463000 | 800 | 370400 | 1800 | 833400
|  |  | Sr. Engineer/ Senior discipline specialist | B1 | 20000 |  | 349 | 6500 | 2268500 | 2500 | 872500 | 2000 | 698000 | 4500 | 1570500
|  |  | Engineer/ Discipline Specialist | C1 | 17557 |  | 302 | 5707 | 1723514 | 2195 | 662890 | 1756 | 530312 | 3949.5 | 1192749
|  |  | Draftsman | D1 | 20000 |  | 169 | 6500 | 1098500 | 2500 | 422500 | 2000 | 338000 | 4500 | 760500
|  |  | Project Manager | E1 | 8000 |  | 463 | 2600 | 1203800 | 1000 | 463000 | 800 | 370400 | 1800 | 833400
|  |  | Project Manager | F1 | 7997 |  | 179 | 2599 | 465221 | 999.5 | 178910.5 | 799.5 | 143110.5 | 1799.5 | 322110.5
|  |  | TOTAL | [5 empty] | 7963335 |  | 3062800.5 |  | 2450222.5 |  | 5512659.5
|  |  | Design Bridge 3rd HIGHWAY RiyaDH 4 |  |  |  |  | Invoice5
|  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount
|  |  | Lead Engineer/ Discipline Engineer | A1 | 923 |  | 463 | 126.5 | 58569.5
|  |  | Sr. Engineer/ Senior discipline specialist | B1 | 832 |  | 349 | 135.5 | 47289.5
|  |  | Engineer/ Discipline Specialist | C1 | 530 |  | 302 | 75 | 22650
|  |  | Draftsman | D1 | 375 |  | 169 | 50 | 8450
|  |  | Project Manager | E1 | 290 |  | 463 | 50 | 23150
|  |  | Project Manager | F1 | 273 |  | 179 | 48 | 8592
168701

## Engicon - P1
|  |  |  | Sudair lake |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4
Description |  | Total quantity | Remaining quantity | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity3 | Amount4 | Quantity25 | Amount36
Lead Engineer/ Discipline Engineer | A1 |  |  | Lead Engineer/ Discipline Engineer | A1 | 810 | 0 | 405 | 364.5 | 147622.5 | 445.5 | 180427.5
Sr. Engineer/ Senior discipline specialist | B1 |  |  | Sr. Engineer/ Senior discipline specialist | B1 | 1905 | 0 | 302 | 857.25 | 258889.5 | 1047.75 | 316420.5
Engineer/ Discipline Specialist | C1 |  |  | Engineer/ Discipline Specialist | C1 | 2233 | 0 | 259 | 1004.85 | 260256.15 | 1228.15 | 318090.85
Draftsman | D1 |  |  | Draftsman | D1 | 1212 | 0 | 146 | 545.4 | 79628.4 | 666.6 | 97323.6
Project Manager | E1 |  | #REF! | Project Manager | E1 | 0 | 0 | 405 |  | 0
Project Manager | F1 |  | #VALUE! | Project Manager | F1 | 0 | 0 | 162 |  | 0
|  |  |  | TOTAL |  |  | 0 |  |  | 746396.55 |  | 912262.45
|  |  |  | NIS RBF |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 6 |  | Invoice 8
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity3 | Amount4 | Quantity25 | Amount36 | Quantity26 | Amount38
|  |  |  | Lead Engineer/ Discipline Engineer | A1 | 5359 | 0.00069136 | 405 | 2067.0429 | 837152.36 | 1224.9143 | 496090.29 |  |  | 1550.2821 | 627864.27 | 516.76 | 209287.8
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 | 8558 | -0.0042715 | 302 | 3300.9428 | 996884.74 | 1956.1143 | 590746.51 |  |  | 2475.7072 | 747663.56 | 825.24 | 249222.48
|  |  |  | Engineer/ Discipline Specialist | C1 | 8695 | -0.0035907 | 259 | 3353.7857 | 868630.5 | 1987.4286 | 514744 |  |  | 2515.3393 | 651472.88 | 838.45 | 217158.55
|  |  |  | Draftsman | D1 | 6391 | -0.005 | 146 | 2465.1 | 359904.6 | 1460.8 | 213276.8 |  |  | 1848.825 | 269928.45 | 616.28 | 89976.88
|  |  |  | Project Manager | E1 | 0 | 0 | 405 |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | Project Manager | F1 | 0 | 0 | 162 |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | TOTAL |  |  | 0 |  |  | 3062572.2 |  | 1814857.6 |  |  |  | 2296929.16 |  | 765643.05
4877429.8
|  |  |  | Technology zones - Asfan |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4 |  |  |  | Invoice 5 |  | Invoice 7
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity3 | Amount4 | Quantity25 | Amount36 | Amount37 | Amount38 | Amount39 | Amount40 | Amount41 | Amount42
|  |  |  | Lead Engineer/ Discipline Engineer | A1 | 1008 |  | 405 |  |  |  | 0 | 110 | 44550 | 388 | 157140 | 200 | 81000 | 200 | 81000 | 310 | 125550
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 | 1008 |  | 302 |  |  |  | 0 | 110 | 33220 | 388 | 117176 | 200 | 60400 | 200 | 60400 | 310 | 93620
|  |  |  | Engineer/ Discipline Specialist | C1 | 617 |  | 259 |  |  |  | 0 | 50 | 12950 | 169 | 43771 | 174 | 45066 | 174 | 45066 | 224 | 58016
|  |  |  | Draftsman | D1 | 520 |  | 146 |  |  |  |  | 40 | 5840 | 140 | 20440 | 150 | 21900 | 150 | 21900 | 190 | 27740
|  |  |  | Project Manager | E1 | 440 |  | 405 |  |  |  |  | 40 | 16200 | 140 | 56700 | 110 | 44550 | 110 | 44550 | 150 | 60750
|  |  |  | Project Manager | F1 | 410 |  | 162 |  |  |  |  | 40 | 6480 | 140 | 22680 | 95 | 15390 | 95 | 15390 | 135 | 21870
|  |  |  | TOTAL | [9 empty] | 119240 |  | 417907 |  | 268306 |  | 268306 |  | 387546
|  |  |  | Technology zones - Khumra |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4 |  |  |  | Invoice5 |  | Invoice7
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity3 | Amount4 | Quantity25 | Amount36 | Amount37 | Amount38 | Amount39 | Amount40 | Amount41 | Amount42
|  |  |  | Lead Engineer/ Discipline Engineer | A1 | 1023 |  | 405 |  |  |  | 0 | 121 | 49005 | 341 | 138105 | 220 | 89100 | 220 | 89100 | 341 | 138105
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 | 1023 |  | 302 |  |  |  | 0 | 121 | 36542 | 341 | 102982 | 220 | 66440 | 220 | 66440 | 341 | 102982
|  |  |  | Engineer/ Discipline Specialist | C1 | 765 |  | 259 |  |  |  | 0 | 57 | 14763 | 265 | 68635 | 193 | 49987 | 193 | 49987 | 250 | 64750
|  |  |  | Draftsman | D1 | 677 |  | 146 |  |  |  |  | 44 | 6424 | 259 | 37814 | 165 | 24090 | 165 | 24090 | 209 | 30514
|  |  |  | Project Manager | E1 | 569 |  | 405 |  |  |  |  | 44 | 17820 | 239 | 96795 | 121 | 49005 | 121 | 49005 | 165 | 66825
|  |  |  | Project Manager | F1 | 418 |  | 162 |  |  |  |  | 45 | 7290 | 106 | 17172 | 111 | 17982 | 111 | 17982 | 156 | 25272
|  |  |  | TOTAL | [9 empty] | 131844 |  | 461503 |  | 296604 |  | 296604 |  | 428448
|  |  |  | Industrial incubators 3rd ind. City |  |  |  |  | Invoice 7 |  | Invoice 8 |  | Invoice 10
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount | Quantity | Amount
|  |  |  | Lead Engineer/ Discipline Engineer | A1 | 1000 | 800 | 405 | 100 | 40500 | 100 | 40500 | 550 | 222750
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 | 1000 | 800 | 302 | 100 | 30200 | 100 | 30200 | 550 | 166100
|  |  |  | Engineer/ Discipline Specialist | C1 | 800 | 640 | 259 | 80 | 20720 | 80 | 20720 | 440 | 113960
|  |  |  | Draftsman | D1 | 472 | 377 | 146 | 48 | 7008 | 47 | 6862 | 258 | 37668
|  |  |  | Project Manager | E1 | 438 | 350 | 405 | 44 | 17820 | 44 | 17820 | 241 | 97605
|  |  |  | Project Manager | F1 | 429 | 344.5 | 162 | 42 | 6804 | 42.5 | 6885 | 237 | 38394
|  |  |  | TOTAL | [5 empty] | 123052 |  | 122987 |  | 676477

## Invoices
Invoices Process Report - Design Projects
|  | Consultant | Column1 | Frame Work Contract | Value | Duration | Start Date | Finsih Date2 | Committed | remaining from framework | Invoices w/out VAT | Earned value
NA |  | Dorsch |  | 2178 | 29966000 | 48M |  | 2023-11-14 | #REF! | #REF! | #REF! | #REF!
W/OUT VAT | 94.4866 | Dorsch food |  | 2547 | 19993600 | 24M | 2023-06-08 | 2025-06-08 | 19558881 | 434719 | 18891265.58 | 19558881
W/OUT VAT | #REF! | EGEC old |  | 2454 | 3400000 | 9M |  | 2023-08-13 | 3400000 | 0 | #REF! | #REF!
W/OUT VAT | 82.4609 | SYSTRA |  | 2672 | 15054089 | 24M | 2024-02-20 | 2026-02-20 | 15054089 | 0 | 12413741 | 15054089
W/OUT VAT | 72.4796 | EGEC - NIS2 |  | 2709 | 19979840 | 48M | 2024-05-09 | 2028-05-09 | 18492779 | 1487061 | 14481307.34 | 15572069
W/OUT VAT | 90 | ENGICON |  | 2666 | 27837620 | 10M | 2024-06-01 | 2025-04-01 | 27837620 | 0 | 25053857.995 | 27837620
W/OUT VAT | 66.3992 | EGEC - WAS |  | TBA | 9799000 | 24M | 2024-11-12 | 2026-11-12 | 7075670 | 2723330 | 6506456.77 | 6221850
| 62.2285 | ENGICON - Package1 |  | 2891 | 19856000 | 60M | 2025-02-12 | 2030-02-12 | 13340059 | 6515941 | 12356098.01 | 12479059 | [55 empty] | a | b | c
W/OUT VAT | 100 | ENGICON - RDH4 |  | TBA | 7025000 | 24M | 2024-11-21 | 2026-11-21 | 7025000 | 0 | 7024999.85 | 7025000 | [54 empty] | a | 15 | 13 | 15
W/OUT VAT | 24.7646 | Dar AlRiyadh 2 |  | 2814 | 59999685.82 | 60M | 2024-10-02 | 2029-10-02 | 59999685.82 | 0 | 14858654.79 | 14858654.79
W/OUT VAT |  | Meinhardt (KHJ - FOOD) |  | 2966 | 14990000 | 24M | 2025-06-24 | 2027-06-24 | 2997130 | 11992870 | 1198852.07 | -0.07
W/OUT VAT |  | ENGICON - RDH4 PH2 |  | 3026 | 59500000 | 36M | 2025-07-20 | 2028-07-20 | 26992134 | 32507866 | 9333061 | 1347327.61 | [55 empty] | 1
W/OUT VAT |  | AlDar International (KHJ - FOOD2) |  | 3041 | 11637180 | 24M | 2025-08-10 | 2027-08-10 | 7146100 | 4491080 | 1385226.5032 | 845071.3068
W/OUT VAT |  | ENGICON - Logistics |  | 3042 | 27800000 | 24M | 2025-07-30 | 2027-07-30 | 19206662 | 8593338 | 4993631.95 | 614713.354
W/OUT VAT |  | EGEC - NIS3 |  | 3020 | 19955000 | 48M | 2025-07-10 | 2029-07-10 |  | 19955000 | 0 | 0
CASH FLOW OVERVIEW OF RUNNING PROJECTS
INVOICES STATUS
Consultant | NO. | Projects | Column1 | Column2 | Column3 | Column4 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35 | Column36 | Column37 | Column38 | Column39 | Column40 | Column41 | Column42 | Column43 | Column44 | Column45 | Column46 | Column47 | Column48 | Column49 | Column50 | Column51 | Column52 | Column53 | Column54 | Column55 | Column56 | Column57 | Column58 | Column59 | Column60 | Column61 | Column62 | Column63 | Column64 | Column73 | Column72 | Column74 | Column71 | Column77 | Column78 | Column76 | Column75 | Column79 | Column82 | Column81 | Column80 | Column86 | Column85 | Column84 | Column83 | Column90 | Column89 | Column88 | Column87 | Column94 | Column93 | Column92 | Column91 | Column98 | Column97 | Column96 | Column95 | Column102 | Column101 | Column100 | Column99 | Column103 | Column104 | Column105 | Column106 | Column107 | Column108 | Column109 | Column110 | Column114 | Column113 | Column112 | Column111 | Column5 | Column6 | Column7 | Column65 | Column66 | Column67 | Column68 | Column69 | Column70
Consultant | S/No. | Projects |  |  |  | Project ID | Task Value | Invoice # 1 date | Invoice # 1 amount | Invoice # 1 vat | Invoice # 1 total | Invoice # 2 date | Invoice # 2 amount | Invoice # 2 vat | Invoice # 2 total | Invoice # 3 date | Invoice # 3 amount | Invoice # 3 vat | Invoice # 3 total | Invoice # 4 date | Invoice # 4 amount | Invoice # 4 vat | Invoice # 4 total | Invoice # 5 date | Invoice # 5 amount | Invoice # 5 vat | Invoice # 5 total | Invoice # 6 date | Invoice # 6 amount | Invoice # 6 vat | Invoice # 6 total | Invoice # 7 date | Invoice # 7 amount | Invoice # 7 vat | Invoice # 7 total | Invoice # 8 date | Invoice # 8 amount | Invoice # 8 vat | Invoice # 8 total | Invoice # 9 date | Invoice # 9 amount | Invoice # 9 vat | Invoice # 9 total | Invoice # 10 date | Invoice # 10 amount | Invoice # 10 vat | Invoice # 10 total | Invoice # 11 date | Invoice # 11 amount | Invoice # 11 vat | Invoice # 11 total | Invoice # 12 date | Invoice # 12 amount | Invoice # 12 vat | Invoice # 12 total | Invoice # 13 date | Invoice # 13 amount | Invoice # 13 vat | Invoice # 13 total | Invoice # 14 date | Invoice # 14 amount | Invoice # 14 vat | Invoice # 14 total | Invoice # 15 date | Invoice # 15 amount | Invoice # 15 vat | Invoice # 15 total | Invoice # 16 date | Invoice # 16 amount | Invoice # 16 vat | Invoice # 16 total | Invoice # 17 date | Invoice # 17 amount | Invoice # 17 vat | Invoice # 17 total | Invoice # 18 date | Invoice # 18 amount | Invoice # 18 vat | Invoice # 18 total | Invoice # 19 date | Invoice # 19 amount | Invoice # 19 vat | Invoice # 19 total | Invoice # 20 date | Invoice # 20 amount | Invoice # 20 vat | Invoice # 20 total | Invoice # 21 date | Invoice # 21 amount | Invoice # 21 vat | Invoice # 21 total | Invoice # 22 date | Invoice # 22 amount | Invoice # 22 vat | Invoice # 22 total | Invoice # 23 date | Invoice # 23 amount | Invoice # 23 vat | Invoice # 23 total | Invoice # 24 date | Invoice # 24 amount | Invoice # 24 vat | Invoice # 24 total | Invoice # 25 date | Invoice # 25 amount | Invoice # 25 vat | Invoice # 25 total | Remarks | Task Value | VAT | Total | Invoices Submitted Without VAT | Invoices Submitted With VAT | % Completion | Earned Value | Remaining Value
Dorsch food | [5 empty] | MLTX-01-085 | 19993600 | [109 empty] | #NAME? |  |  | 785604 | 785604 | 450 | 440 | 198000 | 2907 | 1308150
Dorsch food | 1 | Jeddah 2 - Food Cluster - RBF 450 & 900 m2 |  |  |  | JDH2-01-016 | 877779 | 2023-10-26 | 416905 | 62535.75 | 479440.75 |  |  |  |  | 2024-04-16 | 368699 | 55304.85 | 424003.85 | [89 empty] | 877779 | 131666.85 | 1009445.85 | 785604 | 903444.6 | 100% | 877779 | 92175 | #NAME? |  |  | 1403611 | 618007 | 333 | 1416 | 471528 | 4548 | 1514484
Dorsch food | 2 | Jeddah Food Cluster - Masterplan Update & Lands Selection at Jeddah 2nd & 3rd Ind. Cities |  |  |  | MLTX-01-093 | 1403611 | 2023-10-26 | 1403611 | 210541.65 | 1614152.65 | [97 empty] | 1403611 | 210541.65 | 1614152.65 | 1403611 | 1614152.65 | 100% | 1403611 | 0 | #NAME? |  |  | 2675323 | 1271712 | 266 | 2024 | 538384 | 6170 | 1641220
Dorsch food | 3 | Jeddah 3 - Design of Shared Dry & Cold Storage Warehouses in Jeddah 3 Ind. City |  |  |  | JDH3-01-021 | 2999654 | 2023-10-26 | 1377997 | 206699.55 | 1584696.55 |  |  |  |  | 2024-04-16 | 1297326 | 194598.9 | 1491924.9 | [89 empty] | 2999654 | 449948.1 | 3449602.1 | 2675323 | 3076621.45 | 100% | 2999654 | 324331 | #NAME? |  |  | 4125000 | 1449677 | 135 | 2060 | 278100 | 7544 | 1018440
Dorsch food | 4 | Master planning a logistic area in Dammam 2 |  |  |  | DAM2-01-026 | 4125000 |  |  |  |  | 2024-03-19 | 682683 | 102402.45 | 785085.45 |  |  |  |  | 2024-05-23 | 1379810.1 | 206971.515 | 1586781.615 |  |  |  |  | 2024-06-28 | 2062506.53 | 309375.9795 | 2371882.5095 | [77 empty] | 4125000 | 618750 | 4743750 | 4124999.63 | 4743749.5745 | 100% | 4125000 | 0.37 | #NAME? |  |  | 404258 | -3720741.63 |  |  | 1486012 |  | 5482294
Dorsch food | 5 | Hydrology Study for preventing Jeddah 4th Industrial City from floods and stormwater |  |  |  | JDH4-01-040 | 404258 | [12 empty] | 2024-05-23 | 125226 | 18783.9 | 144009.9 | [8 empty] | 2024-09-02 | 279032 | 41854.8 | 320886.8 | [73 empty] | 404258 | 60638.7 | 464896.7 | 404258 | 144009.9 | 100% | 404258 | 0 | Was 5,482,294 (task order= 1,486,012) |  |  | 6968307 | 6564049 |  |  | 5478244
Dorsch food | 6 | Completing the infrastructure networks and residential neighborhood in the 2nd industrial city in Dammam |  |  |  | DAM2-02-027 | 6968306 | [16 empty] | 2024-06-08 | 2539503 | 380925.45 | 2920428.45 | [8 empty] | 2024-09-05 | 1602086 | 240312.9 | 1842398.9 | [16 empty] | 2025-03-12 | 2826717.95 | 424007.6925 | 3250725.6425 | [49 empty] | 6968306 | 1045245.9 | 8013551.9 | 6968306.95 | 8013552.9925 | 100% | 6968306 | -0.95 |  |  |  | 174000 | -6794306.95
Dorsch food | 7 | Reviewing the masterplan for alkhrj nd. City |  |  |  |  | 174000 | [16 empty] | 2024-06-08 | 58000.11 | 8700.0165 | 66700.1265 | 2024-06-28 | 115999.89 | 17399.9835 | 133399.8735 | [77 empty] | 174000 | 26100 | 200100 | 174000 | 200100 | 100% | 174000 | 0 |  |  |  | 836000 | 662000 |  |  |  | 4050
Dorsch food | 8 | Detail MPL and infra Design for the multi-use area in Dammam2 |  |  |  | DAM2-01-029 | 836000 | [32 empty] | 2024-10-07 | 302500.8 | 45375.12 | 347875.92 | 2024-12-24 | 533499.2 | 80024.88 | 613524.08 | [61 empty] | 836000 | 125400 | 961400 | 836000 | 961400 | 100% | 836000 | 0 | with addendum |  |  | 1254658 | 418658
Dorsch food | 9 | Design shared services center - Food cluster |  |  |  | JDH2-01-023 | 1505768 | [32 empty] | 2024-10-07 | 499280 | 74892 | 574172 |  |  |  |  | 2025-02-05 | 500302 | 75045.3 | 575347.3 | 2025-03-04 | 255076 | 38261.4 | 293337.4 | [53 empty] | 1505768 | 225865.2 | 1731633.2 | 1254658 | 1442856.7 | 100% | 1505768 | 251110 |  |  |  | 264505 | -990153
Dorsch food | 10 | الدراسه القيميه لمشاريع المصانع الجاهزة |  |  |  |  | 264505 | [36 empty] | 2024-12-24 | 264505 | 39675.75 | 304180.75 | [61 empty] | 264505 | 39675.75 | 304180.75 | 264505 | 304180.75 | 100% | 264505 | 0 |  |  |  |  | -264505
Dorsch food | [108 empty] | 0 | 0 | 0 | 0 |  | 100% | 0 | 0 |  |  |  |  | 0
Dorsch food | [111 empty] | 0 | [7 empty] | 18891266 | 18891266
Dorsch food | [8 empty] | 3198513 |  | 3678289.95 |  | 682683 |  | 785085.45 | 2082531 | 1666025 |  | 1915928.75 |  | 1505036.1 |  | 1730791.515 |  | 2597503.11 |  | 2987128.5765 |  | 2178506.42 |  | 2505282.383 |  | 279032 |  | 320886.8 |  | 1602086 |  | 1842398.9 |  | 801780.8 |  | 922047.92 |  | 798004.2 |  | 917704.83 |  | 500302 |  | 575347.3 |  | 255076 |  | 293337.4 |  | 2826717.95 |  | 3250725.6425 | [49 empty] | 19558881 | 2933832.15 | 22492713.15 | 18891265.58 | 21404068.617 |  | 19558881 | 667615.42 |  |  |  |  | -18891265.58
SYSTRA | [5 empty] | MLTX-01-102 | 15054089 | [104 empty] | 0 | [5 empty] | 9 |  | 5381577.6 | 5381577.6
SYSTRA | 1 | Masterplan & Infrstructure Detailed Design For Technology Zones (Jenadryah) |  |  |  | JNDT-01-001 | 6726972 | 2024-07-31 | 672697.82 | 100904.673 | 773602.493 | 2024-08-07 | 1681772 | 252265.8 | 1934037.8 | 2024-12-15 | 1345449 | 201817.35 | 1547266.35 | 2025-03-11 | 1681658.78 | 252248.817 | 1933907.597 |  |  |  |  | 2025-07-01 | 1345394.4 | 201809.16 | 1547203.56 | [77 empty] | 6726972 | 1009045.8 | 7736017.8 | 6726972 | 7736017.8 | 100% | 6726972 | 0 |  |  |  | 330043.5 | -6396928.5
SYSTRA | 2 | Masterplan & Infrstructure Detailed Design For Technology Zones (Dammam) |  |  |  | DAMT-01-001 | 3300435 | [12 empty] | 2025-03-11 | 330043.5 | 49506.525 | 379550.025 | 2025-05-11 | 1072641.37 | 160896.2055 | 1233537.5755 | 2025-07-01 | 577576.13 | 86636.4195 | 664212.5495 | [77 empty] | 3300435 | 495065.25 | 3795500.25 | 1980261 | 2277300.15 | 100% | 3300435 | 1320174 |  | 1980261 | 0 | 330043.5 | -1650217.5
SYSTRA | 3 | Masterplan & Infrstructure Detailed Design For Technology Zones (Dhahran) |  |  |  | DHRT-01-001 | 3300435 | [12 empty] | 2025-03-11 | 330043.5 | 49506.525 | 379550.025 | 2025-05-11 | 1072641.38 | 160896.207 | 1233537.587 | 2025-07-01 | 577576.12 | 86636.418 | 664212.538 | [77 empty] | 3300435 | 495065.25 | 3795500.25 | 1980261 | 2277300.15 | 100% | 3300435 | 1320174 |  | 1980261 | 0 |  | -1980261
SYSTRA | 4 | Technical review and transport planning expertise support for Riyadh Industrial cities 1 & 4 |  |  |  | MLTX-01-111 | 1726247 | [16 empty] | 2025-05-11 | 1208357.98 | 181253.697 | 1389611.677 | 2025-07-01 | 517889.02 | 77683.353 | 595572.373 | [77 empty] | 1726247 | 258937.05 | 1985184.05 | 1726247 | 1985184.05 | 100% | 1726247 | 0 |  |  | -1726247 |  | -1726247
SYSTRA | [111 empty] | 0 | [6 empty] | 0 | 6041664.6 | 6041664.6
SYSTRA | [8 empty] | 672697.82 |  | 773602.493 |  | 1681772 |  | 1934037.8 |  | 1345449 |  | 1547266.35 |  | 2341745.78 |  | 2693007.647 |  | 3353640.73 |  | 3856686.8395 |  | 3018435.67 |  | 3471201.0205 | [77 empty] | 15054089 | 2258113.35 | 17312202.35 | 12413741 | 14275802.15 |  | 15054089 | 2640348 |  |  |  |  | -12413741
EGEC - NIS2 | [5 empty] | MLTX-01-099 | 19979840 | [104 empty] | 0 | [6 empty] | 0 | 4360270 | 4360270
EGEC - NIS2 | 1 | Updated concept masterplan & Infrastructure designs for Tabouk ind. City |  |  |  | TAB-01-009 | 4360270 | 2024-07-23 | 1395290.5 | 209293.575 | 1604584.075 | 2024-08-28 | 1874916.39 | 281237.4585 | 2156153.8485 | [8 empty] | 2024-11-30 | 872049.61 | 130807.4415 | 1002857.0515 | 2024-12-25 | 218013.5 | 32702.025 | 250715.525 | [77 empty] | 4360270 | 654040.5 | 5014310.5 | 4360270 | 5014310.5 | 100% | 4360270 | 5.0003e-06 |  |  | -4360270 | 1116225 | -3244045
EGEC - NIS2 | 2 | Project support services (6 months) (Masterplan) |  |  |  |  | 744150 |  |  |  |  | 2024-08-28 | 372075 | 55811.25 | 427886.25 |  |  |  |  | 2024-10-31 | 372075 | 55811.25 | 427886.25 | [85 empty] | 744150 | 111622.5 | 855772.5 | 744150 | 855772.5 | 100% | 744150 | 0 |  |  | -744150 | 0 | -744150
EGEC - NIS2 | 3 | Project support services (6 months) (VRO) |  |  |  |  | 744150 | [24 empty] | 2025-01-31 | 372075 | 55811.25 | 427886.25 | [12 empty] | 2025-05-30 | 372075 | 55811.25 | 427886.25 | [57 empty] | 744150 | 111622.5 | 855772.5 | 744150 | 855772.5 | 100% | 744150 | 0 |  |  | -744150 | 153002.2 | -591147.8
EGEC - NIS2 | 4 | Testing and evaluating concrete structure |  |  |  |  | 153002 |  |  |  |  | 2024-08-28 | 107101.54 | 16065.231 | 123166.771 | 2024-10-21 | 45900.66 | 6885.099 | 52785.759 | [89 empty] | 153002 | 22950.3 | 175952.3 | 153002.2 | 175952.53 | 100% | 153002 | -0.2 |  |  | -153002.2 | 156177 | 3174.8
EGEC - NIS2 | 5 | Preliminary designs for the expansion of the industrial city in riyadh |  |  |  |  | 156177 | [8 empty] | 2024-10-21 | 109323.9 | 16398.585 | 125722.485 |  |  |  |  | 2024-11-30 | 46853.1 | 7027.965 | 53881.065 | [81 empty] | 156177 | 23426.55 | 179603.55 | 156177 | 179603.55 | 100% | 156177 | 0 |  |  | -156177 | 1656100 | 1499923
EGEC - NIS2 | 6 | Incubators in Al-Qassim Oasis |  |  |  | QSM3-01-014 | 1656100 | [16 empty] | 2024-11-30 | 248415 | 37262.25 | 285677.25 | 2024-12-25 | 828050 | 124207.5 | 952257.5 | 2025-01-31 | 579635 | 86945.25 | 666580.25 | [73 empty] | 1656100 | 248415 | 1904515 | 1656100 | 1904515 | 100% | 1656100 | 0 |  |  | -1656100 | 768027 | -888073
EGEC - NIS2 | 7 | Site development and infrastructure design works for expansion in Jeddah 1 |  |  |  | JDH1-01-021 | 2560090 | [24 empty] | 2025-01-31 | 384013.5 | 57602.025 | 441615.525 |  |  |  |  | 2025-04-13 | 384013.5 | 57602.025 | 441615.525 | 2025-04-30 | 640022.5 | 96003.375 | 736025.875 | 2025-05-30 | 896032 | 134404.8 | 1030436.8 | 2025-07-27 | 256008.5 | 38401.275 | 294409.775 | [53 empty] | 2560090 | 384013.5 | 2944103.5 | 2560090 | 2649693.725 | 100% | 2560090 | 0 |  |  | -2560090 | 693000 | -1867090
EGEC - NIS2 | 8 | Detailed design of connection road (Fly Over) in Dammam 2 |  |  |  | DAM2-01-033 | 2310000 | [32 empty] | 2025-04-13 | 693000 | 103950 | 796950 | [65 empty] | 2310000 | 346500 | 2656500 | 693000 | 796950 | 30% | 693000 | 0 |  |  | -693000 | 350000 | -343000
EGEC - NIS2 | 9 | Labour camp masterplan and infrastructure development in AlKharj |  |  |  | KHJ-01-025 | 350000 | [28 empty] | 2025-03-02 | 175000 | 26250 | 201250 | 2025-04-13 | 175000 | 26250 | 201250 | [65 empty] | 350000 | 52500 | 402500 | 350000 | 402500 | 100% | 350000 | 0 |  |  | -350000 | 210000 | -140000
EGEC - NIS2 | 10 | Potable water pipeline supply and connection to alkharj 1st ind. City |  |  |  | KHJ-01-026 | 700000 | [32 empty] | 2025-04-13 | 210000 | 31500 | 241500 | [12 empty] | 2025-09-07 | 175000.64 | 26250.096 | 201250.736 | [8 empty] | 2025-12-03 | 140000 | 21000 | 161000 | [37 empty] | 700000 | 105000 | 805000 | 525000.64 | 603750.736 | 86% | 602000 | 76999.36 |  | 525000.64 | 0 | 85000 | -440000.64
EGEC - NIS2 | 11 | Study design RBFs 900 & 450m2 SFDA requirements |  |  |  |  | 170000 | [32 empty] | 2025-04-13 | 85000 | 12750 | 97750 | [16 empty] | 2025-09-29 | 85000 | 12750 | 97750 | [45 empty] | 170000 | 25500 | 195500 | 170000 | 97750 | 100% | 170000 | 0 |  |  | -170000
EGEC - NIS2 | 12 | Improving the entrances and exit points for Jeddah 1 |  |  |  | JDH1-01-028 | 1590000 | [56 empty] | 2025-10-26 | 794999.1 | 119249.865 | 914248.965 | [41 empty] | 1590000 | 238500 | 1828500 | 794999.1 | 914248.965 | 85% | 1351500 | 556500.9 |  | 794999.1 | 0 |  | -794999.1
EGEC - NIS2 | 13 | Hydrology study for Jeddah 2 |  |  |  |  | 110500 | [56 empty] | 2025-10-26 | 44199.17 | 6629.8755 | 50829.0455 | [41 empty] | 110500 | 16575 | 127075 | 44199.17 | 50829.0455 | 98% | 108290 | 64090.83 |  | 44199.17 | 0
EGEC - NIS2 | 14 | Jenadriyadh Business Incubators |  |  |  | JNDT-01-002 | 500000 | [60 empty] | 2025-12-03 | 100000 | 15000 | 115000 | [37 empty] | 500000 | 75000 | 575000 | 100000 | 115000 | 25% | 125000 | 25000 |  | 100000 | 0
EGEC - NIS2 | 15 | Project support services 3 |  |  |  |  | 1798340 | [48 empty] | 2025-09-07 | 449585 | 67437.75 | 517022.75 | 2025-09-29 | 449585 | 67437.75 | 517022.75 | [45 empty] | 1798340 | 269751 | 2068091 | 899170 | 1034045.5 | 100% | 1798340 | 899170 |  | 899170 | 0
EGEC - NIS2 | 16 | Adaptation and Design of an Administrative Building Humanization in Riyadh 2 |  |  |  |  | 590000 | [52 empty] | 2025-09-29 | 471999.23 | 70799.8845 | 542799.1145 |  |  |  |  | 2025-12-03 | 59000 | 8850 | 67850 | [37 empty] | 590000 | 88500 | 678500 | 530999.23 | 610649.1145 | 80% | 472000 | -58999.23 |  | 530999.23 | 0
EGEC - NIS2 | [117 empty] | 0 | 0 | 9547801.2 | 9547801.2
EGEC - NIS2 | [8 empty] | 1395290.5 |  | 1604584.075 |  | 2354092.93 |  | 2707206.8695 |  | 155224.56 |  | 178508.244 |  | 372075 |  | 427886.25 |  | 1167317.71 |  | 1342415.3665 |  | 1046063.5 |  | 1202973.025 |  | 1335723.5 |  | 1536082.025 |  | 175000 |  | 201250 |  | 1547013.5 |  | 1439815.525 |  | 640022.5 |  | 736025.875 |  | 1268107 |  | 1458323.05 |  | 256008.5 |  | 294409.775 |  | 624585.64 |  | 718273.486 |  | 1006584.23 | 150987.6345 | 1157571.8645 |  | 839198.27 | 125879.7405 | 965078.0105 |  | 299000 | 44850 | 343850 | [37 empty] | 18492779 | 2773916.85 | 21266695.85 | 14481307.34 | 16261343.666 |  | 15572069 | 1621760.89 |  | 14481307.34 | 0 |  | -14481307.34
ENGICON | [5 empty] | RDH4-00-001 | 27837620 | [104 empty] | 0 |  |  |  |  | الضمان | 0 | 0 | 18468720.279 | 18468720.279
ENGICON | 1 | Riyadh 4 Masterplan and Infrastructure concept design |  |  |  |  | 27837620 | 2024-07-07 | 2361050.1 | 354157.515 | 2715207.615 | 2024-08-07 | 3157746.651 | 473661.9976 | 3631408.6486 | 2024-08-31 | 3983985.909 | 597597.8863 | 4581583.7954 | 2024-10-02 | 3449998.296 | 517499.7444 | 3967498.0404 | 2024-12-10 | 1820099.709 | 273014.9563 | 2093114.6653 | 2025-01-28 | 999999.999 | 149999.9998 | 1149999.9989 | 2025-03-04 | 2695839.615 | 404375.9423 | 3100215.5573 | 2025-04-20 | 2223402.876 | 333510.4314 | 2556913.3074 | 2025-05-12 | 1742432.4 | 261364.86 | 2003797.26 | 2025-06-01 | 2619302.44 | 392895.366 | 3012197.806 | [61 empty] | 27837620 | 4175643 | 32013263 | 25053857.995 | 28811936.6943 | 100% | 27837620 |  |  | 25053857.995 | 0 |  | -25053857.995
ENGICON | [111 empty] | 0 | [5 empty] | 0 | 0 | 18468720.279 | 18468720.279
ENGICON | [8 empty] | 2361050.1 |  | 2715207.615 |  | 3157746.651 |  | 3631408.6486 |  | 3983985.909 |  | 4581583.7954 |  | 3449998.296 |  | 3967498.0404 |  | 1820099.709 |  | 2093114.6653 |  | 999999.999 |  | 1149999.9989 |  | 2695839.615 |  | 3100215.5573 |  | 2223402.876 |  | 2556913.3074 |  | 1742432.4 |  | 2003797.26 |  | 2619302.44 |  | 3012197.806 | [24 empty] | ` | [36 empty] | 27837620 | 4175643 | 32013263 | 25053857.995 | 28811936.6943 |  | 27837620 |  |  | #VALUE! |  |  | -25053857.995
EGEC - WAS | [5 empty] | WAS1-01-039 | 9799000 | [104 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 1726555 | 1726555
EGEC - WAS | 1 | Site development and buildings design for labour community area in WAS industrial city |  |  |  | WAS-01-035 | 4421850 | 2024-03-03 | 1726555 | 258983.25 | 1985538.25 |  |  |  |  | 2025-04-30 | 1641704.68 | 246255.702 | 1887960.382 | 2025-05-30 | 611379 | 91706.85 | 703085.85 | 2025-07-27 | 221091 | 33163.65 | 254254.65 | 2025-09-01 | 221120.33 | 33168.0495 | 254288.3795 | [77 empty] | 4421850 | 663277.5 | 5085127.5 | 4421850.01 | 5085127.5115 | 100% | 4421850 | -0.01 |  | 4421850.01 | 0 | 195000 | -4226850.01
EGEC - WAS | 2 | Design commercial area with fuel station in Waad AlShamal |  |  |  | WAS-01-034 | 650000 |  |  |  |  | 2024-04-13 | 195000 | 29250 | 224250 | 2025-04-30 | 227500 | 34125 | 261625 | 2025-05-30 | 227500 | 34125 | 261625 | [85 empty] | 650000 | 97500 | 747500 | 650000 | 747500 | 100% | 650000 | 0 |  | 650000 | 0 |  | -650000
EGEC - WAS | 4 | Development of labour camps in: DAM03, NJR, MKH2, JDH2, SUD, ASR1 |  |  |  | MLTX-01-119 | 1150000 | [16 empty] | 2025-07-27 | 115000 | 17250 | 132250 |  |  |  |  | 2025-09-17 | 460000 | 69000 | 529000 | 2025-10-26 | 575000 | 86250 | 661250 | [69 empty] | 1150000 | 172500 | 1322500 | 1150000 | 1322500 | 100% | 1150000 | 0 |  | 1150000 | 0
EGEC - WAS | 4 | Project support services 4 |  |  |  |  | 853820 | [32 empty] | 2025-12-03 | 284606.76 | 42691.014 | 327297.774 | [68 empty] | 284606.76 | 327297.774 |  |  |  |  | 284606.76 | 0 | 1921555 | 1636948.24
EGEC - WAS | [8 empty] | 1726555 |  | 1985538.25 |  | 195000 |  | 224250 |  | 1869204.68 |  | 2149585.382 |  | 838879 |  | 964710.85 |  | 336091 |  | 386504.65 |  | 221120.33 |  | 254288.3795 |  | 460000 |  | 529000 |  | 575000 |  | 661250 |  | 284606.76 | 42691.014 | 327297.774 | [65 empty] | 6221850 | 933277.5 | 7155127.5 | 6506456.77 | 7155127.5115 |  | 6221850 | -0.01 |  | 6506456.77 | 0 |  | -6506456.77
ENGICON - RDH4 | [5 empty] | RDH4-01-002 | 7025000 | [104 empty] | 0 | [5 empty] | 0 | 0 | 1999999.85 | 1999999.85
ENGICON - RDH4 | 1 | Design work for entrance and facilities for Riyadh 4 |  |  |  |  | 7025000 | 2025-01-27 | 1999999.85 | 299999.9775 | 2299999.8275 | 2025-07-01 | 2350000 | 352500 | 2702500 | 2025-07-10 | 2675000 | 401250 | 3076250 | [89 empty] | 7025000 | 1053750 | 8078750 | 7024999.85 | 2299999.8275 | 100% | 7025000 | 0.15 |  | 7024999.85 | 0 | 1999999.85 | -5025000
ENGICON - RDH4 | [108 empty] | 7025000 | 1053750 | 8078750 | 7024999.85 | 2299999.8275 |  | 7025000 | 0.15 |  | 0 | -7024999.85 |  | -7024999.85
Dar AlRiyadh 2 | [5 empty] | MLTX-01-100 | 59999685.82 | [104 empty] | 0 | 0 |  |  |  |  | 0 | 0 |  | 0
Dar AlRiyadh 2 | [6 empty] | 1 | 2024-12-19 | 40768 | 6115.2 | 46883.2 | [100 empty] | 40768 | 46883.2 |  |  |  |  | 40768 | 0 |  | -40768
Dar AlRiyadh 2 | [6 empty] | 2 | 2024-12-19 | 866679.33 | 130001.8995 | 996681.2295 | [100 empty] | 866679.33 | 996681.2295 |  |  |  |  | 866679.33 | 0 |  | -866679.33
Dar AlRiyadh 2 | [6 empty] | 3 | 2025-01-01 | 1114782.01 | 167217.3015 | 1281999.3115 | [100 empty] | 1114782.01 | 1281999.3115 |  |  |  |  | 1114782.01 | 0 |  | -1114782.01
Dar AlRiyadh 2 | [6 empty] | 4 | 2025-02-04 | 1206719.08 | 181007.862 | 1387726.942 | [100 empty] | 1206719.08 | 1387726.942 |  |  |  |  | 1206719.08 | 0 |  | -1206719.08
Dar AlRiyadh 2 | [6 empty] | 5 | 2025-03-03 | 1200633.93 | 180095.0895 | 1380729.0195 | [100 empty] | 1200633.93 | 1380729.0195 |  |  |  |  | 1200633.93 | 0 |  | -1200633.93
Dar AlRiyadh 2 | [6 empty] | 6 | 2025-04-08 | 1118030.39 | 167704.5585 | 1285734.9485 | [100 empty] | 1118030.39 | 1285734.9485 |  |  |  |  | 1118030.39 | 0
Dar AlRiyadh 2 | [6 empty] | 7 | 2025-05-04 | 1216426.3 | 182463.945 | 1398890.245 | [100 empty] | 1216426.3 | 1398890.245 |  |  |  |  | 1216426.3 | 0
Dar AlRiyadh 2 | [6 empty] | 8 | 2025-06-01 | 1310618.68 | 196592.802 | 1507211.482 | [100 empty] | 1310618.68 | 1507211.482 |  |  |  |  | 1310618.68 | 0
Dar AlRiyadh 2 | [6 empty] | 9 | 2025-07-02 | 1147200.41 | 172080.0615 | 1319280.4715 | [100 empty] | 1147200.41 | 1319280.4715 |  |  |  |  | 1147200.41 | 0
Dar AlRiyadh 2 | [6 empty] | 10 | 2025-08-04 | 1122204.53 | 168330.6795 | 1290535.2095 | [100 empty] | 1122204.53 | 1290535.2095 |  |  |  |  | 1122204.53 | 0
Dar AlRiyadh 2 | [6 empty] | 11 | 2025-09-01 | 1165613.3 | 174841.995 | 1340455.295 | [100 empty] | 1165613.3 | 1340455.295 |  |  |  |  | 1165613.3 | 0
Dar AlRiyadh 2 | [6 empty] | 12 | 2025-10-01 | 1069979.68 | 160496.952 | 1230476.632 | [100 empty] | 1069979.68 | 1230476.632 |  |  |  |  | 1069979.68 | 0
Dar AlRiyadh 2 | [6 empty] | 13 | 2025-11-02 | 1203549.11 | 180532.3665 | 1384081.4765 | [100 empty] | 1203549.11 | 1384081.4765 |  |  |  |  | 1203549.11 | 0 |  | -1203549.11
Dar AlRiyadh 2 | [6 empty] | 14 | 2025-12-03 | 1075450.04 | 161317.506 | 1236767.546 | [100 empty] | 1075450.04 | 1236767.546 |  |  |  |  | 1075450.04 | 0 |  | -1075450.04
Dar AlRiyadh 2 | [8 empty] | 14858654.79 |  | 17087453.0085 | [100 empty] | 14858654.79 | 17087453.0085 |  |  |  |  | 14858654.79 | 0 |  | -14858654.79
ENGICON - Package1 | [5 empty] | MLTX-01-098 | 19856000 | [104 empty] | 0 | [5 empty] | 0 | 0 |  | 0
ENGICON - Package1 | 1 | NIS Design adaptation of RBF 450 , 900 m2 |  |  |  |  | 7940002 | 2025-01-28 | 3062572.2 | 459385.83 | 3521958.03 | 2025-07-10 | 1814857.6 | 272228.64 | 2087086.24 | [12 empty] | 2025-10-08 | 2296929.16 | 344539.374 | 2641468.534 |  |  |  |  | 2025-11-30 | 765643.05 | 114846.4575 | 880489.5075 | [69 empty] | 7940002 | 1191000.3 | 9131002.3 | 7940002.01 | 9131002.3115 | 100% | 7940002 | -0.01 |  | 7940002.01 | 0 |  | -7940002.01
ENGICON - Package1 | 2 | Detailed design of lake park and supply connection for Sudair Industrial City |  |  |  | SUD1-01-033 | 1658659 | 2025-01-28 | 746396.55 | 111959.4825 | 858356.0325 | 2025-07-10 | 912262.45 | 136839.3675 | 1049101.8175 | [93 empty] | 1658659 | 248798.85 | 1907457.85 | 1658659 | 1907457.85 | 100% | 1658659 | 0 |  | 1658659 | 0
ENGICON - Package1 | 3 | Technology Zone- Asfan |  |  |  | ASFT-01-001 | 1192999 | [8 empty] | 2025-07-21 | 119240 | 17886 | 137126 | 2025-08-24 | 417907 | 62686.05 | 480593.05 | 2025-09-29 | 268306 | 40245.9 | 308551.9 |  |  |  |  | 2025-10-29 | 387546 | 58131.9 | 445677.9 | [73 empty] | 1192999 | 178949.85 | 1371948.85 | 1192999 | 926270.95 | 100% | 1192999 | 0 |  | 1192999 | 0
ENGICON - Package1 | 4 | Technology Zone- Khumra |  |  |  | KUMT-01-001 | 1318399 | [8 empty] | 2025-07-21 | 131844 | 19776.6 | 151620.6 | 2025-08-24 | 461503 | 69225.45 | 530728.45 | 2025-09-29 | 296604 | 44490.6 | 341094.6 |  |  |  |  | 2025-10-29 | 428448 | 64267.2 | 492715.2 | [73 empty] | 1318399 | 197759.85 | 1516158.85 | 1318399 | 1023443.65 | 100% | 1318399 | 0 |  | 1318399 | 0 |  | -1318399
ENGICON - Package1 | 5 | Riyadh 3 Business incubators |  |  |  | RDH3-01-012 | 1230000 | [24 empty] | 2025-10-29 | 123052 | 18457.8 | 141509.8 | 2025-11-30 | 122987 | 18448.05 | 141435.05 | [69 empty] | 1230000 | 184500 | 1414500 | 246039 | 282944.85 | 30% | 369000 | 122961 |  | 246039 | 0
ENGICON - Package1 | [117 empty] | 0 | 0 |  | 0
ENGICON - Package1 | [8 empty] | 3808968.75 |  | 4380314.0625 |  | 2727120.05 |  | 3136188.0575 |  | 251084 |  | 288746.6 |  | 879410 |  | 1011321.5 |  | 564910 |  | 649646.5 |  | 2296929.16 |  | 2641468.534 |  | 939046 |  | 1079902.9 |  | 888630.05 |  | 1021924.5575 | [69 empty] | 13340059 | 2001008.85 | 15341067.85 | 12356098.01 | 13271119.6115 |  | 12479059 | 122960.99 |  | 12356098.01 | 0
Meinhardt (KHJ- FOOD) | [5 empty] | KHJ1-01-020 | 14990000 | [110 empty] | 0 | 0
Meinhardt (KHJ- FOOD) | 1 | Development of Design guidelines, production strategy, and prototype packages for mid-sized RBFs |  |  |  |  | 2997130 | 2025-10-09 | 299713 | 44956.95 | 344669.95 | 2025-10-21 | 299713 | 44956.95 | 344669.95 | 2025-10-29 | 599426.07 | 89913.9105 | 689339.9805 | [89 empty] | 2997130 | 449569.5 | 3446699.5 | 1198852.07 | 1378679.8805 | 40% | 1198852 | -0.07 |  | 1198852.07 | 0
Meinhardt (KHJ- FOOD) | [111 empty] | 0 | [5 empty] | 0 | 0
Meinhardt (KHJ- FOOD) | [111 empty] | 0 | 0 |  |  |  |  | 0 | 0
[112 empty] | 0 | 0 |  |  |  |  | 0 | 0
[9 empty] | 299713 |  | 344669.95 |  | 299713 |  | 344669.95 |  | 599426.07 |  | 689339.9805 | [89 empty] | 2997130 | 449569.5 | 3446699.5 | 1198852.07 | 1378679.8805 |  | 1198852 | -0.07 |  | 1198852.07 | 0
ENGICON - RDH4 PH2 | [5 empty] | RDH4-01-003 | 59500000 | [110 empty] | 0 | 0
ENGICON - RDH4 PH2 | 1 | 70 RBF's in Riyadh 04 |  |  |  |  | 2490457 | 2025-11-05 | 747154 | 112073.1 | 859227.1 |  | 622572 | 93385.8 | 715957.8 | [93 empty] | 2490457 | 373568.55 | 2864025.55 | 1369726 | 1575184.9 | 55% | 1369751.35 | 25.35 |  | 1369726 | 0
ENGICON - RDH4 PH2 | 2 | Development for the Masterplan and Concept Infrastructure for the expansion of Riyadh 4 industrial city |  |  |  | RDH4-01-005 | 24501677 | 2025-11-05 | 7963335 | 1194500.25 | 9157835.25 | [97 empty] | 24501677 | 3675251.55 | 28176928.55 | 7963335 | 9157835.25 | 38% | 9310637.26 | 1347302.26 |  | 7963335 | 0
ENGICON - RDH4 PH2 | [117 empty] | 0 | 0
[118 empty] | 0 | 0
[9 empty] | 8710489 |  | 10017062.35 |  | 622572 |  | 715957.8 | [93 empty] | 26992134 | 4048820.1 | 31040954.1 | 9333061 | 10733020.15 |  | 10680388.61 | 1347327.61 |  | 9333061 | 0
AlDar International (KHJ - FOOD2) | [5 empty] | KHJ-01-027 | 11637180 | [110 empty] | 0 | 0
AlDar International (KHJ - FOOD2) | 1 | AlKharj Food cluster |  |  |  | KHJ1-01-030 | 7146100 | 2025-10-30 | 659049.98 | 98857.497 | 757907.477 | 2025-11-20 | 726176.5232 | 108926.4785 | 835103.0017 | [93 empty] | 7146100 | 1071915 | 8218015 | 1385226.5032 | 1593010.4787 | 31.21% | 2230297.81 | 845071.3068 |  | 1385226.5032 | 0
AlDar International (KHJ - FOOD2) | [111 empty] | 0 |  |  |  |  | 0 | 0 | 0
AlDar International (KHJ - FOOD2) | [111 empty] | 0 | [5 empty] | 0 | 0
[118 empty] | 0 | 0
[9 empty] | 659049.98 |  | 757907.477 |  | 726176.5232 |  | 835103.0017 | [93 empty] | 7146100 | 1071915 | 8218015 | 1385226.5032 | 1593010.4787 |  | 2230297.81 | 845071.3068 |  | 1385226.5032 | 0
ENGICON - Logistics | [5 empty] | MLTX-01-117 | 27800000 | [110 empty] | 0 | 0
ENGICON - Logistics | 1 | Logistic Zones (JDH3,DAM3,MAD,MKH2) |  |  |  | MLTX-01-123 | 19206662 | 2025-09-29 | 960349 | 144052.35 | 1104401.35 | 2025-10-08 | 960349 | 144052.35 | 1104401.35 | 2025-10-29 | 288080.85 | 43212.1275 | 331292.9775 | 2025-12-01 | 2784853.1 | 417727.965 | 3202581.065 | [85 empty] | 19206662 | 2880999.3 | 22087661.3 | 4993631.95 | 5742676.7425 | 29.2% | 5608345.304 | 614713.354 |  | 4993631.95 | 0
ENGICON - Logistics | [111 empty] | 0 | [5 empty] | 0 | 0
ENGICON - Logistics | [111 empty] | 0 | [5 empty] | 0 | 0
[118 empty] | 0 | 0
[9 empty] | 960349 |  | 1104401.35 |  | 960349 |  | 1104401.35 |  | 288080.85 |  | 331292.9775 |  | 2784853.1 |  | 3202581.065 | [85 empty] | 19206662 | 2880999.3 | 22087661.3 | 4993631.95 | 5742676.7425 |  | 5608345.304 | 614713.354 |  | 4993631.95 | 0
EGEC - NIS3 | [5 empty] | MLTX-01-112 | 19955000 | [104 empty] | 0 | [5 empty] | 0 | 0
EGEC - NIS3 | [111 empty] | 0 | [5 empty] | 0 | 0
EGEC - NIS3 | [111 empty] | 0 | [5 empty] | 0 | 0
EGEC - NIS3 | [117 empty] | 0 | 0
[118 empty] | 0 | 0
[118 empty] | 0 | 0
[118 empty] | 0 | 0
TYPSA- (KHJ-AMIC) | [5 empty] | KHJ2-01-001 | 57332139 | [110 empty] | 0 | 0
TYPSA- (KHJ2-01-001) | [5 empty] | KHJ2-01-001 | 42715823.6 | 2025-11-30 | 857830 | 128674.5 | 986504.5 | [97 empty] | 42715823.6 |  |  | 857830 | 986504.5 |  |  |  |  | 857830 | 0
TYPSA- (KHJ2-01-001) | [111 empty] | 0 | 0 |  |  |  |  | 0 | 0
TYPSA- (KHJ2-01-001) | [111 empty] | 0 | 0 |  |  |  |  | 0 | 0
[112 empty] | 0 | 0 |  |  |  |  | 0 | 0
[112 empty] | 0 | 0 |  |  |  |  | 0 | 0
[9 empty] | 857830 | 128674.5 | 986504.5 | [106 empty] | 857830 | 857830 |  | 0
[118 empty] | 0 | 0 |  | 0
2 | [111 empty] | 0 | [5 empty] | 0 | 0 |  | 0
Prepared By:
PM
EGEC - NIS2 | Saed | Detailed design of connection road (Fly Over) in Dammam 2 | [5 empty] | 2310000
EGEC - NIS2 | Ibrahim |  | Potable water pipeline supply and connection to alkharj 1st ind. City |  |  |  |  | 700000
EGEC - WAS | Malik - Omar | Site development and buildings design for labour community area in WAS industrial city | [5 empty] | 4421850
EGEC - WAS | Shoug | Design commercial area with fuel station in Waad AlShamal | [5 empty] | 650000
Formulas:
Start Date = EDATE(Wrapup[[#This Row],[Finsih Date2]], - 24)

## EGEC - WAS
|  |  |  | Labour community WAS |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4 |  | Invoice 5 |  | Invoice 6
Description |  | Total quantity | Remaining quantity | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity3 | Amount4 | Quantity25 | Amount36 | Amount37 | Amount38 | Amount39 | Amount40 | Amount41 | Amount42
Lead Engineer/ Discipline Engineer | A1 | 670 |  | Lead Engineer/ Discipline Engineer | A1 | 15000 | 13028.1776 | 239 | 1971.8224 | 471265.55 |  |  | 1874.9185 | 448105.53 | 698.229 | 166876.73 | 252.4983 | 60347.09 | 252.5318 | 60355.1
Sr. Engineer/ Senior discipline specialist | B1 | 1050 |  | Sr. Engineer/ Senior discipline specialist | B1 | 16000 | 13149.6429 | 155 | 2850.3571 | 441805.35 |  |  | 2710.2783 | 420093.14 | 1009.3212 | 156444.78 | 364.9975 | 56574.62 | 365.0459 | 56582.12
Engineer/ Discipline Specialist | C1 | 1810 |  | Engineer/ Discipline Specialist | C1 | 16000 | 12446.8151 | 142 | 3553.1849 | 504552.25 |  |  | 3378.5661 | 479756.39 | 1258.1949 | 178663.67 | 454.9969 | 64609.56 | 455.0573 | 64618.13
Draftsman | D1 | 2380 |  | Draftsman | D1 | 17000 | 13407.7692 | 86 | 3592.2308 | 308931.85 |  |  | 3415.6933 | 293749.62 | 1272.0212 | 109393.82 | 459.9969 | 39559.73 | 460.0579 | 39564.98
Lead engineer/ discipline expert | A2 | 9040 | 8904 | Lead engineer/ discipline expert | A2 | [14 empty] | 0
Sr. Engineer/ Senior discipline specialist | B2 | 19600 | #VALUE! | Sr. Engineer/ Senior discipline specialist | B2 | [14 empty] | 0
Engineer/ Discipline Specialist | C2 | 33970 | 31930 | Engineer/ Discipline Specialist | C2 | [14 empty] | 0
Draftsman | D2 | 36820 | 32780 | Draftsman | D2 | [14 empty] | 0
E2/ Project Manager | E2 | 7140 | 3968 | E2/ Project Manager | E2 | [14 empty] | 0
F2/ Project Manager | F2 | 7140 | 829 | F2/ Project Manager | F2 | [14 empty] | 0
[8 empty] | Total | 11967.5952 | 1726555 | 0 | 0 | 11379.4562 | 1641704.68 | 4237.7662 | 611379 |  | 221091 |  | 221120.33
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
|  |  |  | Commercial area |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4 |  | Invoice 5
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity3 | Amount4 | Quantity25 | Amount36 | Amount37 | Amount38
|  |  |  | Lead Engineer/ Discipline Engineer | A1 | 136 | 95.205 | 239 |  |  | 40.795 | 9750 | 47.5941 | 11375 | 47.5941 | 11375
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 | 419 | 293.1935 | 155 |  |  | 125.8065 | 19500 | 146.7742 | 22750 | 146.7742 | 22750
|  |  |  | Engineer/ Discipline Specialist | C1 | 1831 | 1281.7042 | 142 |  |  | 549.2958 | 78000 | 640.8451 | 91000 | 640.8451 | 91000
|  |  |  | Draftsman | D1 | 3401 | 2380.6512 | 86 |  |  | 1020.3488 | 87750 | 1190.407 | 102375 | 1190.407 | 102375
|  |  |  | Lead engineer/ discipline expert | A2 | [8 empty] | 0
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2
|  |  |  | Engineer/ Discipline Specialist | C2
|  |  |  | Draftsman | D2
|  |  |  | E2/ Project Manager | E2
|  |  |  | F2/ Project Manager | F2
[8 empty] | Total |  |  | 1736.246 | 195000 | 2025.6204 | 227500 | 2025.6204 | 227500
|  |  |  | Development of labour camps in: DAM03, NJR, MKH2, JDH2, SUD, ASR1 |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4 |  | Invoice 5 |  | Invoice 7 |  | Invoice 8
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity3 | Amount4 | Quantity25 | Amount36 | quantity4 | amount2 | quantity5 | amount32 | quantity6 | amount33
|  |  |  | Lead Engineer/ Discipline Engineer | A1 | 209 | 209 | 239 | [8 empty] | 22.1 | 5281.9 | 83.64 | 19989.96 | 104.5454 | 24986.36
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 | 639 | 639 | 155 | [8 empty] | 66.2 | 10261 | 255.56 | 39611.8 | 319.4445 | 49513.89
|  |  |  | Engineer/ Discipline Specialist | C1 | 3172 | 3172 | 142 | [8 empty] | 317.0359 | 45019.0978 | 1268.97 | 180193.74 | 2771.6317 | 393571.7
|  |  |  | Draftsman | D1 | 6311 | 6311 | 86 | [8 empty] | 633 | 54438 | 2524.39 | 217097.54 | 1243.3494 | 106928.05
|  |  |  | Lead engineer/ discipline expert | A2 | [12 empty] | 0 |  | 0 | #DIV/0!
|  |  |  | Sr. Engineer/ Senior discipline specialist | B2 | [12 empty] | 0 |  | 0 | #DIV/0!
|  |  |  | Engineer/ Discipline Specialist | C2 | [12 empty] | 0 |  | 0 | 0
|  |  |  | Draftsman | D2 | [12 empty] | 0 |  | 19989.96 | #DIV/0!
|  |  |  | E2/ Project Manager | E2 | [14 empty] | 59601.76 | #DIV/0!
|  |  |  | F2/ Project Manager | F2 | [14 empty] | 239795.5 | #DIV/0!
[8 empty] | Total | [6 empty] | 0 | 0 |  | 114999.9978
[20 empty] | 456893.04 |  | 575000
[20 empty] | 23000 | 96.2343
[18 empty] | 104.5454 |  | 46000 | 296.7742
[18 empty] | 319.4445 |  | 184000 | 1295.7746
[18 empty] | 2771.6317 |  | 207000 | 2406.9767
|  |  |  | Project support services 4 |  |  |  |  | Invoice 9 |  | Invoice 10 | [6 empty] | 1243.3494
|  |  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount
|  |  |  | Lead Engineer/ Discipline Engineer | A1 | 1765 |  | 239 | 588.33 | 140610.87 | 735.42 | 175765.38
|  |  |  | Sr. Engineer/ Senior discipline specialist | B1 | 2787 |  | 155 | 929 | 143995 | 1161.25 | 179993.75
|  |  |  | Engineer/ Discipline Specialist | C1 |  |  | 0
|  |  |  | Draftsman | D1 |  |  | 0
[8 empty] | Total |  | 284606.76 |  | 355759.13
.

## AlDar International
[8 empty] | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4
|  |  | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
|  |  | Lead Engineer/ Discipline Expert | A1 | 440.08 |  | 619 |  |  |  |  | 67.1628 | 41573.7658 | 216.5888 | 134068.4842
|  |  | Sr. Engineer/ Senior discipline specialist | B1 | 586 |  | 475 |  |  |  |  | 89.4486 | 42488.0955 | 288.4038 | 136991.7879
|  |  | Engineer/ Discipline Specialist | C1 | 880 |  | 379 |  |  |  |  | 134.3256 | 50909.3933 | 433.0978 | 164144.0673
|  |  | Draftsman | D1 | 1320 |  | 351 |  |  |  |  | 201.5101 | 70730.0479 | 649.6467 | 228025.9931
|  |  | Lead Engineer/ Discipline Engineer | A2 | 2500 |  | 351 | 802.2162 | 281577.89 | 944.8757 | 281577.89 | 381.6068 | 133943.9696 | 371.3013 | 130326.7686
|  |  | Sr. Engineer/ Senior discipline specialist | B2 | 3000 |  | 303 | 398.4451 | 120728.87 | 469.3013 | 142198.2939 | 457.9281 | 138752.2146 | 1476.4698 | 447370.3555
|  |  | Engineer/ Discipline Specialist | C2 | 4000 |  | 274 | 341.1293 | 93469.43 | 401.7929 | 110091.2546 | 610.5708 | 167296.3995 | 1968.6264 | 539403.627
|  |  | Draftsman | D2 | 6000 |  | 169 | 718.7841 | 121474.51 | 846.6067 | 143076.5323 | 915.8562 | 154779.698 | 2952.9396 | 499046.7863
|  |  | Project Manager | E2 | 3000 |  | 365 | 34.8808 | 12731.49 | 41.0837 | 14995.5505 | 457.9281 | 167143.7569 | 2302.6085 | 840452.1131
|  |  | Project Manager | F2 | 3000 |  | 269 | 108.0587 | 29067.79 | 127.2751 | 34237.0019 | 457.9281 | 123182.6592 | 1476.4698 | 397170.3714
|  |  | TOTAL | [5 empty] | 659049.98 |  | 726176.5232 |  | 1090800.0001 |  | 3517000.3543
Category | Total Quantity | Remaining quantity
A1 | 1500
B1 | 2000
C1 | 3000
D1 | 4500
A2 | 2500
B2 | 3000
C2 | 4000
D2 | 6000
E2 | 3000
F2 | 3000

## Sheet3
Updated concept masterplan & Infrastructure designs for Tabouk ind. City | 4360270 | 100%
Project support services (6 months) (Masterplan) | 744150 | 100%
Project support services (6 months) (VRO) | 744150 | 100%
Testing and evaluating concrete structure | 153002 | 100%
Preliminary designs for the expansion of the industrial city in riyadh | 156177 | 100%
Incubators in Al-Qassim Oasis | 1656100 | 100%
Site development and infrastructure design works for expansion in Jeddah 1 | 2560090 | 100%
Detailed design of connection road (Fly Over) in Dammam 2 | 2310000 | 30%
Labour camp masterplan and infrastructure development in AlKharj | 350000 | 100%
Potable water pipeline supply and connection to alkharj 1st ind. City | 700000 | 30%
Study design RBFs 900 & 450m2 SFDA requirements | 170000 | 100%
Development of labour camps in: DAM03, NJR, MKH2, JDH2, SUD, ASR1 | 1150000 | 5%
Project support services | 1798340 | 0%
Site development and buildings design for labour community area in WAS industrial city | 4421850 | 100%
Design commercial area with fuel station in Waad AlShamal | 650000 | 100%

## TYPSA-KHJ2MIC
Military Industries City in Al Kharj |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4 |  | Invoice 5 |  | Invoice 6 |  | Invoice 7 |  | Invoice 8 |  | Invoice 9 |  | Invoice 10 |  | Invoice 11 |  | Invoice 12 |  | Invoice 13 |  | Invoice 14 |  | Invoice 15 |  | Invoice 16 |  | Invoice 17 |  | Invoice 18 |  | Invoice 19 |  | Invoice 20
Description | Category | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity4 | Amount5 | Quantity6 | Amount7 | Quantity8 | Amount9 | Quantity10 | Amount11 | Quantity12 | Amount13 | Quantity14 | Amount15 | Quantity16 | Amount17 | Quantity18 | Amount19 | Quantity20 | Amount21 | Quantity22 | Amount23 | Quantity24 | Amount25 | Quantity26 | Amount27 | Quantity28 | Amount29 | Quantity30 | Amount31 | Quantity32 | Amount33 | Quantity34 | Amount35 | Quantity36 | Amount37 | Quantity38 | Amount39
Initial Info. Package; Gap Tracker |  | 427775 | 100% | 427775
Rapid Site, Data & Gap Analysis |  | 1711103 |  |  | 50% | 855551.5 | 50% | 855551.5
Military Survey- Methodology |  | 1308994 |  |  | 50% | 654497 | 50% | 654497
Military Survey-Survey Data |  | 1963490
Military Survey-Report & Analysis |  | 3272485.06
Traffic Impact Study |  | 875679.41
Environmental Impact Assmt. |  | 559394
Waste Management Plan |  | 116181.66
Post-Hydrology Study |  | 507769.6
Safety Impact Assessment Report |  | 911450
HCIS Security Report |  | 1367173.49
Data Gathering & Baseline Assmt. |  | 132241.99 |  |  |  |  | 50% | 66120.995 | 50% | 66120.995
Benchmark Successful Cases |  | 66121 |  |  |  |  | 50% | 33060.5 | 50% | 33060.5
Market Assmt. & Demand Forecast |  | 145466.19 |  |  |  |  | 50% | 72733.095 | 50% | 72733.095
Development Scenarios |  | 119017.79 | [6 empty] | 100% | 119017.79
Governance Model |  | 105793.59
Mix of Products & Incentives |  | 119017.79
Business Plan |  | 264483.98
Financial Modelling & Risk Assmt. |  | 264483.98
Inputs to the Master Plan Devt. |  | 105793.59
3 Preliminary Masterplan Options |  | 2724043.45
Fast-Track Concept Master Plan |  | 2292108.71
Pre-Concept Infra. Strategy (Plot) |  | 2566577.57
Concept Infrastructure (F&G) Pre-workshop Submission |  | 2872428
Concept Infrastructure (F&G) |  | 2872428
Initial Devt. Brief Workshop & Appr. |  | 514671 | [8 empty] | 100% | 514671
PPP Model and Roadmap |  | 278780.95
Detailed Master Plan-(F&G) Pre-workshop Submission |  | 2111313
Detailed Master Plan-(F&G) |  | 2111314.21
Enabling Work / Early Package IFT |  | 1126033.92
Detailed Infrastructure 60%-(F&G) |  | 2815084.81
Detailed Infrastructure 100%-(F&G) |  | 3800364.49
IFT Infrastructure-(Only F&G Zones) |  | 1407542.4
Business Plan Project Charter |  | 430055 | 100% | 430055
Final Business Plan per DD Compt. |  | 98912.97
Project Manager |  | 892.5
Master Planner |  | 720
Utilities & Infra. Specialist |  | 720
Quantity Surveyor |  | 600
Contracts Specialist |  | 720
Specifications Specialist |  | 600
Schematic Infra. Design |  | 600
Total |  |  |  | 857830 |  | 1510048.5 |  | 1681963.09 |  | 290932.38 |  | 514671
VAT |  |  |  | 128674.5 |  | 226507.275 |  | 252294.4635 |  | 43639.857 |  | 77200.65
Total WITH VAT |  |  |  | 986504.5 |  | 1736555.775 |  | 1934257.5535 |  | 334572.237 |  | 591871.65

## MEINHARDT
|  |  | Development of Design guidelines, production strategy, and prototype packages for mid-sized RBFs |  |  |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4 |  | Invoice 5 |  | Invoice 6 |  | Invoice 7 |  | Invoice 8 |  | Invoice 9 |  | Invoice 10 |  | Invoice 11 |  | Invoice 12 |  | Invoice 13 |  | Invoice 14 |  | Invoice 15
Category | Total Quantity | Remaining quantity | Description | Category | Total Quantity | Remaining quantity | Rate | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
A1 | 2600 | 1210 | Lead Engineer/ Discipline Engineer | A1 | 1390 |  | 600 | 139.02 | 83412 | 139.02 | 83412 | 278.04 | 166824 | 27.29 | 16374 | 27.29 | 16374 | 27.29 | 16374 | 196.98 | 118188 | 108.4073 | 65044.3632
B1 | 6500 | 4034 | Sr. Engineer/ Senior discipline specialist | B1 | 2466 |  | 460 | 246.587 | 113430 | 246.587 | 113430 | 493.174 | 226860.04 | 68.23 | 31385.8 | 68.23 | 31385.8 | 68.23 | 31385.8 | 455.72 | 209631.2 | 297.1766 | 136701.2199
C1 | 10000 | 9788 | Engineer/ Discipline Specialist | C1 | 212 |  | 360 | 21.1722 | 7622 | 21.1722 | 7622 | 42.344 | 15243.84 | 104.97 | 37789.2 | 104.97 | 37789.2 | 104.97 | 37789.2 | 50 | 18000 | 583.0153 | 209885.5078
D1 | 10000 | 8261 | Draftsman | D1 | 1739 |  | 200 | 173.88 | 34776 | 173.88 | 34776 | 347.76 | 69552 | 104.97 | 20994 | 104.97 | 20994 | 104.97 | 20994 | 739.11 | 147822 | 498.8398 | 99767.9546
E1 | 5000 | 4158 | Project Manager | E1 | 842 |  | 695 | 84.2388 | 58546 | 84.2388 | 58546 | 168.478 | 117092.21 | 52.48 | 36473.6 | 52.48 | 36473.6 | 52.49 | 36480.55 | 103.04 | 71612.8 | 270.2361 | 187814.0888
F1 | 3500 | 3451 | Project Manager | F1 | 49 |  | 390 | 4.941 | 1927 | 4.941 | 1927 | 9.882 | 3853.98 | 36.74 | 14328.6 | 36.74 | 14328.6 | 36.74 | 14328.6 | 10.77 | 4200.3 | 205.2321 | 80040.5272
TOTAL | 37600 |  | TOTAL | [5 empty] | 299713 |  | 299713 |  | 599426.07 |  | 157345.2 |  | 157345.2 |  | 134870.85 |  | 569454.3 |  | 779253.6615

## Dates
Framework ID | Consultant | Date of invoice | Value of invoice
| Dorsch food | 2023-10-26 | 416905
| Dorsch food | 2023-10-26 | 1403611
| Dorsch food | 2023-10-26 | 1377997
| Dorsch food | 2024-03-19 | 682683
| Dorsch food | 2024-04-16 | 368699
| Dorsch food | 2024-04-16 | 1297326
| Dorsch food | 2024-05-23 | 1379810.1
| Dorsch food | 2024-05-23 | 125226
| Dorsch food | 2024-06-08 | 2539503
| Dorsch food | 2024-06-08 | 58000
| Dorsch food | 2024-06-28 | 2062506.53
| Dorsch food | 2024-06-28 | 115999.89
| Dorsch food | 2024-09-02 | 279032
| Dorsch food | 2024-09-05 | 1602086
| Dorsch food | 2024-10-07 | 302500.8
| Dorsch food | 2024-10-07 | 499280
| Dorsch food | 2024-12-24 | 533499.2
| Dorsch food | 2024-12-24 | 264505
| Dorsch food | 2025-02-05 | 500302
| Dorsch food | 2025-03-04 | 255076
| Parsons | 2020-12-22 | #REF!
| Parsons | 2020-12-22 | #REF!
| Parsons | 2020-12-22 | #REF!
| Parsons | 2020-12-22 | #REF!
| Parsons | 2021-04-05 | #REF!
| Parsons | 2021-06-17 | #REF!
| Parsons | 2021-06-17 | #REF!
| Parsons | 2021-06-17 | #REF!
| Parsons | 2022-03-16 | #REF!
| Parsons | 2022-11-14 | #REF!
| Parsons | 2023-01-02 | #REF!
| Parsons | 2023-07-03 | #REF!
| Parsons | 2023-06-14 | #REF!
| Parsons | 2023-06-14 | #REF!
| Parsons | 2023-06-14 | #REF!
| Parsons | 2023-06-14 | #REF!
| Parsons | 2023-10-12 | #REF!
| Parsons | 2023-10-12 | #REF!
| Parsons | 2023-10-12 | #REF!
| Parsons | 2023-10-12 | #REF!
| Parsons | 2023-10-12 | #REF!
| Parsons | 2023-11-20 | #REF!
| Parsons | 2023-11-20 | #REF!
| Parsons | 2023-11-20 | #REF!
| Parsons | 2023-11-20 | #REF!
| Parsons | 2023-11-20 | #REF!
| Parsons | 2023-11-20 | #REF!
| Parsons | 2023-11-20 | #REF!
| Parsons | 2023-12-12 | #REF!
| Parsons | 2024-01-15 | #REF!
| Parsons | 2024-02-27 | 786764.5
| Parsons | 2024-02-27 | #REF!
| Parsons | 2024-03-24 | 2085544
| Parsons | 2024-04-28 | 1163476.5
| Parsons | 2024-06-02 | 600023
| Parsons | 2024-06-02 | 1674941
| Parsons | 2024-06-30 | 657935
| Parsons | 2024-07-28 | 553430
| Parsons | 2024-08-14 | 262152.5
| Parsons | 2024-08-29 | 2295002
| Dar Al Handasah | 2021-06-13 | 495517
| Dar Al Handasah | 2021-06-13 | 111657
| Dar Al Handasah | 2021-06-13 | 418279.5
| Dar Al Handasah | 2021-08-30 | 217982
| Dar Al Handasah | 2021-11-20 | 237379.5
| Dar Al Handasah | 2022-02-06 | 181823
| Dar Al Handasah | 2022-02-06 | 679023
| Dar Al Handasah | 2023-10-09 | 323830
| Dar Al Handasah | 2023-10-23 | 258818
| Dar Al Handasah | 2024-06-30 | 165354.75
| Dar Al Handasah | 2024-07-29 | 413061.5
| DAR Al Riyadh | 2023-02-05 | 514566.67
| DAR Al Riyadh | 2023-02-05 | 500566.67
| DAR Al Riyadh | 2023-03-01 | 685816.67
| DAR Al Riyadh | 2023-03-20 | 918349.94
| DAR Al Riyadh | 2023-03-28 | 1036516.67
| DAR Al Riyadh | 2023-04-11 | 1133966.67
| DAR Al Riyadh | 2023-04-17 | 1203150
| DAR Al Riyadh | 2023-05-22 | 1201600
| DAR Al Riyadh | 2023-06-19 | 1339233.33
| DAR Al Riyadh | 2023-07-19 | 1345166.67
| DAR Al Riyadh | 2023-08-08 | 1193033.33
| DAR Al Riyadh | 2023-09-21 | 1324433.33
| DAR Al Riyadh | 2023-10-23 | 1300700
| DAR Al Riyadh | 2023-11-19 | 1311066.67
| DAR Al Riyadh | 2023-12-06 | 1331150
| DAR Al Riyadh | 2024-01-23 | 1279800
| DAR Al Riyadh | 2024-02-13 | 1090316.67
| DAR Al Riyadh | 2024-02-29 | 1156216.67
| DAR Al Riyadh | 2024-04-02 | 1097216.67
| DAR Al Riyadh | 2024-05-12 | 1061966.67
| DAR Al Riyadh | 2024-06-05 | 1052866.67
| DAR Al Riyadh | 2024-07-07 | 993666.67
| DAR Al Riyadh | 2024-08-14 | 930183.33
| DAR Al Riyadh | 2024-09-03 | 949500
| EGEC - NIS2 | 2024-07-23 | 1395290.5
| EGEC - NIS2 | 2024-08-28 | 1874916.39
| EGEC - NIS2 | 2024-08-28 | 372075
| EGEC - NIS2 | 2024-08-28 | 107101.54
| EGEC - NIS2 | 2024-10-21 | 45900.66
| EGEC - NIS2 | 2024-10-21 | 109323.9
| EGEC - NIS2 | 2024-10-31 | 372075
| EGEC - NIS2 | 2024-11-30 | 872049.61
| EGEC - NIS2 | 2024-11-30 | 46853.1
| EGEC - NIS2 | 2024-11-30 | 248415
| EGEC - NIS2 | 2024-12-25 | 218013.5
| EGEC - NIS2 | 2024-12-25 | 828050
| EGEC - NIS2 | 2025-01-31 | 372075
| EGEC - NIS2 | 2025-01-31 | 579635
| EGEC - NIS2 | 2025-01-31 | 384013.5
| EGEC - NIS2 | 2025-03-02 | 175000
| ENGICON | 2024-07-07 | 2361050.1
| ENGICON | 2024-08-07 | 3157746.66
| ENGICON | 2024-08-31 | 3983985.909
| ENGICON | 2024-10-02 | 3449998.296
| ENGICON | 2024-12-10 | 1820099.709
| ENGICON | 2025-01-28 | 999999.999
| SYSTRA | 2024-07-31 | 672697.82
| SYSTRA | 2024-08-07 | 1681772
| SYSTRA | 2024-12-15 | 1345449

## Calendar
DA TES 2020-2025
2020-01-01
2020-01-02
2020-01-03
2020-01-04
2020-01-05
2020-01-06
2020-01-07
2020-01-08
2020-01-09
2020-01-10
2020-01-11
2020-01-12
2020-01-13
2020-01-14
2020-01-15
2020-01-16
2020-01-17
2020-01-18
2020-01-19
2020-01-20
2020-01-21
2020-01-22
2020-01-23
2020-01-24
2020-01-25
2020-01-26
2020-01-27
2020-01-28
2020-01-29
2020-01-30
2020-01-31
2020-02-01
2020-02-02
2020-02-03
2020-02-04
2020-02-05
2020-02-06
2020-02-07
2020-02-08
2020-02-09
2020-02-10
2020-02-11
2020-02-12
2020-02-13
2020-02-14
2020-02-15
2020-02-16
2020-02-17
2020-02-18
2020-02-19
2020-02-20
2020-02-21
2020-02-22
2020-02-23
2020-02-24
2020-02-25
2020-02-26
2020-02-27
2020-02-28
2020-02-29
2020-03-01
2020-03-02
2020-03-03
2020-03-04
2020-03-05
2020-03-06
2020-03-07
2020-03-08
2020-03-09
2020-03-10
2020-03-11
2020-03-12
2020-03-13
2020-03-14
2020-03-15
2020-03-16
2020-03-17
2020-03-18
2020-03-19
2020-03-20
2020-03-21
2020-03-22
2020-03-23
2020-03-24
2020-03-25
2020-03-26
2020-03-27
2020-03-28
2020-03-29
2020-03-30
2020-03-31
2020-04-01
2020-04-02
2020-04-03
2020-04-04
2020-04-05
2020-04-06
2020-04-07
2020-04-08
2020-04-09
2020-04-10
2020-04-11
2020-04-12
2020-04-13
2020-04-14
2020-04-15
2020-04-16
2020-04-17
2020-04-18
2020-04-19
2020-04-20
2020-04-21
2020-04-22
2020-04-23
2020-04-24
2020-04-25
2020-04-26
2020-04-27
2020-04-28
2020-04-29
2020-04-30
2020-05-01
2020-05-02
2020-05-03
2020-05-04
2020-05-05
2020-05-06
2020-05-07
2020-05-08
2020-05-09
2020-05-10
2020-05-11
2020-05-12
2020-05-13
2020-05-14
2020-05-15
2020-05-16
2020-05-17
2020-05-18
2020-05-19
2020-05-20
2020-05-21
2020-05-22
2020-05-23
2020-05-24
2020-05-25
2020-05-26
2020-05-27
2020-05-28
2020-05-29
2020-05-30
2020-05-31
2020-06-01
2020-06-02
2020-06-03
2020-06-04
2020-06-05
2020-06-06
2020-06-07
2020-06-08
2020-06-09
2020-06-10
2020-06-11
2020-06-12
2020-06-13
2020-06-14
2020-06-15
2020-06-16
2020-06-17
2020-06-18
2020-06-19
2020-06-20
2020-06-21
2020-06-22
2020-06-23
2020-06-24
2020-06-25
2020-06-26
2020-06-27
2020-06-28
2020-06-29
2020-06-30
2020-07-01
2020-07-02
2020-07-03
2020-07-04
2020-07-05
2020-07-06
2020-07-07
2020-07-08
2020-07-09
2020-07-10
2020-07-11
2020-07-12
2020-07-13
2020-07-14
2020-07-15
2020-07-16
2020-07-17
2020-07-18
2020-07-19
2020-07-20
2020-07-21
2020-07-22
2020-07-23
2020-07-24
2020-07-25
2020-07-26
2020-07-27
2020-07-28
2020-07-29
2020-07-30
2020-07-31
2020-08-01
2020-08-02
2020-08-03
2020-08-04
2020-08-05
2020-08-06
2020-08-07
2020-08-08
2020-08-09
2020-08-10
2020-08-11
2020-08-12
2020-08-13
2020-08-14
2020-08-15
2020-08-16
2020-08-17
2020-08-18
2020-08-19
2020-08-20
2020-08-21
2020-08-22
2020-08-23
2020-08-24
2020-08-25
2020-08-26
2020-08-27
2020-08-28
2020-08-29
2020-08-30
2020-08-31
2020-09-01
2020-09-02
2020-09-03
2020-09-04
2020-09-05
2020-09-06
2020-09-07
2020-09-08
2020-09-09
2020-09-10
2020-09-11
2020-09-12
2020-09-13
2020-09-14
2020-09-15
2020-09-16
2020-09-17
2020-09-18
2020-09-19
2020-09-20
2020-09-21
2020-09-22
2020-09-23
2020-09-24
2020-09-25
2020-09-26
2020-09-27
2020-09-28
2020-09-29
2020-09-30
2020-10-01
2020-10-02
2020-10-03
2020-10-04
2020-10-05
2020-10-06
2020-10-07
2020-10-08
2020-10-09
2020-10-10
2020-10-11
2020-10-12
2020-10-13
2020-10-14
2020-10-15
2020-10-16
2020-10-17
2020-10-18
2020-10-19
2020-10-20
2020-10-21
2020-10-22
2020-10-23
2020-10-24
2020-10-25
2020-10-26
2020-10-27
2020-10-28
2020-10-29
2020-10-30
2020-10-31
2020-11-01
2020-11-02
2020-11-03
2020-11-04
2020-11-05
2020-11-06
2020-11-07
2020-11-08
2020-11-09
2020-11-10
2020-11-11
2020-11-12
2020-11-13
2020-11-14
2020-11-15
2020-11-16
2020-11-17
2020-11-18
2020-11-19
2020-11-20
2020-11-21
2020-11-22
2020-11-23
2020-11-24
2020-11-25
2020-11-26
2020-11-27
2020-11-28
2020-11-29
2020-11-30
2020-12-01
2020-12-02
2020-12-03
2020-12-04
2020-12-05
2020-12-06
2020-12-07
2020-12-08
2020-12-09
2020-12-10
2020-12-11
2020-12-12
2020-12-13
2020-12-14
2020-12-15
2020-12-16
2020-12-17
2020-12-18
2020-12-19
2020-12-20
2020-12-21
2020-12-22
2020-12-23
2020-12-24
2020-12-25
2020-12-26
2020-12-27
2020-12-28
2020-12-29
2020-12-30
2020-12-31
2021-01-01
2021-01-02
2021-01-03
2021-01-04
2021-01-05
2021-01-06
2021-01-07
2021-01-08
2021-01-09
2021-01-10
2021-01-11
2021-01-12
2021-01-13
2021-01-14
2021-01-15
2021-01-16
2021-01-17
2021-01-18
2021-01-19
2021-01-20
2021-01-21
2021-01-22
2021-01-23
2021-01-24
2021-01-25
2021-01-26
2021-01-27
2021-01-28
2021-01-29
2021-01-30
2021-01-31
2021-02-01
2021-02-02
2021-02-03
2021-02-04
2021-02-05
2021-02-06
2021-02-07
2021-02-08
2021-02-09
2021-02-10
2021-02-11
2021-02-12
2021-02-13
2021-02-14
2021-02-15
2021-02-16
2021-02-17
2021-02-18
2021-02-19
2021-02-20
2021-02-21
2021-02-22
2021-02-23
2021-02-24
2021-02-25
2021-02-26
2021-02-27
2021-02-28
2021-03-01
2021-03-02
2021-03-03
2021-03-04
2021-03-05
2021-03-06
2021-03-07
2021-03-08
2021-03-09
2021-03-10
2021-03-11
2021-03-12
2021-03-13
2021-03-14
2021-03-15
2021-03-16
2021-03-17
2021-03-18
2021-03-19
2021-03-20
2021-03-21
2021-03-22
2021-03-23
2021-03-24
2021-03-25
2021-03-26
2021-03-27
2021-03-28
2021-03-29
2021-03-30
2021-03-31
2021-04-01
2021-04-02
2021-04-03
2021-04-04
2021-04-05
2021-04-06
2021-04-07
2021-04-08
2021-04-09
2021-04-10
2021-04-11
2021-04-12
2021-04-13
2021-04-14
2021-04-15
2021-04-16
2021-04-17
2021-04-18
2021-04-19
2021-04-20
2021-04-21
2021-04-22
2021-04-23
2021-04-24
2021-04-25
2021-04-26
2021-04-27
2021-04-28
2021-04-29
2021-04-30
2021-05-01
2021-05-02
2021-05-03
2021-05-04
2021-05-05
2021-05-06
2021-05-07
2021-05-08
2021-05-09
2021-05-10
2021-05-11
2021-05-12
2021-05-13
2021-05-14
2021-05-15
2021-05-16
2021-05-17
2021-05-18
2021-05-19
2021-05-20
2021-05-21
2021-05-22
2021-05-23
2021-05-24
2021-05-25
2021-05-26
2021-05-27
2021-05-28
2021-05-29
2021-05-30
2021-05-31
2021-06-01
2021-06-02
2021-06-03
2021-06-04
2021-06-05
2021-06-06
2021-06-07
2021-06-08
2021-06-09
2021-06-10
2021-06-11
2021-06-12
2021-06-13
2021-06-14
2021-06-15
2021-06-16
2021-06-17
2021-06-18
2021-06-19
2021-06-20
2021-06-21
2021-06-22
2021-06-23
2021-06-24
2021-06-25
2021-06-26
2021-06-27
2021-06-28
2021-06-29
2021-06-30
2021-07-01
2021-07-02
2021-07-03
2021-07-04
2021-07-05
2021-07-06
2021-07-07
2021-07-08
2021-07-09
2021-07-10
2021-07-11
2021-07-12
2021-07-13
2021-07-14
2021-07-15
2021-07-16
2021-07-17
2021-07-18
2021-07-19
2021-07-20
2021-07-21
2021-07-22
2021-07-23
2021-07-24
2021-07-25
2021-07-26
2021-07-27
2021-07-28
2021-07-29
2021-07-30
2021-07-31
2021-08-01
2021-08-02
2021-08-03
2021-08-04
2021-08-05
2021-08-06
2021-08-07
2021-08-08
2021-08-09
2021-08-10
2021-08-11
2021-08-12
2021-08-13
2021-08-14
2021-08-15
2021-08-16
2021-08-17
2021-08-18
2021-08-19
2021-08-20
2021-08-21
2021-08-22
2021-08-23
2021-08-24
2021-08-25
2021-08-26
2021-08-27
2021-08-28
2021-08-29
2021-08-30
2021-08-31
2021-09-01
2021-09-02
2021-09-03
2021-09-04
2021-09-05
2021-09-06
2021-09-07
2021-09-08
2021-09-09
2021-09-10
2021-09-11
2021-09-12
2021-09-13
2021-09-14
2021-09-15
2021-09-16
2021-09-17
2021-09-18
2021-09-19
2021-09-20
2021-09-21
2021-09-22
2021-09-23
2021-09-24
2021-09-25
2021-09-26
2021-09-27
2021-09-28
2021-09-29
2021-09-30
2021-10-01
2021-10-02
2021-10-03
2021-10-04
2021-10-05
2021-10-06
2021-10-07
2021-10-08
2021-10-09
2021-10-10
2021-10-11
2021-10-12
2021-10-13
2021-10-14
2021-10-15
2021-10-16
2021-10-17
2021-10-18
2021-10-19
2021-10-20
2021-10-21
2021-10-22
2021-10-23
2021-10-24
2021-10-25
2021-10-26
2021-10-27
2021-10-28
2021-10-29
2021-10-30
2021-10-31
2021-11-01
2021-11-02
2021-11-03
2021-11-04
2021-11-05
2021-11-06
2021-11-07
2021-11-08
2021-11-09
2021-11-10
2021-11-11
2021-11-12
2021-11-13
2021-11-14
2021-11-15
2021-11-16
2021-11-17
2021-11-18
2021-11-19
2021-11-20
2021-11-21
2021-11-22
2021-11-23
2021-11-24
2021-11-25
2021-11-26
2021-11-27
2021-11-28
2021-11-29
2021-11-30
2021-12-01
2021-12-02
2021-12-03
2021-12-04
2021-12-05
2021-12-06
2021-12-07
2021-12-08
2021-12-09
2021-12-10
2021-12-11
2021-12-12
2021-12-13
2021-12-14
2021-12-15
2021-12-16
2021-12-17
2021-12-18
2021-12-19
2021-12-20
2021-12-21
2021-12-22
2021-12-23
2021-12-24
2021-12-25
2021-12-26
2021-12-27
2021-12-28
2021-12-29
2021-12-30
2021-12-31
2022-01-01
2022-01-02
2022-01-03
2022-01-04
2022-01-05
2022-01-06
2022-01-07
2022-01-08
2022-01-09
2022-01-10
2022-01-11
2022-01-12
2022-01-13
2022-01-14
2022-01-15
2022-01-16
2022-01-17
2022-01-18
2022-01-19
2022-01-20
2022-01-21
2022-01-22
2022-01-23
2022-01-24
2022-01-25
2022-01-26
2022-01-27
2022-01-28
2022-01-29
2022-01-30
2022-01-31
2022-02-01
2022-02-02
2022-02-03
2022-02-04
2022-02-05
2022-02-06
2022-02-07
2022-02-08
2022-02-09
2022-02-10
2022-02-11
2022-02-12
2022-02-13
2022-02-14
2022-02-15
2022-02-16
2022-02-17
2022-02-18
2022-02-19
2022-02-20
2022-02-21
2022-02-22
2022-02-23
2022-02-24
2022-02-25
2022-02-26
2022-02-27
2022-02-28
2022-03-01
2022-03-02
2022-03-03
2022-03-04
2022-03-05
2022-03-06
2022-03-07
2022-03-08
2022-03-09
2022-03-10
2022-03-11
2022-03-12
2022-03-13
2022-03-14
2022-03-15
2022-03-16
2022-03-17
2022-03-18
2022-03-19
2022-03-20
2022-03-21
2022-03-22
2022-03-23
2022-03-24
2022-03-25
2022-03-26
2022-03-27
2022-03-28
2022-03-29
2022-03-30
2022-03-31
2022-04-01
2022-04-02
2022-04-03
2022-04-04
2022-04-05
2022-04-06
2022-04-07
2022-04-08
2022-04-09
2022-04-10
2022-04-11
2022-04-12
2022-04-13
2022-04-14
2022-04-15
2022-04-16
2022-04-17
2022-04-18
2022-04-19
2022-04-20
2022-04-21
2022-04-22
2022-04-23
2022-04-24
2022-04-25
2022-04-26
2022-04-27
2022-04-28
2022-04-29
2022-04-30
2022-05-01
2022-05-02
2022-05-03
2022-05-04
2022-05-05
2022-05-06
2022-05-07
2022-05-08
2022-05-09
2022-05-10
2022-05-11
2022-05-12
2022-05-13
2022-05-14
2022-05-15
2022-05-16
2022-05-17
2022-05-18
2022-05-19
2022-05-20
2022-05-21
2022-05-22
2022-05-23
2022-05-24
2022-05-25
2022-05-26
2022-05-27
2022-05-28
2022-05-29
2022-05-30
2022-05-31
2022-06-01
2022-06-02
2022-06-03
2022-06-04
2022-06-05
2022-06-06
2022-06-07
2022-06-08
2022-06-09
2022-06-10
2022-06-11
2022-06-12
2022-06-13
2022-06-14
2022-06-15
2022-06-16
2022-06-17
2022-06-18
2022-06-19
2022-06-20
2022-06-21
2022-06-22
2022-06-23
2022-06-24
2022-06-25
2022-06-26
2022-06-27
2022-06-28
2022-06-29
2022-06-30
2022-07-01
2022-07-02
2022-07-03
2022-07-04
2022-07-05
2022-07-06
2022-07-07
2022-07-08
2022-07-09
2022-07-10
2022-07-11
2022-07-12
2022-07-13
2022-07-14
2022-07-15
2022-07-16
2022-07-17
2022-07-18
2022-07-19
2022-07-20
2022-07-21
2022-07-22
2022-07-23
2022-07-24
2022-07-25
2022-07-26
2022-07-27
2022-07-28
2022-07-29
2022-07-30
2022-07-31
2022-08-01
2022-08-02
2022-08-03
2022-08-04
2022-08-05
2022-08-06
2022-08-07
2022-08-08
2022-08-09
2022-08-10
2022-08-11
2022-08-12
2022-08-13
2022-08-14
2022-08-15
2022-08-16
2022-08-17
2022-08-18
2022-08-19
2022-08-20
2022-08-21
2022-08-22
2022-08-23
2022-08-24
2022-08-25
2022-08-26
2022-08-27
2022-08-28
2022-08-29
2022-08-30
2022-08-31
2022-09-01
2022-09-02
2022-09-03
2022-09-04
2022-09-05
2022-09-06
2022-09-07
2022-09-08
2022-09-09
2022-09-10
2022-09-11
2022-09-12
2022-09-13
2022-09-14
2022-09-15
2022-09-16
2022-09-17
2022-09-18
2022-09-19
2022-09-20
2022-09-21
2022-09-22
2022-09-23
2022-09-24
2022-09-25
2022-09-26
2022-09-27
2022-09-28
2022-09-29
2022-09-30
2022-10-01
2022-10-02
2022-10-03
2022-10-04
2022-10-05
2022-10-06
2022-10-07
2022-10-08
2022-10-09
2022-10-10
2022-10-11
2022-10-12
2022-10-13
2022-10-14
2022-10-15
2022-10-16
2022-10-17
2022-10-18
2022-10-19
2022-10-20
2022-10-21
2022-10-22
2022-10-23
2022-10-24
2022-10-25
2022-10-26
2022-10-27
2022-10-28
2022-10-29
2022-10-30
2022-10-31
2022-11-01
2022-11-02
2022-11-03
2022-11-04
2022-11-05
2022-11-06
2022-11-07
2022-11-08
2022-11-09
2022-11-10
2022-11-11
2022-11-12
2022-11-13
2022-11-14
2022-11-15
2022-11-16
2022-11-17
2022-11-18
2022-11-19
2022-11-20
2022-11-21
2022-11-22
2022-11-23
2022-11-24
2022-11-25
2022-11-26
2022-11-27
2022-11-28
2022-11-29
2022-11-30
2022-12-01
2022-12-02
2022-12-03
2022-12-04
2022-12-05
2022-12-06
2022-12-07
2022-12-08
2022-12-09
2022-12-10
2022-12-11
2022-12-12
2022-12-13
2022-12-14
2022-12-15
2022-12-16
2022-12-17
2022-12-18
2022-12-19
2022-12-20
2022-12-21
2022-12-22
2022-12-23
2022-12-24
2022-12-25
2022-12-26
2022-12-27
2022-12-28
2022-12-29
2022-12-30
2022-12-31
2023-01-01
2023-01-02
2023-01-03
2023-01-04
2023-01-05
2023-01-06
2023-01-07
2023-01-08
2023-01-09
2023-01-10
2023-01-11
2023-01-12
2023-01-13
2023-01-14
2023-01-15
2023-01-16
2023-01-17
2023-01-18
2023-01-19
2023-01-20
2023-01-21
2023-01-22
2023-01-23
2023-01-24
2023-01-25
2023-01-26
2023-01-27
2023-01-28
2023-01-29
2023-01-30
2023-01-31
2023-02-01
2023-02-02
2023-02-03
2023-02-04
2023-02-05
2023-02-06
2023-02-07
2023-02-08
2023-02-09
2023-02-10
2023-02-11
2023-02-12
2023-02-13
2023-02-14
2023-02-15
2023-02-16
2023-02-17
2023-02-18
2023-02-19
2023-02-20
2023-02-21
2023-02-22
2023-02-23
2023-02-24
2023-02-25
2023-02-26
2023-02-27
2023-02-28
2023-03-01
2023-03-02
2023-03-03
2023-03-04
2023-03-05
2023-03-06
2023-03-07
2023-03-08
2023-03-09
2023-03-10
2023-03-11
2023-03-12
2023-03-13
2023-03-14
2023-03-15
2023-03-16
2023-03-17
2023-03-18
2023-03-19
2023-03-20
2023-03-21
2023-03-22
2023-03-23
2023-03-24
2023-03-25
2023-03-26
2023-03-27
2023-03-28
2023-03-29
2023-03-30
2023-03-31
2023-04-01
2023-04-02
2023-04-03
2023-04-04
2023-04-05
2023-04-06
2023-04-07
2023-04-08
2023-04-09
2023-04-10
2023-04-11
2023-04-12
2023-04-13
2023-04-14
2023-04-15
2023-04-16
2023-04-17
2023-04-18
2023-04-19
2023-04-20
2023-04-21
2023-04-22
2023-04-23
2023-04-24
2023-04-25
2023-04-26
2023-04-27
2023-04-28
2023-04-29
2023-04-30
2023-05-01
2023-05-02
2023-05-03
2023-05-04
2023-05-05
2023-05-06
2023-05-07
2023-05-08
2023-05-09
2023-05-10
2023-05-11
2023-05-12
2023-05-13
2023-05-14
2023-05-15
2023-05-16
2023-05-17
2023-05-18
2023-05-19
2023-05-20
2023-05-21
2023-05-22
2023-05-23
2023-05-24
2023-05-25
2023-05-26
2023-05-27
2023-05-28
2023-05-29
2023-05-30
2023-05-31
2023-06-01
2023-06-02
2023-06-03
2023-06-04
2023-06-05
2023-06-06
2023-06-07
2023-06-08
2023-06-09
2023-06-10
2023-06-11
2023-06-12
2023-06-13
2023-06-14
2023-06-15
2023-06-16
2023-06-17
2023-06-18
2023-06-19
2023-06-20
2023-06-21
2023-06-22
2023-06-23
2023-06-24
2023-06-25
2023-06-26
2023-06-27
2023-06-28
2023-06-29
2023-06-30
2023-07-01
2023-07-02
2023-07-03
2023-07-04
2023-07-05
2023-07-06
2023-07-07
2023-07-08
2023-07-09
2023-07-10
2023-07-11
2023-07-12
2023-07-13
2023-07-14
2023-07-15
2023-07-16
2023-07-17
2023-07-18
2023-07-19
2023-07-20
2023-07-21
2023-07-22
2023-07-23
2023-07-24
2023-07-25
2023-07-26
2023-07-27
2023-07-28
2023-07-29
2023-07-30
2023-07-31
2023-08-01
2023-08-02
2023-08-03
2023-08-04
2023-08-05
2023-08-06
2023-08-07
2023-08-08
2023-08-09
2023-08-10
2023-08-11
2023-08-12
2023-08-13
2023-08-14
2023-08-15
2023-08-16
2023-08-17
2023-08-18
2023-08-19
2023-08-20
2023-08-21
2023-08-22
2023-08-23
2023-08-24
2023-08-25
2023-08-26
2023-08-27
2023-08-28
2023-08-29
2023-08-30
2023-08-31
2023-09-01
2023-09-02
2023-09-03
2023-09-04
2023-09-05
2023-09-06
2023-09-07
2023-09-08
2023-09-09
2023-09-10
2023-09-11
2023-09-12
2023-09-13
2023-09-14
2023-09-15
2023-09-16
2023-09-17
2023-09-18
2023-09-19
2023-09-20
2023-09-21
2023-09-22
2023-09-23
2023-09-24
2023-09-25
2023-09-26
2023-09-27
2023-09-28
2023-09-29
2023-09-30
2023-10-01
2023-10-02
2023-10-03
2023-10-04
2023-10-05
2023-10-06
2023-10-07
2023-10-08
2023-10-09
2023-10-10
2023-10-11
2023-10-12
2023-10-13
2023-10-14
2023-10-15
2023-10-16
2023-10-17
2023-10-18
2023-10-19
2023-10-20
2023-10-21
2023-10-22
2023-10-23
2023-10-24
2023-10-25
2023-10-26
2023-10-27
2023-10-28
2023-10-29
2023-10-30
2023-10-31
2023-11-01
2023-11-02
2023-11-03
2023-11-04
2023-11-05
2023-11-06
2023-11-07
2023-11-08
2023-11-09
2023-11-10
2023-11-11
2023-11-12
2023-11-13
2023-11-14
2023-11-15
2023-11-16
2023-11-17
2023-11-18
2023-11-19
2023-11-20
2023-11-21
2023-11-22
2023-11-23
2023-11-24
2023-11-25
2023-11-26
2023-11-27
2023-11-28
2023-11-29
2023-11-30
2023-12-01
2023-12-02
2023-12-03
2023-12-04
2023-12-05
2023-12-06
2023-12-07
2023-12-08
2023-12-09
2023-12-10
2023-12-11
2023-12-12
2023-12-13
2023-12-14
2023-12-15
2023-12-16
2023-12-17
2023-12-18
2023-12-19
2023-12-20
2023-12-21
2023-12-22
2023-12-23
2023-12-24
2023-12-25
2023-12-26
2023-12-27
2023-12-28
2023-12-29
2023-12-30
2023-12-31
2024-01-01
2024-01-02
2024-01-03
2024-01-04
2024-01-05
2024-01-06
2024-01-07
2024-01-08
2024-01-09
2024-01-10
2024-01-11
2024-01-12
2024-01-13
2024-01-14
2024-01-15
2024-01-16
2024-01-17
2024-01-18
2024-01-19
2024-01-20
2024-01-21
2024-01-22
2024-01-23
2024-01-24
2024-01-25
2024-01-26
2024-01-27
2024-01-28
2024-01-29
2024-01-30
2024-01-31
2024-02-01
2024-02-02
2024-02-03
2024-02-04
2024-02-05
2024-02-06
2024-02-07
2024-02-08
2024-02-09
2024-02-10
2024-02-11
2024-02-12
2024-02-13
2024-02-14
2024-02-15
2024-02-16
2024-02-17
2024-02-18
2024-02-19
2024-02-20
2024-02-21
2024-02-22
2024-02-23
2024-02-24
2024-02-25
2024-02-26
2024-02-27
2024-02-28
2024-02-29
2024-03-01
2024-03-02
2024-03-03
2024-03-04
2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10
2024-03-11
2024-03-12
2024-03-13
2024-03-14
2024-03-15
2024-03-16
2024-03-17
2024-03-18
2024-03-19
2024-03-20
2024-03-21
2024-03-22
2024-03-23
2024-03-24
2024-03-25
2024-03-26
2024-03-27
2024-03-28
2024-03-29
2024-03-30
2024-03-31
2024-04-01
2024-04-02
2024-04-03
2024-04-04
2024-04-05
2024-04-06
2024-04-07
2024-04-08
2024-04-09
2024-04-10
2024-04-11
2024-04-12
2024-04-13
2024-04-14
2024-04-15
2024-04-16
2024-04-17
2024-04-18
2024-04-19
2024-04-20
2024-04-21
2024-04-22
2024-04-23
2024-04-24
2024-04-25
2024-04-26
2024-04-27
2024-04-28
2024-04-29
2024-04-30
2024-05-01
2024-05-02
2024-05-03
2024-05-04
2024-05-05
2024-05-06
2024-05-07
2024-05-08
2024-05-09
2024-05-10
2024-05-11
2024-05-12
2024-05-13
2024-05-14
2024-05-15
2024-05-16
2024-05-17
2024-05-18
2024-05-19
2024-05-20
2024-05-21
2024-05-22
2024-05-23
2024-05-24
2024-05-25
2024-05-26
2024-05-27
2024-05-28
2024-05-29
2024-05-30
2024-05-31
2024-06-01
2024-06-02
2024-06-03
2024-06-04
2024-06-05
2024-06-06
2024-06-07
2024-06-08
2024-06-09
2024-06-10
2024-06-11
2024-06-12
2024-06-13
2024-06-14
2024-06-15
2024-06-16
2024-06-17
2024-06-18
2024-06-19
2024-06-20
2024-06-21
2024-06-22
2024-06-23
2024-06-24
2024-06-25
2024-06-26
2024-06-27
2024-06-28
2024-06-29
2024-06-30
2024-07-01
2024-07-02
2024-07-03
2024-07-04
2024-07-05
2024-07-06
2024-07-07
2024-07-08
2024-07-09
2024-07-10
2024-07-11
2024-07-12
2024-07-13
2024-07-14
2024-07-15
2024-07-16
2024-07-17
2024-07-18
2024-07-19
2024-07-20
2024-07-21
2024-07-22
2024-07-23
2024-07-24
2024-07-25
2024-07-26
2024-07-27
2024-07-28
2024-07-29
2024-07-30
2024-07-31
2024-08-01
2024-08-02
2024-08-03
2024-08-04
2024-08-05
2024-08-06
2024-08-07
2024-08-08
2024-08-09
2024-08-10
2024-08-11
2024-08-12
2024-08-13
2024-08-14
2024-08-15
2024-08-16
2024-08-17
2024-08-18
2024-08-19
2024-08-20
2024-08-21
2024-08-22
2024-08-23
2024-08-24
2024-08-25
2024-08-26
2024-08-27
2024-08-28
2024-08-29
2024-08-30
2024-08-31
2024-09-01
2024-09-02
2024-09-03
2024-09-04
2024-09-05
2024-09-06
2024-09-07
2024-09-08
2024-09-09
2024-09-10
2024-09-11
2024-09-12
2024-09-13
2024-09-14
2024-09-15
2024-09-16
2024-09-17
2024-09-18
2024-09-19
2024-09-20
2024-09-21
2024-09-22
2024-09-23
2024-09-24
2024-09-25
2024-09-26
2024-09-27
2024-09-28
2024-09-29
2024-09-30
2024-10-01
2024-10-02
2024-10-03
2024-10-04
2024-10-05
2024-10-06
2024-10-07
2024-10-08
2024-10-09
2024-10-10
2024-10-11
2024-10-12
2024-10-13
2024-10-14
2024-10-15
2024-10-16
2024-10-17
2024-10-18
2024-10-19
2024-10-20
2024-10-21
2024-10-22
2024-10-23
2024-10-24
2024-10-25
2024-10-26
2024-10-27
2024-10-28
2024-10-29
2024-10-30
2024-10-31
2024-11-01
2024-11-02
2024-11-03
2024-11-04
2024-11-05
2024-11-06
2024-11-07
2024-11-08
2024-11-09
2024-11-10
2024-11-11
2024-11-12
2024-11-13
2024-11-14
2024-11-15
2024-11-16
2024-11-17
2024-11-18
2024-11-19
2024-11-20
2024-11-21
2024-11-22
2024-11-23
2024-11-24
2024-11-25
2024-11-26
2024-11-27
2024-11-28
2024-11-29
2024-11-30
2024-12-01
2024-12-02
2024-12-03
2024-12-04
2024-12-05
2024-12-06
2024-12-07
2024-12-08
2024-12-09
2024-12-10
2024-12-11
2024-12-12
2024-12-13
2024-12-14
2024-12-15
2024-12-16
2024-12-17
2024-12-18
2024-12-19
2024-12-20
2024-12-21
2024-12-22
2024-12-23
2024-12-24
2024-12-25
2024-12-26
2024-12-27
2024-12-28
2024-12-29
2024-12-30
2024-12-31
2025-01-01
2025-01-02
2025-01-03
2025-01-04
2025-01-05
2025-01-06
2025-01-07
2025-01-08
2025-01-09
2025-01-10
2025-01-11
2025-01-12
2025-01-13
2025-01-14
2025-01-15
2025-01-16
2025-01-17
2025-01-18
2025-01-19
2025-01-20
2025-01-21
2025-01-22
2025-01-23
2025-01-24
2025-01-25
2025-01-26
2025-01-27
2025-01-28
2025-01-29
2025-01-30
2025-01-31
2025-02-01
2025-02-02
2025-02-03
2025-02-04
2025-02-05
2025-02-06
2025-02-07
2025-02-08
2025-02-09
2025-02-10
2025-02-11
2025-02-12
2025-02-13
2025-02-14
2025-02-15
2025-02-16
2025-02-17
2025-02-18
2025-02-19
2025-02-20
2025-02-21
2025-02-22
2025-02-23
2025-02-24
2025-02-25
2025-02-26
2025-02-27
2025-02-28
2025-03-01
2025-03-02
2025-03-03
2025-03-04
2025-03-05
2025-03-06
2025-03-07
2025-03-08
2025-03-09
2025-03-10
2025-03-11
2025-03-12
2025-03-13
2025-03-14
2025-03-15
2025-03-16
2025-03-17
2025-03-18
2025-03-19
2025-03-20
2025-03-21
2025-03-22
2025-03-23
2025-03-24
2025-03-25
2025-03-26
2025-03-27
2025-03-28
2025-03-29
2025-03-30
2025-03-31
2025-04-01
2025-04-02
2025-04-03
2025-04-04
2025-04-05
2025-04-06
2025-04-07
2025-04-08
2025-04-09
2025-04-10
2025-04-11
2025-04-12
2025-04-13
2025-04-14
2025-04-15
2025-04-16
2025-04-17
2025-04-18
2025-04-19
2025-04-20
2025-04-21
2025-04-22
2025-04-23
2025-04-24
2025-04-25
2025-04-26
2025-04-27
2025-04-28
2025-04-29
2025-04-30
2025-05-01
2025-05-02
2025-05-03
2025-05-04
2025-05-05
2025-05-06
2025-05-07
2025-05-08
2025-05-09
2025-05-10
2025-05-11
2025-05-12
2025-05-13
2025-05-14
2025-05-15
2025-05-16
2025-05-17
2025-05-18
2025-05-19
2025-05-20
2025-05-21
2025-05-22
2025-05-23
2025-05-24
2025-05-25
2025-05-26
2025-05-27
2025-05-28
2025-05-29
2025-05-30
2025-05-31
2025-06-01
2025-06-02
2025-06-03
2025-06-04
2025-06-05
2025-06-06
2025-06-07
2025-06-08
2025-06-09
2025-06-10
2025-06-11
2025-06-12
2025-06-13
2025-06-14
2025-06-15
2025-06-16
2025-06-17
2025-06-18
2025-06-19
2025-06-20
2025-06-21
2025-06-22
2025-06-23
2025-06-24
2025-06-25
2025-06-26
2025-06-27
2025-06-28
2025-06-29
2025-06-30
2025-07-01
2025-07-02
2025-07-03
2025-07-04
2025-07-05
2025-07-06
2025-07-07
2025-07-08
2025-07-09
2025-07-10
2025-07-11
2025-07-12
2025-07-13
2025-07-14
2025-07-15
2025-07-16
2025-07-17
2025-07-18
2025-07-19
2025-07-20
2025-07-21
2025-07-22
2025-07-23
2025-07-24
2025-07-25
2025-07-26
2025-07-27
2025-07-28
2025-07-29
2025-07-30
2025-07-31
2025-08-01
2025-08-02
2025-08-03
2025-08-04
2025-08-05
2025-08-06
2025-08-07
2025-08-08
2025-08-09
2025-08-10
2025-08-11
2025-08-12
2025-08-13
2025-08-14
2025-08-15
2025-08-16
2025-08-17
2025-08-18
2025-08-19
2025-08-20
2025-08-21
2025-08-22
2025-08-23
2025-08-24
2025-08-25
2025-08-26
2025-08-27
2025-08-28
2025-08-29
2025-08-30
2025-08-31
2025-09-01
2025-09-02
2025-09-03
2025-09-04
2025-09-05
2025-09-06
2025-09-07
2025-09-08
2025-09-09
2025-09-10
2025-09-11
2025-09-12
2025-09-13
2025-09-14
2025-09-15
2025-09-16
2025-09-17
2025-09-18
2025-09-19
2025-09-20
2025-09-21
2025-09-22
2025-09-23
2025-09-24
2025-09-25
2025-09-26
2025-09-27
2025-09-28
2025-09-29
2025-09-30
2025-10-01
2025-10-02
2025-10-03
2025-10-04
2025-10-05
2025-10-06
2025-10-07
2025-10-08
2025-10-09
2025-10-10
2025-10-11
2025-10-12
2025-10-13
2025-10-14
2025-10-15
2025-10-16
2025-10-17
2025-10-18
2025-10-19
2025-10-20
2025-10-21
2025-10-22
2025-10-23
2025-10-24
2025-10-25
2025-10-26
2025-10-27
2025-10-28
2025-10-29
2025-10-30
2025-10-31
2025-11-01
2025-11-02
2025-11-03
2025-11-04
2025-11-05
2025-11-06
2025-11-07
2025-11-08
2025-11-09
2025-11-10
2025-11-11
2025-11-12
2025-11-13
2025-11-14
2025-11-15
2025-11-16
2025-11-17
2025-11-18
2025-11-19
2025-11-20
2025-11-21
2025-11-22
2025-11-23
2025-11-24
2025-11-25
2025-11-26
2025-11-27
2025-11-28
2025-11-29
2025-11-30
2025-12-01
2025-12-02
2025-12-03
2025-12-04
2025-12-05
2025-12-06
2025-12-07
2025-12-08
2025-12-09
2025-12-10
2025-12-11
2025-12-12
2025-12-13
2025-12-14
2025-12-15
2025-12-16
2025-12-17
2025-12-18
2025-12-19
2025-12-20
2025-12-21
2025-12-22
2025-12-23
2025-12-24
2025-12-25
2025-12-26
2025-12-27
2025-12-28
2025-12-29
2025-12-30
2025-12-31

## ENGICON
advance payment (10%): 3,201,326.3
Riyadh 4 |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4 |  | Invoice 5 |  | Invoice 6 |  | Invoice 7 |  | Invoice 8 |  | Invoice 9
Description | Category | Rate | Quantity | Amount | Quantity2 | Amount3 | Quantity22 | Amount33 | Amount34 | Amount35 | Amount342 | Amount353 | Amount3422 | Amount3533 | Amount3534 | Amount3535 | Amount35342 | Amount35353 | Amount353422 | Amount353533 | Amount353534 | Amount353535
Data collection - A |  | 1005568 | 1 | 1005568 | [5 empty] | 0 |  | 0 |  | 0 |  | 0
Data collection - B |  | 251392 | 1 | 251392 | [5 empty] | 0 |  | 0 |  | 0 |  | 0
Geotechnical - A |  | 815640 | 0.97 | 791170.8 | 0.03 | 24469.2 |  |  |  | 0 |  | 0 |  | 0 |  | 0
Geotechnical - B |  | 203910 | 0.96 | 195753.4 | 0.040001 | 8156.6 |  |  |  | 0 |  | 0 |  | 0 |  | 0
Benchmark - A |  | 318600 | 0.96 | 305855.97 | 0.04 | 12744.03 |  |  |  | 0 |  | 0 |  | 0 |  | 0
Benchmark - B |  | 79650 | 0.92466 | 73648.83 | 0.075344 | 6001.17 |  |  |  | 0 |  | 0 |  | 0 |  | 0
Concept masterplan - A |  | 1564632 |  |  | 1 | 1564632 |  |  |  | 0 |  | 0 |  | 0 |  | 0
Concept masterplan - B |  | 391158 |  |  | 1 | 391158 |  |  |  | 0 |  | 0 |  | 0 |  | 0
Concept Infrastructure - A |  | 1795968 |  |  | 0.4415 | 792922.93 | 0.5585 | 1003045.07 |  | 0 |  | 0 |  | 0 |  | 0
Concept Infrastructure - B |  | 448992 |  |  | 0.4 | 179596.8 | 0.6 | 269395.2 |  | 0 |  | 0 |  | 0 |  | 0
Urban & Arch. Design guidelines - A |  | 425800 |  |  |  | 0 | 1 | 425800 |  | 0 |  | 0 |  | 0 |  | 0
Urban & Arch. Design guidelines - B |  | 106450 |  |  |  | 0 | 1 | 106450 |  | 0 |  | 0 |  | 0 |  | 0
Hydrology/Flood protection - A |  | 55096 |  |  | 0.7 | 38567.2 | 0.3 | 16528.8 |  | 0 |  | 0 |  | 0 |  | 0
Hydrology/Flood protection - B |  | 13774 |  |  | 0.701 | 9655.57 | 0.299 | 4118.43 |  | 0 |  | 0 |  | 0 |  | 0
TIA - A |  | 160696 |  |  | 0.24999 | 40172.39 | 0.75001 | 120523.61 |  | 0 |  | 0 |  | 0 |  | 0
TIA - B |  | 40174 |  |  | 0.25 | 10043.5 | 0.75 | 30130.5 |  | 0 |  | 0 |  | 0 |  | 0
Enabling work package - A |  | 430488 |  |  | 1 | 430488 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Enabling work package - B |  | 107622 |  |  |  |  | 1 | 107622 |  | 0 |  | 0 |  | 0 |  | 0
Detailed masterplan - A |  | 1387432 |  |  |  |  | 0.5 | 693716 | 0.5 | 693716 | [5 empty] | 0
Detailed masterplan - B |  | 346858 |  |  |  |  | 0.5 | 173429 | 0.5 | 173429 | [5 empty] | 0
Detailed infrastructure - A |  | 2303368 |  |  |  |  | 0.51575 | 1187971.4 | 0.48425 | 1115396.6 | [5 empty] | 0
Detailed infrastructure - B |  | 575842 |  |  |  |  | 0.5 | 287921 | 0.5 | 287921 | [5 empty] | 0
Detailed infrastructure (90%) - A |  | 1766120 |  | 0 |  |  |  |  | 0.70992 | 1253797.84 | [5 empty] | 0
Detailed infrastructure (90%) - B |  | 441530 |  | 0 |  |  |  |  | 0.7 | 309071 | [5 empty] | 0
IFT Package - A |  | 395204 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0
IFT Package - B |  | 98801 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0
IFC Pckage - A |  | 395204 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0
IFC Pckage - B |  | 98801 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0
Lead Engineer/ Discipline Engineer | A | 2005 |  | 0 |  | 0 |  | 0 |  | 0 | 200 | 401000 |  |  | 400 | 802000
Sr. Engineer/ Senior discipline specialist | A | 1448 |  | 0 |  | 0 |  | 0 |  | 0 | 200 | 289600 | 150 | 217200 | 350 | 506800 | 200 | 289600
Engineer/ Discipline Specialist | A | 2005 |  | 0 |  | 0 |  | 0 |  | 0 | 400 | 802000 | 200 | 401000 | 400 | 802000 | 500 | 1002500
Draftsman | A | 805 |  | 0 |  | 0 |  | 0 |  | 0 | 400 | 322000 | 150 | 120750 | 250 | 201250 | 850 | 684250 | 350 | 281750
Lead engineer/ discipline expert | A | 450 | [7 empty] | 0 | 100 | 45000 | 300 | 135000 | 500 | 225000 | 300 | 135000 |  | 0
Sr. Engineer/ Senior discipline specialist | A | 320 | [7 empty] | 0 | 200 | 64000 | 300 | 96000 | 700 | 224000 | 400 | 128000 | 200 | 64000
Engineer/ Discipline Specialist | A | 260 | [7 empty] | 0 | 250 | 65000 | 400 | 104000 | 600 | 156000 | 750 | 195000 | 1000 | 260000
Draftsman | A | 175 | [7 empty] | 0 | 192.7601 | 33733.01 | 212.3492 | 37161.11 | 447.5849 | 78327.35 | 206.2722 | 36097.64 | 2817.2914 | 493026
|  | Total | 0 | 2623389 | 0 | 3508607.39 | 0 | 4426651.01 |  | 3833331.44 |  | 2022333.01 |  | 1111111.11 |  | 2995377.35 |  | 2470447.64 |  | 1098776
|  | Adnvance paymnt amount |  | 262338.9 |  | 350860.739 |  | 442665.101 |  | 383333.144 |  | 202233.301 |  | 111111.111 |  | 299537.735 |  | 247044.764 |  | 109877.6
|  | After advance payment discount |  | 2361050.1 |  | 3157746.651 |  | 3983985.909 |  | 3449998.296 |  | 1820099.709 |  | 999999.999 |  | 2695839.615 |  | 2223402.876 |  | 988898.4
|  | VAT |  | 354157.515 |  | 473661.9976 |  | 597597.8863 |  | 517499.7444 |  | 273014.9563 |  | 149999.9998 |  | 404375.9423 |  | 333510.4314 |  | 148334.76
|  | Total with VAT |  | 2715207.615 |  | 3631408.6486 |  | 4581583.7954 |  | 3967498.0404 |  | 2093114.6653 |  | 1149999.9989 |  | 3100215.5573 |  | 2556913.3074 |  | 1137233.16

## SYSTRA
Technology zones - Riyadh |  |  | 15054089 |  | Invoice 1 |  | Invoice 2 |  | Invoice 3 |  | Invoice 4 |  | Invoice 5 |  | Invoice 6
Description | Category | Total Quantity | Remaining Quantity | Rate | Quantity | Amount | Quantity2 | Amount2 | Quantity3 | Amount3 | Quantity32 | Amount33 | Amount34 | Amount35 | Amount36 | Amount37 | Amount38 | Amount39
Lead Engineer/ Discipline Engineer | A1 | 926 | 736 | 471 | 80 | 37680 | 110 | 51810 | 290 | 136590 | 150 | 70650 |  |  | 296 | 139416
Sr. Engineer/ Senior discipline specialist | B1 | 705 | 448.332 | 368 | 100.668 | 37045.82 | 156 | 57408 | 85 | 31280 | 150 | 55200 |  |  | 213.332 | 78506.18
Engineer/ Discipline Specialist | C1 | 1332 | 943 | 263 | 184 | 48392 | 205 | 53915 | 199 | 52337 | 124 | 32612 |  |  | 620 | 163060
Draftsman | D1 | 1626 | 1069 | 179 | 254 | 45466 | 303 | 54237 | 398 | 71242 | 299 | 53521 |  |  | 372 | 66588
Lead engineer/ discipline expert | A2 | 3416 | 2700 | 373 | 150 | 55950 | 566 | 211118 | 888 | 331224 | 1050 | 391650 |  |  | 762 | 284226
Sr. Engineer/ Senior discipline specialist | B2 | 4204 | 3406 | 320 | 310 | 99200 | 488 | 156160 | 901 | 288320 | 1605 | 513600 |  |  | 900 | 288000
Engineer/ Discipline Specialist | C2 | 6548 | 3862 | 240 | 731 | 175440 | 1955 | 469200 | 989 | 237360 | 1781.25 | 427500 |  |  | 1091.75 | 262020
Draftsman | D2 | 8444 | 2800 | 142 | 1222 | 173524 | 4422 | 627924 | 1388 | 197096 | 964.2661 | 136925.78 |  |  | 447.7339 | 63578.22
|  |  |  | Total | 3031.668 | 672697.82 | 8205 | 1681772 | 5138 | 1345449 | 6123.5161 | 1681658.78 |  |  |  | 1345394.4
6726972
Technology zones - Dammam | [8 empty] | Invoice 3 |  | Invoice 4 |  | Invoice 5 |  | Invoice 6
Description | Category | Total Quantity | Remaining Quantity | Rate | Column1 | Column2 | Column3 | Column4 | Quantity3 | Amount3 | Quantity32 | Amount33 | Amount34 | Amount35 | Amount36 | Amount37 | Amount38
Lead Engineer/ Discipline Engineer | A1 | 149 | 149 | 471 | [6 empty] | 14.9 | 7017.9 | 48.49 | 22838.79 | 26.01 | 12250.71
Sr. Engineer/ Senior discipline specialist | B1 | 279.5 | 279.5 | 368 | [6 empty] | 27.95 | 10285.6 | 90.92 | 33458.56 | 48.83 | 17969.44
Engineer/ Discipline Specialist | C1 | 424 | 424 | 263 | [6 empty] | 42.4 | 11151.2 | 137.8 | 36241.4 | 74.2 | 19514.6
Draftsman | D1 | 622 | 622 | 179 | [6 empty] | 62.2 | 11133.8 | 202.15 | 36184.85 | 108.85 | 19484.15
Lead engineer/ discipline expert | A2 | 1440 | 1440 | 373 | [6 empty] | 144 | 53712 | 468 | 174564 | 252 | 93996
Sr. Engineer/ Senior discipline specialist | B2 | 2422 | 2422 | 320 | [6 empty] | 242.2 | 77504 | 787.1 | 251872 | 423.9 | 135648
Engineer/ Discipline Specialist | C2 | 3792 | 3792 | 240 | [6 empty] | 379.2 | 91008 | 1232.4 | 295776 | 663.6 | 159264
Draftsman | D2 | 4805 | 4805 | 142 | [6 empty] | 480.5 | 68231 | 1561.3082 | 221705.77 | 841.1918 | 119449.23
|  |  |  | Total |  |  |  |  | 0 | 0 | 1393.35 | 330043.5 |  | 1072641.37 |  | 577576.13
3300435
Technology zones - Dhahran | [8 empty] | Invoice 3 |  | Invoice 4 |  | Invoice 5 |  | Invoice 6
Description | Category | Total Quantity | Remaining Quantity | Rate | Column1 | Column2 | Column3 | Column4 | Quantity3 | Amount3 | Quantity32 | Amount33 | Amount34 | Amount35 | Amount36 | Amount37 | Amount38 | Amount39
Lead Engineer/ Discipline Engineer | A1 | 149 | 149 | 471 | [6 empty] | 14.9 | 7017.9 | 48.465 | 22827.02 | 26.035 | 12262.48
Sr. Engineer/ Senior discipline specialist | B1 | 279.5 | 279.5 | 368 | [6 empty] | 27.95 | 10285.6 | 90.87 | 33440.16 | 48.88 | 17987.84
Engineer/ Discipline Specialist | C1 | 424 | 424 | 263 | [6 empty] | 42.4 | 11151.2 | 137.8 | 36241.4 | 74.2 | 19514.6
Draftsman | D1 | 622 | 622 | 179 | [6 empty] | 62.2 | 11133.8 | 202.2 | 36193.8 | 108.8 | 19475.2
Lead engineer/ discipline expert | A2 | 1440 | 1440 | 373 | [6 empty] | 144 | 53712 | 468 | 174564 | 252 | 93996
Sr. Engineer/ Senior discipline specialist | B2 | 2422 | 2422 | 320 | [6 empty] | 242.2 | 77504 | 787.15 | 251888 | 423.85 | 135632
Engineer/ Discipline Specialist | C2 | 3792 | 3792 | 240 | [6 empty] | 379.2 | 91008 | 1232.4 | 295776 | 663.6 | 159264
Draftsman | D2 | 4805 | 4805 | 142 | [6 empty] | 480.5 | 68231 | 1561.3451 | 221711 | 841.1549 | 119444
|  |  |  | Total |  |  |  |  | 0 | 0 | 1393.35 | 330043.5 |  | 1072641.38 |  | 577576.12
3300435
Technical review and transport planning expertise support for Riyadh Industrial cities 1 & 4 |  |  |  |  | Invoice 1 | [7 empty] | Invoice 5 |  | Invoice 6
Description | Category | Total Quantity | Remaining Quantity | Rate | Quantity | Amount | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12
Lead Engineer/ Discipline Engineer | A1 | 100 | 100 | 471 | [8 empty] | 70 | 32970 | 30 | 14130
Sr. Engineer/ Senior discipline specialist | B1 | 500 | 500 | 368 | [8 empty] | 350 | 128800 | 150 | 55200
Engineer/ Discipline Specialist | C1 | 800 | 800 | 263 | [8 empty] | 560 | 147280 | 240 | 63120
Draftsman | D1 | 1100 | 1100 | 179 | [8 empty] | 770 | 137830 | 330 | 59070
Lead engineer/ discipline expert | A2 | 539 | 539 | 373 | [8 empty] | 377.26 | 140717.98 | 161.74 | 60329.02
Sr. Engineer/ Senior discipline specialist | B2 | 330 | 330 | 320 | [8 empty] | 231 | 73920 | 99 | 31680
Engineer/ Discipline Specialist | C2 | 1480 | 1480 | 240 | [8 empty] | 1036 | 248640 | 444 | 106560
Draftsman | D2 | 3000 | 3000 | 142 | [8 empty] | 2100 | 298200 | 900 | 127800
|  |  |  | Total | [9 empty] | 1208357.98 |  | 517889.02
1726247

## ENGICON-RDH4
Riyadh 4 entrance |  |  | Invoice 1 |  | Invoice 2 |  | Invoice 3
Description | Category | Rate | Quantity | Amount | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10
Data collection, concept design, detailed design, and tender package A1 |  | 360 | 1500 | 540000 | 2000 | 720000 | 1500 | 540000
Data collection, concept design, detailed design, and tender package B1 |  | 260 | 2000 | 520000 | 2500 | 650000 | 2500 | 650000
Data collection, concept design, detailed design, and tender package C1 |  | 210 | 3000 | 630000 | 3500 | 735000 | 3500 | 735000
Data collection, concept design, detailed design, and tender package |  | 145 | 2137.93 | 309999.85 | 1689.6552 | 245000 | 5172.4138 | 750000
|  | Total |  | 1999999.85 |  | 2350000 |  | 2675000
|  | VAT |  | 299999.9775 |  | 352500 |  | 401250
|  | Total with VAT |  | 2299999.8275 |  | 2702500 |  | 3076250